## QH WBS Master (hidden)
QldHydro Revised WBS Structure
Current at 7/03/2024
ENTERPRISE
L0 - Program |  | L1 - Projects |  | L2 - Phases |  | L3 - Area |  | L4 - Element |  | L5 - Sub Element | Borumba Control Account | L5 - Sub Element | Pioneer-Burdekin Control Account
Group ID | Group Description | Group ID | Group Description | Group ID | Group Description | Group ID | Group Description | Group ID | Group Description | Group ID | Group Description | Group ID | Group Description
QH | QLD Hydro PHES | BRI | Borumba PHES | P0 | Program | 1 | QH Costs | 10000 | QH Delivery (Staff) | 110010 | Project (Staff) | 10010 | Project (Staff)
|  | PBI | Pioneer-Burdekin PHES | P1 | Feasibility Studies | 2 | Surface Infrastructure and Enabling | 11000 | Project Contractors | 110020 | Commercial (Staff) | 10020 | Commercial (Staff)
|  | PRG | Program / Corporate | P2 | Options Analysis & DAR | 3 | Underground Waterways | 12000 | Engineering | 110030 | Engineering Assurance (Staff) | 10030 | Engineering Assurance (Staff)
|  |  |  | P3 | Design Development & Procurement | 4 | Underground Access & Caverns | 13000 | Environment and Approvals | 110040 | Health & Safety (Staff) | 10040 | Health & Safety (Staff)
|  |  |  | P4 | Delivery | 5 | Powerhouse Mech & Elec | 14000 | Community Development and Stakeholder | 110050 | Project Controls (Staff) | 10050 | Project Controls (Staff)
|  |  |  | P5 | Transition to Operations | 6 | Lower Reservoir | 15000 | Heath and Safety | 110060 | Environment (Staff) | 10060 | Environment (Staff)
|  |  |  | P6 | Close-out | 7 | Upper Reservoir | 16000 | Land Acquisition | 110070 | Community and Stakeholder (Staff) | 10070 | Community and Stakeholder (Staff)
[6 empty] | 8 | Transmissions | 17000 | Indirect | 110080 | Land (Staff) | 10080 | Land (Staff)
[6 empty] | 9 | Contingency & Escalation | 18000 | Ops Readiness & Commissioning | 110090 | Regional Development (Staff) | 10090 | Regional Development (Staff)
[8 empty] | 20100 | Contractor Indirect & overheads | 110100 | Quality (Staff) | 10100 | Quality (Staff)
[8 empty] | 20200 | Design | 120010 | Project Support | 11010 | Project Support
[8 empty] | 20300 | Camps | 120020 | Commercial Pre-Contracts | 11020 | Commercial Pre-Contracts
|  |  |  | Previous Revision WBS |  |  |  | 20400 | Geotechnical | 120030 | Commercial - Contracts Admin | 11030 | Commercial - Contracts Admin
|  |  |  | L3 - Work Package |  | L4 - Area | Used for Scope Package Coding | 20500 | Temporary Water Infrastructure | 120040 | Project Controls | 11040 | Project Controls
|  |  |  | Group ID | Group Description | Group ID | Group Description | 20600 | Communication Infrastructure Upgrade | 120050 | Legal | 11050 | Legal
|  |  |  | W01 | Project Management & Overheads | 1 | Client Costs | 20700 | Power Supply Upgrade | 120060 | Health and Safety Consultants | 11060 | Engineering Assurance
|  |  |  | W02 | Health & Safety | 2 | Exploratory & Enabling Works | 21000 | Yabba Creek Road Option 1 | 120070 | Engineering Assurance | 11070 | Operation and Maintenance Strategy
|  |  |  | W03 | Community & Stakeholder Engagement | 3 | Lower Reservoir | 21200 | Old Forestry Drive Option 2 | 120080 | Operation and Maintenance Strategy | 12010 | Specialist Engineering - External Advisory Services
|  |  |  | W04 | Cultural Heritage & Native Title | 4 | Upper Reservoir | 21300 | Yielo Rd | 130010 | Specialist Engineering - External Advisory Services | 12020 | Specialist Engineering - Owners Engineer
|  |  |  | W05 | Land Access & Acquisition | 5 | Waterways, Tunnels & Caverns | 21400 | Walkers Top Access Track | 130020 | Specialist Engineering - Owners Engineer | 12030 | Specialist Engineering - Design for Procurement
|  |  |  | W06 | Environment & Approvals | 6 | Transmission Lines | 21500 | Access Roads - The Borgan | 130030 | Specialist Engineering - Design for Procurement | 12040 | Specialist Engineering - FEED
|  |  |  | W07 | Geotechnical | 7 | Land Acquisition | 21600 | Lower Res Access Road | 130040 | Specialist Engineering - FEED | 12050 | Specialist Engineering - Exploratory Works
|  |  |  | W08 | Procurement & Commercial |  |  | 21700 | Lower Res Haul Road - Construct and Maintain | 130050 | Specialist Engineering - Exploratory Works | 12060 | Specialist Advisors - Technical Assurance
|  |  |  | W09 | Engineering & Design |  |  | 21800 | Bella Creek Road | 130060 | Specialist Advisors - Technical Assurance | 12070 | Connection Application Process/Services
|  |  |  | W10 | Exploratory Works |  |  | 21900 | Yabba Creek Bridge | 130070 | Connection Application Process/Services | 12080 | Independent certifier
|  |  |  | W11 | Enabling & Surface Works |  |  | 22000 | Kingaham Creek Bridge | 130080 | Independent certifier | 13010 | Technical Advisors - EIS Approvals and Studies
|  |  |  | W12 | Main Facility - Stage 1 |  |  | 22100 | Road to Lower Inlet / Outlet Structure | 140010 | Technical Advisors - EIS Approvals and Studies | 13020 | EIS - Engineering Input
|  |  |  | W13 | Main Facility - Stage 2 |  |  | 22200 | Road to Upper Res/Saddle Dam | 140020 | EIS - Engineering Input | 13030 | EIS - Technical Studies
|  |  |  | W14 | Lower Reservoir |  |  | 22300 | Ring Road at Upper Res incl. Access to upper intake and Bellmouth | 140030 | EIS - Technical Studies | 13040 | Exploratory Works Approvals
|  |  |  | W15 | Upper Reservoir |  |  | 30100 | Contractor Indirect & overheads stage 1 | 140040 | Exploratory Works Approvals | 13050 | Main Works - Approvals
|  |  |  | W16 | Mechanical & Electrical |  |  | 30200 | Design | 140050 | Main Works - Approvals | 13060 | Offset Implementation
|  |  |  | W17 | Transmissions |  |  | 31000 | North Alignment Waterway | 140060 | Offset Implementation | 13070 | Sustainability
|  |  |  | W18 | Commissioning |  |  | 32000 | South Alignment Waterway | 140070 | Sustainability | 13080 | Office of the Coordinator-General (OCG Costs)
|  |  |  | W19 | Contingency & Escalation |  |  | 33000 | Platform and Control Buildings | 140080 | Office of the Coordinator-General (OCG Costs) | 13090 | EIS - Delivery
[8 empty] | 34000 | Lower Inlet Structure Approach | 140090 | EIS - Delivery | 13100 | GIS Support
|  |  |  | L3 - Area | PB Proposed |  |  | 35000 | Surge Tanks Permanent access tunnel | 140100 | GIS Support | 13110 | Cultural Heritage - Investigations and Monitoring
|  |  |  | Group ID | Group Description |  |  | 36000 | Assembly Chambers | 140110 | Cultural Heritage - Investigations and Monitoring | 13120 | Indigenous Land Use Agreement
|  |  |  | PM | Project Management |  |  | 37000 | Site Rehabilitation | 140120 | Indigenous Land Use Agreement | 13130 | Compliance Monitoring
|  |  |  | DP | Design & Procurement |  |  | 40100 | Contractor Indirect & overheads | 140130 | Compliance Monitoring | 13140 | Indigenous Partnerships
|  |  |  | AP | Property & Approvals |  |  | 40200 | Design | 140140 | Indigenous Partnerships | 14010 | Community and Stakeholder Consultants
|  |  |  | SI | Surface Infrastructure and Enabling Works |  |  | 40300 | Site Clearing | 150010 | Community and Stakeholder Consultants | 14020 | Community Benefits Program
|  |  |  | UG | Underground Works |  |  | 40400 | Construction Surface Facilities | 150020 | Community Benefits Program | 14030 | Sponsorships
|  |  |  | UR | Upper Reservoir |  |  | 40500 | ECTV Exploratory Drilling | 150030 | Sponsorships | 14040 | Community Engagement Program
|  |  |  | LR | Lower Reservoir |  |  | 40600 | MAT and ECVT | 150040 | Community Engagement Program | 14050 | Regional Development
|  |  |  | BR | Roadworks and Bridges |  |  | 40700 | Power Cavern | 150050 | Regional Development | 14060 | Regional Development Accommodation Partners
[8 empty] | 40800 | Transformer Cavern | 150060 | Regional Development Accommodation Partners | 14070 | Regional Development Community Infrastructure
[8 empty] | 40900 | IPB Galleries (x 6) | 150070 | Regional Development Community Infrastructure | 14080 | Regional Development - Community Development Initiatives (GRC)
[8 empty] | 41000 | MAT Tunnels between Power Cavern and Transformer Cavern | 150080 | Regional Development - Community Development Initiatives (GRC) | 14090 | Regional Development - Community Development Initiatives (SRC)
[8 empty] | 41100 | Site Rehabilitation | 150090 | Regional Development - Community Development Initiatives (SRC) | 15010 | PPE
[8 empty] | 50100 | Contractor Indirect & overheads | 160010 | Land Access & Conveyancing | 15020 | Health and Safety Consultants
[8 empty] | 50200 | Design | 160020 | Land Acquisition | 15030 | Mandatory Safety Training
[8 empty] | 50300 | Mech & Elec | 160030 | Land Access - Specialist Advisors | 15040 | Emergency Response Plan
[8 empty] | 50400 | Power Turbines | 170010 | Project Expenses – General | 16010 | Land Access & Conveyancing
[8 empty] | 50500 | Transformers | 170020 | PPE | 16020 | Land Acquisition
[8 empty] | 50600 | Hydro-Mechanical Works | 170030 | Emergency Response Plan | 16030 | Land Access - Specialist Advisors
[8 empty] | 50700 | Electrical Install | 170040 | Travel, Accommodation & Disbursements | 17010 | Project Expenses – General
[8 empty] | 50800 | Power Evacuation and Grid Connection | 170050 | IT Software, Licenses & Equipment | 17020 | Travel, Accommodation & Disbursements
[8 empty] | 50900 | Commissioning OEM | 170060 | Training & Development (Delivery) | 17030 | IT Software, Licenses & Equipment
[8 empty] | 51000 | Site Rehabilitation | 170070 | Mandatory Safety Training | 17040 | Training & Development
[8 empty] | 60100 | Contractor Indirect & overheads | 170080 | Site Vehicles and Transport | 17050 | Site Vehicles and Transport
[8 empty] | 60200 | Design | 170090 | Project Offices and Facilities | 17060 | Project Offices and Facilities
[8 empty] | 60300 | Site Clearing | 170100 | Portable Long Service Leave Levy | 17070 | Portable Long Service Leave Levy
[8 empty] | 60400 | Quarry Development and Material Operations | 170110 | Insurances | 17080 | Insurances
[8 empty] | 60500 | Diversion and Watering | 170120 | Bid cost reimbursement | 17090 | Bid cost reimbursement
[8 empty] | 60600 | Foundations | 170130 | Site Equipment & Tooling | 17100 | Site Equipment & Tooling
[8 empty] | 60700 | Dam Construction | 170140 | Corporate Overheads | 17110 | Corporate Overheads
[8 empty] | 60800 | Spillway | 170150 | Legal Costs | 17120 | Legal Costs
[8 empty] | 60900 | Intake Tower | 170160 | Site Communications | 17130 | Site Communications
[8 empty] | 61000 | Outlet Works | 170170 | Finance costs (FBT) | 17140 | Finance costs (FBT)
[8 empty] | 61100 | Fishway | 170180 | Other Staff Costs (memberships, subscriptions) | 17150 | Other Staff Costs (memberships, subscriptions)
[8 empty] | 61200 | Over topping Event of the Lower Dam | 180010 | Op Readiness | 18010 | Op Readiness
[8 empty] | 61300 | Traffic Control | 180020 | Commissioning | 18020 | Commissioning
[8 empty] | 61400 | Site Rehabilitation | 180030 | Full Load Compliance Testing | 18030 | Full Load Compliance Testing
[8 empty] | 70100 | Contractor Indirect & overheads | 201010 | Temporary Camps - Indirects and Overheads | 20110 | Temporary Camps - Indirects and Overheads
[8 empty] | 70200 | Design | 201020 | Main Camps - Indirects and Overheads | 20120 | Main Camps - Indirects and Overheads
[8 empty] | 70300 | Site Clearing | 201030 | Exploratory Works - Contractor Indirect & overheads | 20130 | Exploratory Works - Contractor Indirect & overheads
[8 empty] | 70400 | Quarry Development and Material Operations | 201040 | Enabling Works - Contractor Indirect & overheads | 20140 | Enabling Works - Contractor Indirect & overheads
[8 empty] | 70500 | Diversion and Watering | 202010 | Design - Exploratory Works | 20210 | Design - Exploratory Works
[8 empty] | 70600 | Foundations | 202020 | Design - Enabling Works | 20220 | Design - Enabling Works
[8 empty] | 70700 | Dam Construction | 202030 | Temp Camps Design | 20230 | Temp Camps Design
[8 empty] | 70800 | Emergency Spillway | 203010 | Temp Camps | 20310 | Temp Camps
[8 empty] | 70900 | Traffic Control | 203020 | Upper Res Camps Hardstand | 20320 | Upper Res Camps Hardstand
[8 empty] | 71000 | Site Rehabilitation | 203030 | Lower Res Camps Hardstand | 20330 | Lower Res Camps Hardstand
[8 empty] | 80000 | Borumba - Tarong 275kV | 203040 | Main Camps Hardstand | 20340 | Main Camps Hardstand
[8 empty] | 80100 | Borumba - Woolooga 275kV | 203050 | Upper Res Camps Install and Operate | 20350 | Upper Res Camps Install and Operate
[8 empty] | 99100 | Contingency | 203060 | Lower Res Camps Install and Operate | 20360 | Lower Res Camps Install and Operate
[8 empty] | 99500 | Escalation | 203070 | Main Camps Install and Operate | 20370 | Main Camps Install and Operate
[10 empty] | 203080 | Camp Set up | 20380 | Camp Set up
[10 empty] | 204010 | Contractor Indirect & overheads | 20410 | Contractor Indirect & overheads
[10 empty] | 204020 | Geotechnical Studies | 20420 | Geotechnical Studies
[10 empty] | 204030 | Geotechnical Drilling | 20430 | Geotechnical Drilling
[10 empty] | 204040 | Geotechnical Service Management | 20440 | Geotechnical Service Management
[10 empty] | 205010 | Preliminaries Temporary Water Infrastructure | 20510 | Preliminaries Temporary Water Infrastructure
[10 empty] | 205020 | Temporary Water Infrastructure | 20520 | Temporary Water Infrastructure
[10 empty] | 205030 | Temporary Water Supply | 20530 | Temporary Water Supply
[10 empty] | 206010 | Preliminaries Communication Infrastructure Upgrade | 20610 | Preliminaries Communication Infrastructure Upgrade
[10 empty] | 206020 | Communication Infrastructure Upgrade | 20620 | Communication Infrastructure Upgrade
[10 empty] | 207010 | Preliminaries Power Supply Upgrade | 20710 | Preliminaries Power Supply Upgrade
[10 empty] | 207020 | Power Supply Upgrade | 20720 | Power Supply Upgrade
[10 empty] | 210010 | Preliminaries Yabba Ck Rd Option 1 | 21010 | Preliminaries Yabba Ck Rd Option 1
[10 empty] | 210020 | Bridge 1 (on Yabba Ck Rd - Ana Branche No 1) | 21020 | Bridge 1 (on Yabba Ck Rd - Ana Branche No 1)
[10 empty] | 210030 | Bridge 2 (on Yabba Ck Rd - Ana Branche No 2) | 21030 | Bridge 2 (on Yabba Ck Rd - Ana Branche No 2)
[10 empty] | 210040 | Bridge 3 (on Yabba Ck Rd - No 1 Crossing - Neumans Crossing) | 21040 | Bridge 3 (on Yabba Ck Rd - No 1 Crossing - Neumans Crossing)
[10 empty] | 210050 | Bridge 4 (on Yabba Ck Rd - No 2 Crossing - Elbow Crossing) | 21050 | Bridge 4 (on Yabba Ck Rd - No 2 Crossing - Elbow Crossing)
[10 empty] | 210060 | Bridge 5 (on Yabba Ck Rd - No 3 Crossing - Andrews Crossing) | 21060 | Bridge 5 (on Yabba Ck Rd - No 3 Crossing - Andrews Crossing)
[10 empty] | 210070 | Bridge 6 (on Yabba Ck Rd - No ? Crossing - ????) | 21070 | Bridge 6 (on Yabba Ck Rd - No ? Crossing - ????)
[10 empty] | 210080 | Bridge 7 (on Yabba Ck Rd - No 4 Crossing - Boardmans Crossing) | 21080 | Bridge 7 (on Yabba Ck Rd - No 4 Crossing - Boardmans Crossing)
[10 empty] | 210090 | Bridge 8 (on Yabba Ck Rd - No 5 Crossing - Friends Crossing) | 21090 | Bridge 8 (on Yabba Ck Rd - No 5 Crossing - Friends Crossing)
[10 empty] | 210100 | Bridge 9 (on Yabba Ck Rd - No 6 Crossing - Deep Crossing) | 21100 | Bridge 9 (on Yabba Ck Rd - No 6 Crossing - Deep Crossing)
[10 empty] | 210110 | Bridge 10 (on Yabba Ck Rd - No 7 - Crossing - unknown name) | 21110 | Bridge 10 (on Yabba Ck Rd - No 7 - Crossing - unknown name)
[10 empty] | 210120 | Upgrade Bella Creek Road intersection | 21120 | Upgrade Bella Creek Road intersection
[10 empty] | 212010 | Preliminaries Old Forestry Drive Option 2 | 21210 | Preliminaries Old Forestry Drive Option 2
[10 empty] | 212020 | Old Forestry Drive Option 2 Construction | 21220 | Old Forestry Drive Option 2 Construction
[10 empty] | 213010 | Preliminaries Upgrade of Yielo Rd | 21310 | Preliminaries Upgrade of Yielo Rd
[10 empty] | 213020 | Upgrade of Yielo Rd Construction | 21320 | Upgrade of Yielo Rd Construction
[10 empty] | 214010 | Preliminaries Walkers Top Access Track | 21410 | Preliminaries Walkers Top Access Track
[10 empty] | 214020 | Walkers Top Access Track Construction | 21420 | Walkers Top Access Track Construction
[10 empty] | 215010 | Preliminaries Access Roads - The Borgan | 21510 | Preliminaries Access Roads - The Borgan
[10 empty] | 215020 | Access Roads - The Borgan | 21520 | Access Roads - The Borgan
[10 empty] | 216010 | Lower Res Access Road | 21610 | Lower Res Access Road
[10 empty] | 217010 | Lower Res Haul Road - Construct and Maintain | 21710 | Lower Res Haul Road - Construct and Maintain
[10 empty] | 218010 | Bella Creek Road | 21810 | Bella Creek Road
[10 empty] | 219010 | Yabba Creek Bridge | 21910 | Yabba Creek Bridge
[10 empty] | 220010 | Kingaham Creek Bridge | 22010 | Kingaham Creek Bridge
[10 empty] | 221010 | Road to Lower Inlet / Outlet Structure | 22110 | Road to Lower Inlet / Outlet Structure
[10 empty] | 222010 | Road to Upper Res/Saddle Dam | 22210 | Road to Upper Res/Saddle Dam
[10 empty] | 223010 | Ring Road at Upper Res incl. Access to upper intake and Bellmouth | 22310 | Ring Road at Upper Res incl. Access to upper intake and Bellmouth
[10 empty] | 224010 | MAT / ECVT Portal Pad Excavation | 30110 | Contractor Indirects & overheads
[10 empty] | 301110 | Contractor Indirects & overheads | 30210 | Design
[10 empty] | 302210 | Design | 31010 | Upper Inlet/Outlet Structure Bellmouth - North
[10 empty] | 310010 | Upper Inlet/Outlet Structure Bellmouth - North | 31020 | Upper Inlet/Outlet Structure Gate Shaft - North
[10 empty] | 310020 | Upper Inlet/Outlet Structure Gate Shaft - North | 31030 | Lower Inlet/Outlet Structure Bellmouth - North
[10 empty] | 310030 | Lower Inlet/Outlet Structure Bellmouth - North | 31040 | Lower Inlet/Outlet Structure Gate Shaft Middle to Top - North
[10 empty] | 310040 | Lower Inlet/Outlet Structure Gate Shaft Middle to Top - North | 31050 | Lower Inlet/Outlet Structure Gate Shaft Lower Part/Square Section - North
[10 empty] | 310050 | Lower Inlet/Outlet Structure Gate Shaft Lower Part/Square Section - North | 31060 | Low Pressure Tunnel - North
[10 empty] | 310060 | Low Pressure Tunnel - North | 31070 | Erection Chamber - Upper - North
[10 empty] | 310070 | Erection Chamber - Upper - North | 31080 | Vertical Pressure Shaft - North
[10 empty] | 310080 | Vertical Pressure Shaft - North | 31090 | Erection Chamber - Lower - North
[10 empty] | 310090 | Erection Chamber - Lower - North | 31100 | High Pressure Tunnel - North
[10 empty] | 310100 | High Pressure Tunnel - North | 31110 | Penstock Steel Lined - North
[10 empty] | 310110 | Penstock Steel Lined - North | 31120 | Tailrace Collector Tunnel - North
[10 empty] | 310120 | Tailrace Collector Tunnel - North | 31130 | Tailrace Tunnel - North
[10 empty] | 310130 | Tailrace Tunnel - North | 31140 | Surge Tank - North
[10 empty] | 310140 | Surge Tank - North | 32010 | Upper Inlet/Outlet Structure Bellmouth - South
[10 empty] | 320010 | Upper Inlet/Outlet Structure Bellmouth - South | 32020 | Upper Inlet/Outlet Structure Gate Shaft - South
[10 empty] | 320020 | Upper Inlet/Outlet Structure Gate Shaft - South | 32030 | Lower Inlet/Outlet Structure Bellmouth - South
[10 empty] | 320030 | Lower Inlet/Outlet Structure Bellmouth - South | 32040 | Lower Inlet/Outlet Structure Gate Shaft Middle to Top - South
[10 empty] | 320040 | Lower Inlet/Outlet Structure Gate Shaft Middle to Top - South | 32050 | Lower Inlet/Outlet Structure Gate Shaft Lower Part/Square Section - South
[10 empty] | 320050 | Lower Inlet/Outlet Structure Gate Shaft Lower Part/Square Section - South | 32060 | Low Pressure Tunnel - South
[10 empty] | 320060 | Low Pressure Tunnel - South | 32070 | Erection Chamber - Upper - South
[10 empty] | 320070 | Erection Chamber - Upper - South | 32080 | Vertical Pressure Shaft - South
[10 empty] | 320080 | Vertical Pressure Shaft - South | 32090 | Erection Chamber - Lower - South
[10 empty] | 320090 | Erection Chamber - Lower - South | 32100 | High Pressure Tunnel - South
[10 empty] | 320100 | High Pressure Tunnel - South | 32110 | Penstock Steel Lined - South
[10 empty] | 320110 | Penstock Steel Lined - South | 32120 | Tailrace Collector Tunnel - South
[10 empty] | 320120 | Tailrace Collector Tunnel - South | 32130 | Tailrace Tunnel - South
[10 empty] | 320130 | Tailrace Tunnel - South | 32140 | Surge Tank - South
[10 empty] | 320140 | Surge Tank - South | 33010 | Upper Inlet/Outlet Platform and Control Building
[10 empty] | 330010 | Upper Inlet/Outlet Platform and Control Building | 33020 | Lower Inlet/Outlet Platform and Control Building
[10 empty] | 330020 | Lower Inlet/Outlet Platform and Control Building | 34010 | Lower Inlet/Outlet Structure - Approach
[10 empty] | 340010 | Lower Inlet/Outlet Structure - Approach | 35010 | Surge Tanks Permanent access tunnel
[10 empty] | 350010 | Surge Tanks Permanent access tunnel | 36010 | Upstream Assembly Chambers, Connection Tunnels and Adit
[10 empty] | 360010 | Upstream Assembly Chambers, Connection Tunnels and Adit | 36020 | Downstream Assembly Chambers, Connection Tunnels and Adit
[10 empty] | 360020 | Downstream Assembly Chambers, Connection Tunnels and Adit | 37010 | Site Rehabilitation
[10 empty] | 370010 | Site Rehabilitation | 40110 | Contractor Indirects & overheads
[10 empty] | 401010 | Contractor Indirects & overheads | 40210 | Detail Design - Main Facility
[10 empty] | 402010 | Detail Design - Main Facility | 40220 | Detail Design - OEM
[10 empty] | 402020 | Detail Design - OEM | 40310 | Site Clearing
[10 empty] | 403010 | Site Clearing | 40410 | Construction Site Facilities - Platform Areas
[10 empty] | 404010 | Construction Site Facilities - Platform Areas | 40420 | Grout plant - mobilise and demobilise
[10 empty] | 404020 | Grout plant - mobilise and demobilise | 40430 | Construction Site Facilities - Platform 2 - Concrete Plant
[10 empty] | 404030 | Construction Site Facilities - Platform 2 - Concrete Plant | 40440 | Concrete batching plant - mobilise and demobilise
[10 empty] | 404040 | Concrete batching plant - mobilise and demobilise | 40450 | Construction Site Facilities - Upper inlet / outlet - Concrete Plant
[10 empty] | 404050 | Construction Site Facilities - Upper inlet / outlet - Concrete Plant | 40510 | Exploratory Tunnel - Surface Works
[10 empty] | 405010 | Exploratory Tunnel - Surface Works | 40520 | Exploratory Tunnel - Underground Works
[10 empty] | 405020 | Exploratory Tunnel - Underground Works | 40530 | Exploratory Tunnel - Caverns Investigation
[10 empty] | 405030 | Exploratory Tunnel - Caverns Investigation | 40540 | Exploratory Tunnel - Management Services
[10 empty] | 405040 | Exploratory Tunnel - Management Services | 40610 | Main Access Tunnel (MAT)
[10 empty] | 406010 | Main Access Tunnel (MAT) | 40620 | Emergency, Cable and Ventilation Tunnel (ECVT) Completion
[10 empty] | 406020 | Emergency, Cable and Ventilation Tunnel (ECVT) Completion | 40710 | Power Cavern
[10 empty] | 407010 | Power Cavern | 40810 | Transformer Cavern
[10 empty] | 408010 | Transformer Cavern | 40910 | IPB Galleries (x 6)
[10 empty] | 409010 | IPB Galleries (x 6) | 41010 | MAT Tunnels between Power Cavern and Transformer Cavern
[10 empty] | 410010 | MAT Tunnels between Power Cavern and Transformer Cavern | 41110 | Site Rehabilitation
[10 empty] | 411010 | Site Rehabilitation | 50110 | Contractor Indirects & overheads
[10 empty] | 501010 | Contractor Indirects & overheads | 50210 | Design
[10 empty] | 502010 | Design | 50310 | Mech & Elec
[10 empty] | 503010 | Mech & Elec | 50410 | Power Turbines
[10 empty] | 504010 | Power Turbines | 50510 | Transformers
[10 empty] | 505010 | Transformers | 50610 | Hydro-Mechanical Works
[10 empty] | 506010 | Hydro-Mechanical Works | 50710 | Electrical Install
[10 empty] | 507010 | Electrical Install | 50810 | Power Evacuation and Grid Connection
[10 empty] | 508010 | Power Evacuation and Grid Connection | 50910 | Commissioning OEM
[10 empty] | 509010 | Commissioning OEM | 51010 | Site Rehabilitation
[10 empty] | 510010 | Site Rehabilitation | 60110 | Contractor Indirect & overheads
[10 empty] | 601010 | Contractor Indirect & overheads | 60210 | Design
[10 empty] | 602010 | Design | 60310 | Site Clearing
[10 empty] | 603010 | Site Clearing | 60410 | Quarry Development and Material Operations
[10 empty] | 604010 | Quarry Development and Material Operations | 60510 | Diversion and Watering
[10 empty] | 605010 | Diversion and Watering | 60610 | Foundations
[10 empty] | 606010 | Foundations | 60710 | Dam Construction
[10 empty] | 607010 | Dam Construction | 60810 | Spillway
[10 empty] | 608010 | Spillway | 60910 | Intake Tower
[10 empty] | 609010 | Intake Tower | 61010 | Outlet Works
[10 empty] | 610010 | Outlet Works | 61110 | Fishway
[10 empty] | 611010 | Fishway | 61210 | Over topping Event of the Lower Dam
[10 empty] | 612010 | Over topping Event of the Lower Dam | 61310 | Traffic Control
[10 empty] | 613010 | Traffic Control | 61410 | Site Rehabilitation
[10 empty] | 614010 | Site Rehabilitation | 70110 | Contractor Indirect & overheads
[10 empty] | 701010 | Contractor Indirect & overheads | 70210 | Design
[10 empty] | 702010 | Design | 70310 | Site Clearing
[10 empty] | 703010 | Site Clearing | 70410 | Quarry Development and Material Operations
[10 empty] | 704010 | Quarry Development and Material Operations | 70510 | Diversion and Watering
[10 empty] | 705010 | Diversion and Watering | 70610 | Foundations
[10 empty] | 706010 | Foundations | 70710 | Main CFRD Dam
[10 empty] | 707010 | Main CFRD Dam | 70720 | Main Saddle (CFRD) Dam
[10 empty] | 707020 | Main Saddle (CFRD) Dam | 70730 | Secondary Saddle (CFRD) Dam A
[10 empty] | 707030 | Secondary Saddle (CFRD) Dam A | 70740 | Secondary Saddle (CFRD) Dam B1
[10 empty] | 707040 | Secondary Saddle (CFRD) Dam B1 | 70750 | Secondary Saddle (CFRD) Dam B2
[10 empty] | 707050 | Secondary Saddle (CFRD) Dam B2 | 70760 | Secondary Saddle (CFRD) Dam No.B3
[10 empty] | 707060 | Secondary Saddle (CFRD) Dam No.B3 | 70810 | Emergency Spillway
[10 empty] | 708010 | Emergency Spillway | 70910 | Traffic Control
[10 empty] | 709010 | Traffic Control | 71010 | Site Rehabilitation
[10 empty] | 710010 | Site Rehabilitation | 80010 | Borumba - Tarong 275kV
[10 empty] | 801010 | Borumba - Tarong 275kV | 80110 | Borumba - Woolooga 275kV
[10 empty] | 802110 | Borumba - Woolooga 275kV | 99110 | P50 Contingency QH Costs
[10 empty] | 991010 | P50 Contingency QH Costs | 99120 | P90 Contingency QH Costs
[10 empty] | 991020 | P90 Contingency QH Costs | 99130 | P50 Contingency Surface Infrastructure and Enabling
[10 empty] | 991030 | P50 Contingency Surface Infrastructure and Enabling | 99140 | P90 Contingency Surface Infrastructure and Enabling
[10 empty] | 991040 | P90 Contingency Surface Infrastructure and Enabling | 99150 | P50 Contingency Underground Waterways
[10 empty] | 991050 | P50 Contingency Underground Waterways | 99160 | P90 Contingency Underground Waterways
[10 empty] | 991060 | P90 Contingency Underground Waterways | 99170 | P50 Contingency Underground Access & Caverns
[10 empty] | 991070 | P50 Contingency Underground Access & Caverns | 99180 | P90 Contingency Underground Access & Caverns
[10 empty] | 991080 | P90 Contingency Underground Access & Caverns | 99190 | P50 Contingency Powerhouse Mech & Elec
[10 empty] | 991090 | P50 Contingency Powerhouse Mech & Elec | 99200 | P90 Contingency Powerhouse Mech & Elec
[10 empty] | 991100 | P90 Contingency Powerhouse Mech & Elec | 99210 | P50 Contingency Lower Reservoir
[10 empty] | 991110 | P50 Contingency Lower Reservoir | 99220 | P90 Contingency Lower Reservoir
[10 empty] | 991120 | P90 Contingency Lower Reservoir | 99230 | P50 Contingency Upper Reservoir
[10 empty] | 991130 | P50 Contingency Upper Reservoir | 99240 | P90 Contingency Upper Reservoir
[10 empty] | 991140 | P90 Contingency Upper Reservoir | 99510 | Escalation QH Costs
[10 empty] | 995010 | Escalation QH Costs | 99520 | Escalation Surface Infrastructure and Enabling
[10 empty] | 995020 | Escalation Surface Infrastructure and Enabling | 99530 | Escalation Underground Waterways
[10 empty] | 995030 | Escalation Underground Waterways | 99540 | Escalation Underground Access & Caverns
[10 empty] | 995040 | Escalation Underground Access & Caverns | 99550 | Escalation Powerhouse Mech & Elec
[10 empty] | 995050 | Escalation Powerhouse Mech & Elec | 99560 | Escalation Lower Reservoir
[10 empty] | 995060 | Escalation Lower Reservoir | 99570 | Escalation Upper Reservoir
[10 empty] | 995070 | Escalation Upper Reservoir

## Example_Previous (hidden)
OBS ID | OBS Area | WBS Level 4 - ID | WBS Level 4 | WBS Level 5- ID | WBS Level 5 | WBS | Level | Responsible
2 | Surface Infrastructure and Enabling | 00 | Surface Infrastructure and Enabling | 00 | Surface Infrastructure and Enabling | 20000 | 3
2 | Surface Infrastructure and Enabling | 20 | Kingaham Creek Bridge | 00 | Kingaham Creek Bridge | 22000 | 4
2 | Surface Infrastructure and Enabling | 20 | Kingaham Creek Bridge | 10 | Kingaham Creek Bridge | 22010 | 5 | Aiden Goggins
2 | Surface Infrastructure and Enabling | 21 | Road to Lower Inlet / Outlet Structure | 00 | Road to Lower Inlet / Outlet Structure | 22100 | 4
2 | Surface Infrastructure and Enabling | 21 | Road to Lower Inlet / Outlet Structure | 10 | Road to Lower Inlet / Outlet Structure | 22110 | 5 | Aiden Goggins
2 | Surface Infrastructure and Enabling | 22 | Road to Upper Res/Saddle Dam | 00 | Road to Upper Res/Saddle Dam | 22200 | 4
2 | Surface Infrastructure and Enabling | 22 | Road to Upper Res/Saddle Dam | 10 | Road to Upper Res/Saddle Dam | 22210 | 5 | Aiden Goggins
2 | Surface Infrastructure and Enabling | 23 | Ring Road at Upper Res incl. Access to upper intake and Bellmouth | 00 | Ring Road at Upper Res incl. Access to upper intake and Bellmouth | 22300 | 4
2 | Surface Infrastructure and Enabling | 23 | Ring Road at Upper Res incl. Access to upper intake and Bellmouth | 10 | Ring Road at Upper Res incl. Access to upper intake and Bellmouth | 22310 | 5 | Aiden Goggins
3 | Underground Waterways | 00 | Underground Waterways | 00 | Underground Waterways | 30000 | 3
3 | Underground Waterways | 01 | Contractor Indirect & overheads stage 1 | 00 | Contractor Indirect & overheads stage 1 | 30100 | 4
3 | Underground Waterways | 01 | Contractor Indirect & overheads stage 1 | 10 | Contractor Indirect & overheads | 30110 | 5
3 | Underground Waterways | 02 | Design | 00 | Design | 30200 | 4
3 | Underground Waterways | 02 | Design | 10 | Design | 30210 | 5
3 | Underground Waterways | 10 | North Alignment Waterway | 00 | North Alignment Waterway | 31000 | 4
3 | Underground Waterways | 10 | North Alignment Waterway | 10 | Upper Inlet/Outlet Structure Bellmouth - North | 31010 | 5
3 | Underground Waterways | 10 | North Alignment Waterway | 20 | Upper Inlet/Outlet Structure Gate Shaft - North | 31020 | 5
3 | Underground Waterways | 10 | North Alignment Waterway | 30 | Lower Inlet/Outlet Structure Bellmouth - North | 31030 | 5
3 | Underground Waterways | 10 | North Alignment Waterway | 40 | Lower Inlet/Outlet Structure Gate Shaft Middle to Top - North | 31040 | 5
3 | Underground Waterways | 10 | North Alignment Waterway | 50 | Lower Inlet/Outlet Structure Gate Shaft Lower Part/Square Section - North | 31050 | 5
3 | Underground Waterways | 10 | North Alignment Waterway | 60 | Low Pressure Tunnel - North | 31060 | 5
3 | Underground Waterways | 10 | North Alignment Waterway | 70 | Erection Chamber - Upper - North | 31070 | 5
3 | Underground Waterways | 10 | North Alignment Waterway | 80 | Vertical Pressure Shaft - North | 31080 | 5
3 | Underground Waterways | 10 | North Alignment Waterway | 90 | Erection Chamber - Lower - North | 31090 | 5
3 | Underground Waterways | 10 | North Alignment Waterway | 100 | High Pressure Tunnel - North | 310100 | 5 |  | At three levels the hierarchy breaks, more than 10 elements in L5 in some areas when there is two digits at L4
3 | Underground Waterways | 10 | North Alignment Waterway | 110 | Penstock Steel Lined - North | 310110 | 5
3 | Underground Waterways | 10 | North Alignment Waterway | 120 | Tailrace Collector Tunnel - North | 310120 | 5
3 | Underground Waterways | 10 | North Alignment Waterway | 130 | Tailrace Tunnel - North | 310130 | 5
3 | Underground Waterways | 10 | North Alignment Waterway | 140 | Surge Tank - North | 310140 | 5
3 | Underground Waterways | 10 | North Alignment Waterway | 150 | Lower Inlet/Outlet - North | 310150 | 5
3 | Underground Waterways | 10 | North Alignment Waterway | 160 | Permanent Access Tunnel to Surge Tanks - North | 310160 | 5
3 | Underground Waterways | 10 | North Alignment Waterway | 170 | Construction Adit - North | 310170 | 5
3 | Underground Waterways | 20 | South Alignment Waterway | 00 | South Alignment Waterway | 32000 | 4

## FlatFile Review (hidden)
L3 | L3 Desc | L4 | L4 Desc | L5 | Item | Description | Level | Commentary
1 | QH Costs | 0 | QH Costs | 000 | 10000 | QH Costs | 3 | Double up with Staff
1 | QH Costs | 0 | QH Costs | 000 | 10000 | QH Delivery (Staff) | 4 | Double up L3
1 | QH Costs | 0 | QH Costs | 010 | 10010 | Project (Staff) | 5 | Rolls up to L3
1 | QH Costs | 0 | QH Costs | 020 | 10020 | Commercial (Staff) | 5 | Rolls up to L3
1 | QH Costs | 0 | QH Costs | 030 | 10030 | Engineering Assurance (Staff) | 5 | Rolls up to L3
1 | QH Costs | 0 | QH Costs | 040 | 10040 | Health & Safety (Staff) | 5 | Rolls up to L3
1 | QH Costs | 0 | QH Costs | 050 | 10050 | Project Controls (Staff) | 5 | Rolls up to L3
1 | QH Costs | 0 | QH Costs | 060 | 10060 | Environment (Staff) | 5 | Rolls up to L3
1 | QH Costs | 0 | QH Costs | 070 | 10070 | Community and Stakeholder (Staff) | 5 | Rolls up to L3
1 | QH Costs | 0 | QH Costs | 080 | 10080 | Land (Staff) | 5 | Rolls up to L3
1 | QH Costs | 0 | QH Costs | 090 | 10090 | Regional Development (Staff) | 5 | Rolls up to L3
1 | QH Costs | 0 | QH Costs | 100 | 10100 | Quality (Staff) | 5 | Rolls up to L3
1 | QH Costs | 1 | Project Contractors | 000 | 11000 | Project Contractors | 4
1 | QH Costs | 1 | Project Contractors | 010 | 11010 | Project Support | 5
1 | QH Costs | 1 | Project Contractors | 020 | 11020 | Commercial Pre-Contracts | 5
1 | QH Costs | 1 | Project Contractors | 030 | 11030 | Commercial - Contracts Admin | 5
1 | QH Costs | 1 | Project Contractors | 040 | 11040 | Project Controls | 5
1 | QH Costs | 1 | Project Contractors | 050 | 11050 | Legal | 5
1 | QH Costs | 1 | Project Contractors | 060 | 11060 | Engineering Assurance | 5
1 | QH Costs | 1 | Project Contractors | 070 | 11070 | Operation and Maintenance Strategy | 5
1 | QH Costs | 2 | Engineering | 000 | 12000 | Engineering | 4
1 | QH Costs | 2 | Engineering | 010 | 12010 | Specialist Engineering - External Advisory Services | 5
1 | QH Costs | 2 | Engineering | 020 | 12020 | Specialist Engineering - Owners Engineer | 5
1 | QH Costs | 2 | Engineering | 030 | 12030 | Specialist Engineering - Design for Procurement | 5
1 | QH Costs | 2 | Engineering | 040 | 12040 | Specialist Engineering - FEED | 5
1 | QH Costs | 2 | Engineering | 050 | 12050 | Specialist Engineering - Exploratory Works | 5
1 | QH Costs | 2 | Engineering | 060 | 12060 | Specialist Advisors - Technical Assurance | 5
1 | QH Costs | 2 | Engineering | 070 | 12070 | Connection Application Process/Services | 5
1 | QH Costs | 2 | Engineering | 080 | 12080 | Independent certifier | 5
1 | QH Costs | 3 | Environment and Approvals | 000 | 13000 | Environment and Approvals | 4
1 | QH Costs | 3 | Environment and Approvals | 010 | 13010 | Technical Advisors - EIS Approvals and Studies | 5
1 | QH Costs | 3 | Environment and Approvals | 020 | 13020 | EIS - Engineering Input | 5
1 | QH Costs | 3 | Environment and Approvals | 030 | 13030 | EIS - Technical Studies | 5
1 | QH Costs | 3 | Environment and Approvals | 040 | 13040 | Exploratory Works Approvals | 5
1 | QH Costs | 3 | Environment and Approvals | 050 | 13050 | Main Works - Approvals | 5
1 | QH Costs | 3 | Environment and Approvals | 060 | 13060 | Offset Implementation | 5
1 | QH Costs | 3 | Environment and Approvals | 070 | 13070 | Sustainability | 5
1 | QH Costs | 3 | Environment and Approvals | 080 | 13080 | Office of the Coordinator-General (OCG Costs) | 5
1 | QH Costs | 3 | Environment and Approvals | 090 | 13090 | EIS - Delivery | 5
1 | QH Costs | 3 | Environment and Approvals | 100 | 13100 | GIS Support | 5
1 | QH Costs | 3 | Environment and Approvals | 110 | 13110 | Cultural Heritage - Investigations and Monitoring | 5
1 | QH Costs | 3 | Environment and Approvals | 120 | 13120 | Indigenous Land Use Agreement | 5
1 | QH Costs | 3 | Environment and Approvals | 130 | 13130 | Compliance Monitoring | 5
1 | QH Costs | 3 | Environment and Approvals | 140 | 13140 | Indigenous Partnerships | 5
1 | QH Costs | 4 | Community Development and Stakeholder | 000 | 14000 | Community Development and Stakeholder | 4
1 | QH Costs | 4 | Community Development and Stakeholder | 010 | 14010 | Community and Stakeholder Consultants | 5
1 | QH Costs | 4 | Community Development and Stakeholder | 020 | 14020 | Community Benefits Program | 5
1 | QH Costs | 4 | Community Development and Stakeholder | 030 | 14030 | Sponsorships | 5
1 | QH Costs | 4 | Community Development and Stakeholder | 040 | 14040 | Community Engagement Program | 5
1 | QH Costs | 4 | Community Development and Stakeholder | 050 | 14050 | Regional Development | 5
1 | QH Costs | 4 | Community Development and Stakeholder | 060 | 14060 | Regional Development Accommodation Partners | 5
1 | QH Costs | 4 | Community Development and Stakeholder | 070 | 14070 | Regional Development Community Infrastructure | 5
1 | QH Costs | 4 | Community Development and Stakeholder | 080 | 14080 | Regional Development - Community Development Initiatives (GRC) | 5
1 | QH Costs | 4 | Community Development and Stakeholder | 090 | 14090 | Regional Development - Community Development Initiatives (SRC) | 5
1 | QH Costs | 5 | Heath and Safety | 000 | 15000 | Heath and Safety | 4
1 | QH Costs | 5 | Heath and Safety | 010 | 15010 | PPE | 5
1 | QH Costs | 5 | Heath and Safety | 020 | 15020 | Health and Safety Consultants | 5
1 | QH Costs | 5 | Heath and Safety | 030 | 15030 | Mandatory Safety Training | 5
1 | QH Costs | 5 | Heath and Safety | 040 | 15040 | Emergency Response Plan | 5
1 | QH Costs | 6 | Land Acquisition | 000 | 16000 | Land Acquisition | 4
1 | QH Costs | 6 | Land Acquisition | 010 | 16010 | Land Access & Conveyancing | 5
1 | QH Costs | 6 | Land Acquisition | 020 | 16020 | Land Acquisition | 5
1 | QH Costs | 6 | Land Acquisition | 030 | 16030 | Land Access - Specialist Advisors | 5
1 | QH Costs | 7 | Indirect | 000 | 17000 | Indirect | 4
1 | QH Costs | 7 | Indirect | 010 | 17010 | Project Expenses – General | 5
1 | QH Costs | 7 | Indirect | 020 | 17020 | Travel, Accommodation & Disbursements | 5
1 | QH Costs | 7 | Indirect | 030 | 17030 | IT Software, Licenses & Equipment | 5
1 | QH Costs | 7 | Indirect | 040 | 17040 | Training & Development | 5
1 | QH Costs | 7 | Indirect | 050 | 17050 | Site Vehicles and Transport | 5
1 | QH Costs | 7 | Indirect | 060 | 17060 | Project Offices and Facilities | 5
1 | QH Costs | 7 | Indirect | 070 | 17070 | Portable Long Service Leave Levy | 5
1 | QH Costs | 7 | Indirect | 080 | 17080 | Insurances | 5
1 | QH Costs | 7 | Indirect | 090 | 17090 | Bid cost reimbursement | 5
1 | QH Costs | 7 | Indirect | 100 | 17100 | Site Equipment & Tooling | 5
1 | QH Costs | 7 | Indirect | 110 | 17110 | Corporate Overheads | 5
1 | QH Costs | 7 | Indirect | 120 | 17120 | Legal Costs | 5
1 | QH Costs | 7 | Indirect | 130 | 17130 | Site Communications | 5
1 | QH Costs | 7 | Indirect | 140 | 17140 | Finance costs (FBT) | 5
1 | QH Costs | 7 | Indirect | 150 | 17150 | Other Staff Costs (memberships, subscriptions) | 5
1 | QH Costs | 8 | Ops Readiness & Commissioning | 000 | 18000 | Ops Readiness & Commissioning | 4
1 | QH Costs | 8 | Ops Readiness & Commissioning | 010 | 18010 | Op Readiness | 5
1 | QH Costs | 8 | Ops Readiness & Commissioning | 020 | 18020 | Commissioning | 5
1 | QH Costs | 8 | Ops Readiness & Commissioning | 030 | 18030 | Full Load Compliance Testing | 5
2 | Surface Infrastructure and Enabling | 0 | Surface Infrastructure and Enabling | 000 | 20000 | Surface Infrastructure and Enabling | 3
2 | Surface Infrastructure and Enabling | 0 | Surface Infrastructure and Enabling | 100 | 20100 | Contractor Indirect & overheads | 4
2 | Surface Infrastructure and Enabling | 0 | Surface Infrastructure and Enabling | 110 | 20110 | Temporary Camps - Indirects and Overheads | 5 | Rolls up to L3
2 | Surface Infrastructure and Enabling | 0 | Surface Infrastructure and Enabling | 120 | 20120 | Main Camps - Indirects and Overheads | 5 | Rolls up to L3
2 | Surface Infrastructure and Enabling | 0 | Surface Infrastructure and Enabling | 130 | 20130 | Exploratory Works - Contractor Indirect & overheads | 5 | Rolls up to L3
2 | Surface Infrastructure and Enabling | 0 | Surface Infrastructure and Enabling | 140 | 20140 | Enabling Works - Contractor Indirect & overheads | 5 | Rolls up to L3
2 | Surface Infrastructure and Enabling | 0 | Surface Infrastructure and Enabling | 200 | 20200 | Design | 4
2 | Surface Infrastructure and Enabling | 0 | Surface Infrastructure and Enabling | 210 | 20210 | Design - Exploratory Works | 5 | Rolls up to L3
2 | Surface Infrastructure and Enabling | 0 | Surface Infrastructure and Enabling | 220 | 20220 | Design - Enabling Works | 5 | Rolls up to L3
2 | Surface Infrastructure and Enabling | 0 | Surface Infrastructure and Enabling | 230 | 20230 | Temp Camps Design | 5 | Rolls up to L3
2 | Surface Infrastructure and Enabling | 0 | Surface Infrastructure and Enabling | 300 | 20300 | Camps | 4
2 | Surface Infrastructure and Enabling | 0 | Surface Infrastructure and Enabling | 310 | 20310 | Temp Camps | 5 | Rolls up to L3
2 | Surface Infrastructure and Enabling | 0 | Surface Infrastructure and Enabling | 320 | 20320 | Upper Res Camps Hardstand | 5 | Rolls up to L3
2 | Surface Infrastructure and Enabling | 0 | Surface Infrastructure and Enabling | 330 | 20330 | Lower Res Camps Hardstand | 5 | Rolls up to L3
2 | Surface Infrastructure and Enabling | 0 | Surface Infrastructure and Enabling | 340 | 20340 | Main Camps Hardstand | 5 | Rolls up to L3
2 | Surface Infrastructure and Enabling | 0 | Surface Infrastructure and Enabling | 350 | 20350 | Upper Res Camps Install and Operate | 5 | Rolls up to L3
2 | Surface Infrastructure and Enabling | 0 | Surface Infrastructure and Enabling | 360 | 20360 | Lower Res Camps Install and Operate | 5 | Rolls up to L3
2 | Surface Infrastructure and Enabling | 0 | Surface Infrastructure and Enabling | 370 | 20370 | Main Camps Install and Operate | 5 | Rolls up to L3
2 | Surface Infrastructure and Enabling | 0 | Surface Infrastructure and Enabling | 380 | 20380 | Camp Set up | 5 | Rolls up to L3
2 | Surface Infrastructure and Enabling | 0 | Surface Infrastructure and Enabling | 400 | 20400 | Geotechnical | 4
2 | Surface Infrastructure and Enabling | 0 | Surface Infrastructure and Enabling | 410 | 20410 | Contractor Indirect & overheads | 5 | Rolls up to L3
2 | Surface Infrastructure and Enabling | 0 | Surface Infrastructure and Enabling | 420 | 20420 | Geotechnical Studies | 5 | Rolls up to L3
2 | Surface Infrastructure and Enabling | 0 | Surface Infrastructure and Enabling | 430 | 20430 | Geotechnical Drilling | 5 | Rolls up to L3
2 | Surface Infrastructure and Enabling | 0 | Surface Infrastructure and Enabling | 440 | 20440 | Geotechnical Service Management | 5 | Rolls up to L3
2 | Surface Infrastructure and Enabling | 0 | Surface Infrastructure and Enabling | 500 | 20500 | Temporary Water Infrastructure | 4
2 | Surface Infrastructure and Enabling | 0 | Surface Infrastructure and Enabling | 510 | 20510 | Preliminaries Temporary Water Infrastructure | 5 | Rolls up to L3
2 | Surface Infrastructure and Enabling | 0 | Surface Infrastructure and Enabling | 520 | 20520 | Temporary Water Infrastructure | 5 | Rolls up to L3
2 | Surface Infrastructure and Enabling | 0 | Surface Infrastructure and Enabling | 530 | 20530 | Temporary Water Supply | 5 | Rolls up to L3
2 | Surface Infrastructure and Enabling | 0 | Surface Infrastructure and Enabling | 600 | 20600 | Communication Infrastructure Upgrade | 4
2 | Surface Infrastructure and Enabling | 0 | Surface Infrastructure and Enabling | 610 | 20610 | Preliminaries Communication Infrastructure Upgrade | 5 | Rolls up to L3
2 | Surface Infrastructure and Enabling | 0 | Surface Infrastructure and Enabling | 620 | 20620 | Communication Infrastructure Upgrade | 5 | Rolls up to L3
2 | Surface Infrastructure and Enabling | 0 | Surface Infrastructure and Enabling | 700 | 20700 | Power Supply Upgrade | 4
2 | Surface Infrastructure and Enabling | 0 | Surface Infrastructure and Enabling | 710 | 20710 | Preliminaries Power Supply Upgrade | 5 | Rolls up to L3
2 | Surface Infrastructure and Enabling | 0 | Surface Infrastructure and Enabling | 720 | 20720 | Power Supply Upgrade | 5 | Rolls up to L3
2 | Surface Infrastructure and Enabling | 1 | Yabba Creek Road Option 1 | 000 | 21000 | Yabba Creek Road Option 1 | 4
2 | Surface Infrastructure and Enabling | 1 | Yabba Creek Road Option 1 | 010 | 21010 | Preliminaries Yabba Ck Rd Option 1 | 5 | Too many WBS to roll up to single digit L4
2 | Surface Infrastructure and Enabling | 1 | Yabba Creek Road Option 1 | 020 | 21020 | Bridge 1 (on Yabba Ck Rd - Ana Branche No 1) | 5 | Too many WBS to roll up to single digit L4
2 | Surface Infrastructure and Enabling | 1 | Yabba Creek Road Option 1 | 030 | 21030 | Bridge 2 (on Yabba Ck Rd - Ana Branche No 2) | 5 | Too many WBS to roll up to single digit L4
2 | Surface Infrastructure and Enabling | 1 | Yabba Creek Road Option 1 | 040 | 21040 | Bridge 3 (on Yabba Ck Rd - No 1 Crossing - Neumans Crossing) | 5 | Too many WBS to roll up to single digit L4
2 | Surface Infrastructure and Enabling | 1 | Yabba Creek Road Option 1 | 050 | 21050 | Bridge 4 (on Yabba Ck Rd - No 2 Crossing - Elbow Crossing) | 5 | Too many WBS to roll up to single digit L4
2 | Surface Infrastructure and Enabling | 1 | Yabba Creek Road Option 1 | 060 | 21060 | Bridge 5 (on Yabba Ck Rd - No 3 Crossing - Andrews Crossing) | 5 | Too many WBS to roll up to single digit L4
2 | Surface Infrastructure and Enabling | 1 | Yabba Creek Road Option 1 | 070 | 21070 | Bridge 6 (on Yabba Ck Rd - No ? Crossing - ????) | 5 | Too many WBS to roll up to single digit L4
2 | Surface Infrastructure and Enabling | 1 | Yabba Creek Road Option 1 | 080 | 21080 | Bridge 7 (on Yabba Ck Rd - No 4 Crossing - Boardmans Crossing) | 5 | Too many WBS to roll up to single digit L4
2 | Surface Infrastructure and Enabling | 1 | Yabba Creek Road Option 1 | 090 | 21090 | Bridge 8 (on Yabba Ck Rd - No 5 Crossing - Friends Crossing) | 5 | Too many WBS to roll up to single digit L4
2 | Surface Infrastructure and Enabling | 1 | Yabba Creek Road Option 1 | 100 | 21100 | Bridge 9 (on Yabba Ck Rd - No 6 Crossing - Deep Crossing) | 5 | Too many WBS to roll up to single digit L4
2 | Surface Infrastructure and Enabling | 1 | Yabba Creek Road Option 1 | 110 | 21110 | Bridge 10 (on Yabba Ck Rd - No 7 - Crossing - unknown name) | 5 | Too many WBS to roll up to single digit L4
2 | Surface Infrastructure and Enabling | 1 | Yabba Creek Road Option 1 | 120 | 21120 | Upgrade Bella Creek Road intersection | 5 | Too many WBS to roll up to single digit L4
2 | Surface Infrastructure and Enabling | 1 | Yabba Creek Road Option 1 | 200 | 21200 | Old Forestry Drive Option 2 | 4
2 | Surface Infrastructure and Enabling | 1 | Yabba Creek Road Option 1 | 210 | 21210 | Preliminaries Old Forestry Drive Option 2 | 5 | Rolls up to L3
2 | Surface Infrastructure and Enabling | 1 | Yabba Creek Road Option 1 | 220 | 21220 | Old Forestry Drive Option 2 Construction | 5 | Rolls up to L3
2 | Surface Infrastructure and Enabling | 1 | Yabba Creek Road Option 1 | 300 | 21300 | Yielo Rd | 4
2 | Surface Infrastructure and Enabling | 1 | Yabba Creek Road Option 1 | 310 | 21310 | Preliminaries Upgrade of Yielo Rd | 5 | Rolls up to L3
2 | Surface Infrastructure and Enabling | 1 | Yabba Creek Road Option 1 | 320 | 21320 | Upgrade of Yielo Rd Construction | 5 | Rolls up to L3
2 | Surface Infrastructure and Enabling | 1 | Yabba Creek Road Option 1 | 400 | 21400 | Walkers Top Access Track | 4
2 | Surface Infrastructure and Enabling | 1 | Yabba Creek Road Option 1 | 410 | 21410 | Preliminaries Walkers Top Access Track | 5 | Rolls up to L3
2 | Surface Infrastructure and Enabling | 1 | Yabba Creek Road Option 1 | 420 | 21420 | Walkers Top Access Track Construction | 5 | Rolls up to L3
2 | Surface Infrastructure and Enabling | 1 | Yabba Creek Road Option 1 | 500 | 21500 | Access Roads - The Borgan | 4
2 | Surface Infrastructure and Enabling | 1 | Yabba Creek Road Option 1 | 510 | 21510 | Preliminaries Access Roads - The Borgan | 5 | Rolls up to L3
2 | Surface Infrastructure and Enabling | 1 | Yabba Creek Road Option 1 | 520 | 21520 | Access Roads - The Borgan | 5 | Rolls up to L3
2 | Surface Infrastructure and Enabling | 1 | Yabba Creek Road Option 1 | 600 | 21600 | Lower Res Access Road | 4
2 | Surface Infrastructure and Enabling | 1 | Yabba Creek Road Option 1 | 610 | 21610 | Lower Res Access Road | 5 | Rolls up to L3
2 | Surface Infrastructure and Enabling | 1 | Yabba Creek Road Option 1 | 700 | 21700 | Lower Res Haul Road - Construct and Maintain | 4
2 | Surface Infrastructure and Enabling | 1 | Yabba Creek Road Option 1 | 710 | 21710 | Lower Res Haul Road - Construct and Maintain | 5 | Rolls up to L3
2 | Surface Infrastructure and Enabling | 1 | Yabba Creek Road Option 1 | 800 | 21800 | Bella Creek Road | 4
2 | Surface Infrastructure and Enabling | 1 | Yabba Creek Road Option 1 | 810 | 21810 | Bella Creek Road | 5 | Rolls up to L3
2 | Surface Infrastructure and Enabling | 1 | Yabba Creek Road Option 1 | 900 | 21900 | Yabba Creek Bridge | 4
2 | Surface Infrastructure and Enabling | 1 | Yabba Creek Road Option 1 | 910 | 21910 | Yabba Creek Bridge | 5 | Rolls up to L3
2 | Surface Infrastructure and Enabling | 2 | Kingaham Creek Bridge | 000 | 22000 | Kingaham Creek Bridge | 4
2 | Surface Infrastructure and Enabling | 2 | Kingaham Creek Bridge | 010 | 22010 | Kingaham Creek Bridge | 5 | Rolls up to L3
2 | Surface Infrastructure and Enabling | 2 | Kingaham Creek Bridge | 100 | 22100 | Road to Lower Inlet / Outlet Structure | 4
2 | Surface Infrastructure and Enabling | 2 | Kingaham Creek Bridge | 110 | 22110 | Road to Lower Inlet / Outlet Structure | 5 | Rolls up to L3
2 | Surface Infrastructure and Enabling | 2 | Kingaham Creek Bridge | 200 | 22200 | Road to Upper Res/Saddle Dam | 4
2 | Surface Infrastructure and Enabling | 2 | Kingaham Creek Bridge | 210 | 22210 | Road to Upper Res/Saddle Dam | 5 | Rolls up to L3
2 | Surface Infrastructure and Enabling | 2 | Kingaham Creek Bridge | 300 | 22300 | Ring Road at Upper Res incl. Access to upper intake and Bellmouth | 4
2 | Surface Infrastructure and Enabling | 2 | Kingaham Creek Bridge | 310 | 22310 | Ring Road at Upper Res incl. Access to upper intake and Bellmouth | 5 | Rolls up to L3
3 | Underground Waterways | 0 | Underground Waterways | 000 | 30000 | Underground Waterways | 3
3 | Underground Waterways | 0 | Underground Waterways | 100 | 30100 | Contractor Indirect & overheads stage 1 | 4
3 | Underground Waterways | 0 | Underground Waterways | 110 | 30110 | Contractor Indirects & overheads | 5
3 | Underground Waterways | 0 | Underground Waterways | 200 | 30200 | Design | 4
3 | Underground Waterways | 0 | Underground Waterways | 210 | 30210 | Design | 5
3 | Underground Waterways | 1 | North Alignment Waterway | 000 | 31000 | North Alignment Waterway | 4
3 | Underground Waterways | 1 | North Alignment Waterway | 010 | 31010 | Upper Inlet/Outlet Structure Bellmouth - North | 5
3 | Underground Waterways | 1 | North Alignment Waterway | 020 | 31020 | Upper Inlet/Outlet Structure Gate Shaft - North | 5
3 | Underground Waterways | 1 | North Alignment Waterway | 030 | 31030 | Lower Inlet/Outlet Structure Bellmouth - North | 5
3 | Underground Waterways | 1 | North Alignment Waterway | 040 | 31040 | Lower Inlet/Outlet Structure Gate Shaft Middle to Top - North | 5
3 | Underground Waterways | 1 | North Alignment Waterway | 050 | 31050 | Lower Inlet/Outlet Structure Gate Shaft Lower Part/Square Section - North | 5
3 | Underground Waterways | 1 | North Alignment Waterway | 060 | 31060 | Low Pressure Tunnel - North | 5
3 | Underground Waterways | 1 | North Alignment Waterway | 070 | 31070 | Erection Chamber - Upper - North | 5
3 | Underground Waterways | 1 | North Alignment Waterway | 080 | 31080 | Vertical Pressure Shaft - North | 5
3 | Underground Waterways | 1 | North Alignment Waterway | 090 | 31090 | Erection Chamber - Lower - North | 5
3 | Underground Waterways | 1 | North Alignment Waterway | 100 | 31100 | High Pressure Tunnel - North | 5
3 | Underground Waterways | 1 | North Alignment Waterway | 110 | 31110 | Penstock Steel Lined - North | 5
3 | Underground Waterways | 1 | North Alignment Waterway | 120 | 31120 | Tailrace Collector Tunnel - North | 5
3 | Underground Waterways | 1 | North Alignment Waterway | 130 | 31130 | Tailrace Tunnel - North | 5
3 | Underground Waterways | 1 | North Alignment Waterway | 140 | 31140 | Surge Tank - North | 5
3 | Underground Waterways | 2 | South Alignment Waterway | 000 | 32000 | South Alignment Waterway | 4
3 | Underground Waterways | 2 | South Alignment Waterway | 010 | 32010 | Upper Inlet/Outlet Structure Bellmouth - South | 5
3 | Underground Waterways | 2 | South Alignment Waterway | 020 | 32020 | Upper Inlet/Outlet Structure Gate Shaft - South | 5
3 | Underground Waterways | 2 | South Alignment Waterway | 030 | 32030 | Lower Inlet/Outlet Structure Bellmouth - South | 5
3 | Underground Waterways | 2 | South Alignment Waterway | 040 | 32040 | Lower Inlet/Outlet Structure Gate Shaft Middle to Top - South | 5
3 | Underground Waterways | 2 | South Alignment Waterway | 050 | 32050 | Lower Inlet/Outlet Structure Gate Shaft Lower Part/Square Section - South | 5
3 | Underground Waterways | 2 | South Alignment Waterway | 060 | 32060 | Low Pressure Tunnel - South | 5
3 | Underground Waterways | 2 | South Alignment Waterway | 070 | 32070 | Erection Chamber - Upper - South | 5
3 | Underground Waterways | 2 | South Alignment Waterway | 080 | 32080 | Vertical Pressure Shaft - South | 5
3 | Underground Waterways | 2 | South Alignment Waterway | 090 | 32090 | Erection Chamber - Lower - South | 5
3 | Underground Waterways | 2 | South Alignment Waterway | 100 | 32100 | High Pressure Tunnel - South | 5
3 | Underground Waterways | 2 | South Alignment Waterway | 110 | 32110 | Penstock Steel Lined - South | 5
3 | Underground Waterways | 2 | South Alignment Waterway | 120 | 32120 | Tailrace Collector Tunnel - South | 5
3 | Underground Waterways | 2 | South Alignment Waterway | 130 | 32130 | Tailrace Tunnel - South | 5
3 | Underground Waterways | 2 | South Alignment Waterway | 140 | 32140 | Surge Tank - South | 5
3 | Underground Waterways | 3 | Platform and Control Buildings | 000 | 33000 | Platform and Control Buildings | 4
3 | Underground Waterways | 3 | Platform and Control Buildings | 010 | 33010 | Upper Inlet/Outlet Platform and Control Building | 5
3 | Underground Waterways | 3 | Platform and Control Buildings | 020 | 33020 | Lower Inlet/Outlet Platform and Control Building | 5
3 | Underground Waterways | 4 | Lower Inlet Structure Approach | 000 | 34000 | Lower Inlet Structure Approach | 4
3 | Underground Waterways | 4 | Lower Inlet Structure Approach | 010 | 34010 | Lower Inlet/Outlet Structure - Approach | 5
3 | Underground Waterways | 5 | Surge Tanks Permanent access tunnel | 000 | 35000 | Surge Tanks Permanent access tunnel | 4
3 | Underground Waterways | 5 | Surge Tanks Permanent access tunnel | 010 | 35010 | Surge Tanks Permanent access tunnel | 5
3 | Underground Waterways | 6 | Assembly Chambers | 000 | 36000 | Assembly Chambers | 4
3 | Underground Waterways | 6 | Assembly Chambers | 010 | 36010 | Upstream Assembly Chambers, Connection Tunnels and Adit | 5
3 | Underground Waterways | 6 | Assembly Chambers | 020 | 36020 | Downstream Assembly Chambers, Connection Tunnels and Adit | 5
3 | Underground Waterways | 7 | Site Rehabilitation | 000 | 37000 | Site Rehabilitation | 4
3 | Underground Waterways | 7 | Site Rehabilitation | 010 | 37010 | Site Rehabilitation | 5
4 | Underground Access & Caverns | 0 | Underground Access & Caverns | 000 | 40000 | Underground Access & Caverns | 3
4 | Underground Access & Caverns | 0 | Underground Access & Caverns | 100 | 40100 | Contractor Indirect & overheads | 4
4 | Underground Access & Caverns | 0 | Underground Access & Caverns | 110 | 40110 | Contractor Indirects & overheads | 5
4 | Underground Access & Caverns | 0 | Underground Access & Caverns | 200 | 40200 | Design | 4
4 | Underground Access & Caverns | 0 | Underground Access & Caverns | 210 | 40210 | Detail Design - Main Facility | 5
4 | Underground Access & Caverns | 0 | Underground Access & Caverns | 220 | 40220 | Detail Design - OEM | 5
4 | Underground Access & Caverns | 0 | Underground Access & Caverns | 300 | 40300 | Site Clearing | 4
4 | Underground Access & Caverns | 0 | Underground Access & Caverns | 310 | 40310 | Site Clearing | 5
4 | Underground Access & Caverns | 0 | Underground Access & Caverns | 400 | 40400 | Construction Surface Facilities | 4
4 | Underground Access & Caverns | 0 | Underground Access & Caverns | 410 | 40410 | Construction Site Facilities - Platform Areas | 5
4 | Underground Access & Caverns | 0 | Underground Access & Caverns | 420 | 40420 | Grout plant - mobilise and demobilise | 5
4 | Underground Access & Caverns | 0 | Underground Access & Caverns | 430 | 40430 | Construction Site Facilities - Platform 2 - Concrete Plant | 5
4 | Underground Access & Caverns | 0 | Underground Access & Caverns | 440 | 40440 | Concrete batching plant - mobilise and demobilise | 5
4 | Underground Access & Caverns | 0 | Underground Access & Caverns | 450 | 40450 | Construction Site Facilities - Upper inlet / outlet - Concrete Plant | 5
4 | Underground Access & Caverns | 0 | Underground Access & Caverns | 500 | 40500 | ECTV Exploratory Drilling | 4
4 | Underground Access & Caverns | 0 | Underground Access & Caverns | 510 | 40510 | Exploratory Tunnel - Surface Works | 5
4 | Underground Access & Caverns | 0 | Underground Access & Caverns | 520 | 40520 | Exploratory Tunnel - Underground Works | 5
4 | Underground Access & Caverns | 0 | Underground Access & Caverns | 530 | 40530 | Exploratory Tunnel - Caverns Investigation | 5
4 | Underground Access & Caverns | 0 | Underground Access & Caverns | 540 | 40540 | Exploratory Tunnel - Management Services | 5
4 | Underground Access & Caverns | 0 | Underground Access & Caverns | 600 | 40600 | MAT and ECVT | 4
4 | Underground Access & Caverns | 0 | Underground Access & Caverns | 610 | 40610 | Main Access Tunnel (MAT) | 5
4 | Underground Access & Caverns | 0 | Underground Access & Caverns | 620 | 40620 | Emergency, Cable and Ventilation Tunnel (ECVT) Completion | 5
4 | Underground Access & Caverns | 0 | Underground Access & Caverns | 700 | 40700 | Power Cavern | 4
4 | Underground Access & Caverns | 0 | Underground Access & Caverns | 710 | 40710 | Power Cavern | 5
4 | Underground Access & Caverns | 0 | Underground Access & Caverns | 800 | 40800 | Transformer Cavern | 4
4 | Underground Access & Caverns | 0 | Underground Access & Caverns | 810 | 40810 | Transformer Cavern | 5
4 | Underground Access & Caverns | 0 | Underground Access & Caverns | 900 | 40900 | IPB Galleries (x 6) | 4
4 | Underground Access & Caverns | 0 | Underground Access & Caverns | 910 | 40910 | IPB Galleries (x 6) | 5
4 | Underground Access & Caverns | 1 | MAT Tunnels between Power Cavern and Transformer Cavern | 000 | 41000 | MAT Tunnels between Power Cavern and Transformer Cavern | 4
4 | Underground Access & Caverns | 1 | MAT Tunnels between Power Cavern and Transformer Cavern | 010 | 41010 | MAT Tunnels between Power Cavern and Transformer Cavern | 5
4 | Underground Access & Caverns | 1 | MAT Tunnels between Power Cavern and Transformer Cavern | 100 | 41100 | Site Rehabilitation | 4
4 | Underground Access & Caverns | 1 | MAT Tunnels between Power Cavern and Transformer Cavern | 110 | 41110 | Site Rehabilitation | 5
5 | Powerhouse Mech & Elec | 0 | Powerhouse Mech & Elec | 000 | 50000 | Powerhouse Mech & Elec | 3
5 | Powerhouse Mech & Elec | 0 | Powerhouse Mech & Elec | 100 | 50100 | Contractor Indirect & overheads | 4
5 | Powerhouse Mech & Elec | 0 | Powerhouse Mech & Elec | 110 | 50110 | Contractor Indirects & overheads | 5
5 | Powerhouse Mech & Elec | 0 | Powerhouse Mech & Elec | 200 | 50200 | Design | 4
5 | Powerhouse Mech & Elec | 0 | Powerhouse Mech & Elec | 210 | 50210 | Design | 5
5 | Powerhouse Mech & Elec | 0 | Powerhouse Mech & Elec | 300 | 50300 | Mech & Elec | 4
5 | Powerhouse Mech & Elec | 0 | Powerhouse Mech & Elec | 310 | 50310 | Mech & Elec | 5
5 | Powerhouse Mech & Elec | 0 | Powerhouse Mech & Elec | 400 | 50400 | Power Turbines | 4
5 | Powerhouse Mech & Elec | 0 | Powerhouse Mech & Elec | 410 | 50410 | Power Turbines | 5
5 | Powerhouse Mech & Elec | 0 | Powerhouse Mech & Elec | 500 | 50500 | Transformers | 4
5 | Powerhouse Mech & Elec | 0 | Powerhouse Mech & Elec | 510 | 50510 | Transformers | 5
5 | Powerhouse Mech & Elec | 0 | Powerhouse Mech & Elec | 600 | 50600 | Hydro-Mechanical Works | 4
5 | Powerhouse Mech & Elec | 0 | Powerhouse Mech & Elec | 610 | 50610 | Hydro-Mechanical Works | 5
5 | Powerhouse Mech & Elec | 0 | Powerhouse Mech & Elec | 700 | 50700 | Electrical Install | 4
5 | Powerhouse Mech & Elec | 0 | Powerhouse Mech & Elec | 710 | 50710 | Electrical Install | 5
5 | Powerhouse Mech & Elec | 0 | Powerhouse Mech & Elec | 800 | 50800 | Power Evacuation and Grid Connection | 4
5 | Powerhouse Mech & Elec | 0 | Powerhouse Mech & Elec | 810 | 50810 | Power Evacuation and Grid Connection | 5
5 | Powerhouse Mech & Elec | 0 | Powerhouse Mech & Elec | 900 | 50900 | Commissioning OEM | 4
5 | Powerhouse Mech & Elec | 0 | Powerhouse Mech & Elec | 910 | 50910 | Commissioning OEM | 5
5 | Powerhouse Mech & Elec | 1 | Site Rehabilitation | 000 | 51000 | Site Rehabilitation | 4
5 | Powerhouse Mech & Elec | 1 | Site Rehabilitation | 010 | 51010 | Site Rehabilitation | 5
6 | Lower Reservoir | 0 | Lower Reservoir | 000 | 60000 | Lower Reservoir | 3
6 | Lower Reservoir | 0 | Lower Reservoir | 100 | 60100 | Contractor Indirect & overheads | 4
6 | Lower Reservoir | 0 | Lower Reservoir | 110 | 60110 | Contractor Indirect & overheads | 5
6 | Lower Reservoir | 0 | Lower Reservoir | 200 | 60200 | Design | 4
6 | Lower Reservoir | 0 | Lower Reservoir | 210 | 60210 | Design | 5
6 | Lower Reservoir | 0 | Lower Reservoir | 300 | 60300 | Site Clearing | 4
6 | Lower Reservoir | 0 | Lower Reservoir | 310 | 60310 | Site Clearing | 5
6 | Lower Reservoir | 0 | Lower Reservoir | 400 | 60400 | Quarry Development and Material Operations | 4
6 | Lower Reservoir | 0 | Lower Reservoir | 410 | 60410 | Quarry Development and Material Operations | 5
6 | Lower Reservoir | 0 | Lower Reservoir | 500 | 60500 | Diversion and Watering | 4
6 | Lower Reservoir | 0 | Lower Reservoir | 510 | 60510 | Diversion and Watering | 5
6 | Lower Reservoir | 0 | Lower Reservoir | 600 | 60600 | Foundations | 4
6 | Lower Reservoir | 0 | Lower Reservoir | 610 | 60610 | Foundations | 5
6 | Lower Reservoir | 0 | Lower Reservoir | 700 | 60700 | Dam Construction | 4
6 | Lower Reservoir | 0 | Lower Reservoir | 710 | 60710 | Dam Construction | 5
6 | Lower Reservoir | 0 | Lower Reservoir | 800 | 60800 | Spillway | 4
6 | Lower Reservoir | 0 | Lower Reservoir | 810 | 60810 | Spillway | 5
6 | Lower Reservoir | 0 | Lower Reservoir | 900 | 60900 | Intake Tower | 4
6 | Lower Reservoir | 0 | Lower Reservoir | 910 | 60910 | Intake Tower | 5
6 | Lower Reservoir | 1 | Outlet Works | 000 | 61000 | Outlet Works | 4
6 | Lower Reservoir | 1 | Outlet Works | 010 | 61010 | Outlet Works | 5
6 | Lower Reservoir | 1 | Outlet Works | 100 | 61100 | Fishway | 4
6 | Lower Reservoir | 1 | Outlet Works | 110 | 61110 | Fishway | 5
6 | Lower Reservoir | 1 | Outlet Works | 200 | 61200 | Over topping Event of the Lower Dam | 4
6 | Lower Reservoir | 1 | Outlet Works | 210 | 61210 | Over topping Event of the Lower Dam | 5
6 | Lower Reservoir | 1 | Outlet Works | 300 | 61300 | Traffic Control | 4
6 | Lower Reservoir | 1 | Outlet Works | 310 | 61310 | Traffic Control | 5
6 | Lower Reservoir | 1 | Outlet Works | 400 | 61400 | Site Rehabilitation | 4
6 | Lower Reservoir | 1 | Outlet Works | 410 | 61410 | Site Rehabilitation | 5
7 | Upper Reservoir | 0 | Upper Reservoir | 000 | 70000 | Upper Reservoir | 3
7 | Upper Reservoir | 0 | Upper Reservoir | 100 | 70100 | Contractor Indirect & overheads | 4
7 | Upper Reservoir | 0 | Upper Reservoir | 110 | 70110 | Contractor Indirect & overheads | 5
7 | Upper Reservoir | 0 | Upper Reservoir | 200 | 70200 | Design | 4
7 | Upper Reservoir | 0 | Upper Reservoir | 210 | 70210 | Design | 5
7 | Upper Reservoir | 0 | Upper Reservoir | 300 | 70300 | Site Clearing | 4
7 | Upper Reservoir | 0 | Upper Reservoir | 310 | 70310 | Site Clearing | 5
7 | Upper Reservoir | 0 | Upper Reservoir | 400 | 70400 | Quarry Development and Material Operations | 4
7 | Upper Reservoir | 0 | Upper Reservoir | 410 | 70410 | Quarry Development and Material Operations | 5
7 | Upper Reservoir | 0 | Upper Reservoir | 500 | 70500 | Diversion and Watering | 4
7 | Upper Reservoir | 0 | Upper Reservoir | 510 | 70510 | Diversion and Watering | 5
7 | Upper Reservoir | 0 | Upper Reservoir | 600 | 70600 | Foundations | 4
7 | Upper Reservoir | 0 | Upper Reservoir | 610 | 70610 | Foundations | 5
7 | Upper Reservoir | 0 | Upper Reservoir | 700 | 70700 | Dam Construction | 4
7 | Upper Reservoir | 0 | Upper Reservoir | 710 | 70710 | Main CFRD Dam | 5
7 | Upper Reservoir | 0 | Upper Reservoir | 720 | 70720 | Main Saddle (CFRD) Dam | 5
7 | Upper Reservoir | 0 | Upper Reservoir | 730 | 70730 | Secondary Saddle (CFRD) Dam A | 5
7 | Upper Reservoir | 0 | Upper Reservoir | 740 | 70740 | Secondary Saddle (CFRD) Dam B1 | 5
7 | Upper Reservoir | 0 | Upper Reservoir | 750 | 70750 | Secondary Saddle (CFRD) Dam B2 | 5
7 | Upper Reservoir | 0 | Upper Reservoir | 760 | 70760 | Secondary Saddle (CFRD) Dam No.B3 | 5
7 | Upper Reservoir | 0 | Upper Reservoir | 800 | 70800 | Emergency Spillway | 4
7 | Upper Reservoir | 0 | Upper Reservoir | 810 | 70810 | Emergency Spillway | 5
7 | Upper Reservoir | 0 | Upper Reservoir | 900 | 70900 | Traffic Control | 4
7 | Upper Reservoir | 0 | Upper Reservoir | 910 | 70910 | Traffic Control | 5
7 | Upper Reservoir | 1 | Site Rehabilitation | 000 | 71000 | Site Rehabilitation | 4
7 | Upper Reservoir | 1 | Site Rehabilitation | 010 | 71010 | Site Rehabilitation | 5
8 | Transmissions | 0 | Transmissions | 000 | 80000 | Transmissions | 3 | Double up
8 | Transmissions | 0 | Transmissions | 000 | 80000 | Borumba - Tarong 275kV | 4 | Double up
8 | Transmissions | 0 | Transmissions | 010 | 80010 | Borumba - Tarong 275kV | 5
8 | Transmissions | 0 | Transmissions | 100 | 80100 | Borumba - Woolooga 275kV | 4
8 | Transmissions | 0 | Transmissions | 110 | 80110 | Borumba - Woolooga 275kV | 5
9 | Contingency & Escalation | 0 | Contingency & Escalation | 000 | 90000 | Contingency & Escalation | 3 | Need to amend L3
9 | Contingency & Escalation | 9 | Contingency & Escalation | 000 | 99000 | Contingency & Escalation | 4 | Need to add
9 | Contingency & Escalation | 9 | Contingency & Escalation | 100 | 99100 | Contingency | 4 | Doesn’t fit
9 | Contingency & Escalation | 9 | Contingency & Escalation | 110 | 99110 | P50 Contingency QH Costs | 5
9 | Contingency & Escalation | 9 | Contingency & Escalation | 120 | 99120 | P90 Contingency QH Costs | 5
9 | Contingency & Escalation | 9 | Contingency & Escalation | 130 | 99130 | P50 Contingency Surface Infrastructure and Enabling | 5
9 | Contingency & Escalation | 9 | Contingency & Escalation | 140 | 99140 | P90 Contingency Surface Infrastructure and Enabling | 5
9 | Contingency & Escalation | 9 | Contingency & Escalation | 150 | 99150 | P50 Contingency Underground Waterways | 5
9 | Contingency & Escalation | 9 | Contingency & Escalation | 160 | 99160 | P90 Contingency Underground Waterways | 5
9 | Contingency & Escalation | 9 | Contingency & Escalation | 170 | 99170 | P50 Contingency Underground Access & Caverns | 5
9 | Contingency & Escalation | 9 | Contingency & Escalation | 180 | 99180 | P90 Contingency Underground Access & Caverns | 5
9 | Contingency & Escalation | 9 | Contingency & Escalation | 190 | 99190 | P50 Contingency Powerhouse Mech & Elec | 5
9 | Contingency & Escalation | 9 | Contingency & Escalation | 200 | 99200 | P90 Contingency Powerhouse Mech & Elec | 5
9 | Contingency & Escalation | 9 | Contingency & Escalation | 210 | 99210 | P50 Contingency Lower Reservoir | 5
9 | Contingency & Escalation | 9 | Contingency & Escalation | 220 | 99220 | P90 Contingency Lower Reservoir | 5
9 | Contingency & Escalation | 9 | Contingency & Escalation | 230 | 99230 | P50 Contingency Upper Reservoir | 5
9 | Contingency & Escalation | 9 | Contingency & Escalation | 240 | 99240 | P90 Contingency Upper Reservoir | 5
9 | Contingency & Escalation | 9 | Contingency & Escalation | 500 | 99500 | Escalation | 4 | Doesn’t fit
9 | Contingency & Escalation | 9 | Contingency & Escalation | 510 | 99510 | Escalation QH Costs | 5
9 | Contingency & Escalation | 9 | Contingency & Escalation | 520 | 99520 | Escalation Surface Infrastructure and Enabling | 5
9 | Contingency & Escalation | 9 | Contingency & Escalation | 530 | 99530 | Escalation Underground Waterways | 5
9 | Contingency & Escalation | 9 | Contingency & Escalation | 540 | 99540 | Escalation Underground Access & Caverns | 5
9 | Contingency & Escalation | 9 | Contingency & Escalation | 550 | 99550 | Escalation Powerhouse Mech & Elec | 5
9 | Contingency & Escalation | 9 | Contingency & Escalation | 560 | 99560 | Escalation Lower Reservoir | 5
9 | Contingency & Escalation | 9 | Contingency & Escalation | 570 | 99570 | Escalation Upper Reservoir | 5

## Borumba_Edit (hidden)
L3 | L3 Desc | L4 | L4 Desc | L5 | Item | Description | Level | Commentary
1 | QH Costs | 0 | QH Costs | 000 | 10000 | QH Costs | 3 | Double up with Staff
1 | QH Costs | 1 | QH Delivery (Staff) | 000 | 11000 | QH Delivery (Staff) | 4 | Renumbered from zero to 1
1 | QH Costs | 1 | QH Delivery (Staff) | 010 | 11010 | Project (Staff) | 5
1 | QH Costs | 1 | QH Delivery (Staff) | 020 | 11020 | Commercial (Staff) | 5
1 | QH Costs | 1 | QH Delivery (Staff) | 030 | 11030 | Engineering Assurance (Staff) | 5
1 | QH Costs | 1 | QH Delivery (Staff) | 040 | 11040 | Health & Safety (Staff) | 5
1 | QH Costs | 1 | QH Delivery (Staff) | 050 | 11050 | Project Controls (Staff) | 5
1 | QH Costs | 1 | QH Delivery (Staff) | 060 | 11060 | Environment (Staff) | 5
1 | QH Costs | 1 | QH Delivery (Staff) | 070 | 11070 | Community and Stakeholder (Staff) | 5
1 | QH Costs | 1 | QH Delivery (Staff) | 080 | 11080 | Land (Staff) | 5
1 | QH Costs | 1 | QH Delivery (Staff) | 090 | 11090 | Regional Development (Staff) | 5
1 | QH Costs | 1 | QH Delivery (Staff) | 100 | 11100 | Quality (Staff) | 5
1 | QH Costs | 2 | Project Contractors | 000 | 12000 | Project Contractors | 4
1 | QH Costs | 2 | Project Contractors | 010 | 12010 | Project Support | 5
1 | QH Costs | 2 | Project Contractors | 020 | 12020 | Commercial Pre-Contracts | 5
1 | QH Costs | 2 | Project Contractors | 030 | 12030 | Commercial - Contracts Admin | 5
1 | QH Costs | 2 | Project Contractors | 040 | 12040 | Project Controls | 5
1 | QH Costs | 2 | Project Contractors | 050 | 12050 | Legal | 5
1 | QH Costs | 6 | Heath and Safety | 060 | 16060 | Health and Safety Consultants | 5 | Split from H&S L4
1 | QH Costs | 2 | Project Contractors | 070 | 12070 | Engineering Assurance | 5
1 | QH Costs | 2 | Project Contractors | 080 | 12080 | Operation and Maintenance Strategy | 5
1 | QH Costs | 3 | Engineering | 000 | 13000 | Engineering | 4
1 | QH Costs | 3 | Engineering | 010 | 13010 | Specialist Engineering - External Advisory Services | 5
1 | QH Costs | 3 | Engineering | 020 | 13020 | Specialist Engineering - Owners Engineer | 5
1 | QH Costs | 3 | Engineering | 030 | 13030 | Specialist Engineering - Design for Procurement | 5
1 | QH Costs | 3 | Engineering | 040 | 13040 | Specialist Engineering - FEED | 5
1 | QH Costs | 3 | Engineering | 050 | 13050 | Specialist Engineering - Exploratory Works | 5
1 | QH Costs | 3 | Engineering | 060 | 13060 | Specialist Advisors - Technical Assurance | 5
1 | QH Costs | 3 | Engineering | 070 | 13070 | Connection Application Process/Services | 5
1 | QH Costs | 3 | Engineering | 080 | 13080 | Independent certifier | 5
1 | QH Costs | 4 | Environment and Approvals | 000 | 14000 | Environment and Approvals | 4
1 | QH Costs | 4 | Environment and Approvals | 010 | 14010 | Technical Advisors - EIS Approvals and Studies | 5
1 | QH Costs | 4 | Environment and Approvals | 020 | 14020 | EIS - Engineering Input | 5
1 | QH Costs | 4 | Environment and Approvals | 030 | 14030 | EIS - Technical Studies | 5
1 | QH Costs | 4 | Environment and Approvals | 040 | 14040 | Exploratory Works Approvals | 5
1 | QH Costs | 4 | Environment and Approvals | 050 | 14050 | Main Works - Approvals | 5
1 | QH Costs | 4 | Environment and Approvals | 060 | 14060 | Offset Implementation | 5
1 | QH Costs | 4 | Environment and Approvals | 070 | 14070 | Sustainability | 5
1 | QH Costs | 4 | Environment and Approvals | 080 | 14080 | Office of the Coordinator-General (OCG Costs) | 5
1 | QH Costs | 4 | Environment and Approvals | 090 | 14090 | EIS - Delivery | 5
1 | QH Costs | 4 | Environment and Approvals | 100 | 14100 | GIS Support | 5
1 | QH Costs | 4 | Environment and Approvals | 110 | 14110 | Cultural Heritage - Investigations and Monitoring | 5
1 | QH Costs | 4 | Environment and Approvals | 120 | 14120 | Indigenous Land Use Agreement | 5
1 | QH Costs | 4 | Environment and Approvals | 130 | 14130 | Compliance Monitoring | 5
1 | QH Costs | 4 | Environment and Approvals | 140 | 14140 | Indigenous Partnerships | 5
1 | QH Costs | 5 | Community Development and Stakeholder | 000 | 15000 | Community Development and Stakeholder | 4
1 | QH Costs | 5 | Community Development and Stakeholder | 010 | 15010 | Community and Stakeholder Consultants | 5
1 | QH Costs | 5 | Community Development and Stakeholder | 020 | 15020 | Community Benefits Program | 5
1 | QH Costs | 5 | Community Development and Stakeholder | 030 | 15030 | Sponsorships | 5
1 | QH Costs | 5 | Community Development and Stakeholder | 040 | 15040 | Community Engagement Program | 5
1 | QH Costs | 5 | Community Development and Stakeholder | 050 | 15050 | Regional Development | 5
1 | QH Costs | 5 | Community Development and Stakeholder | 060 | 15060 | Regional Development Accommodation Partners | 5
1 | QH Costs | 5 | Community Development and Stakeholder | 070 | 15070 | Regional Development Community Infrastructure | 5
1 | QH Costs | 5 | Community Development and Stakeholder | 080 | 15080 | Regional Development - Community Development Initiatives (GRC) | 5
1 | QH Costs | 5 | Community Development and Stakeholder | 090 | 15090 | Regional Development - Community Development Initiatives (SRC) | 5
| QH Costs |  | Heath and Safety |  |  | Heath and Safety | 4 | Reallocated to Indirect & Project Contractors
1 | QH Costs | 6 | Land Acquisition | 000 | 16000 | Land Acquisition | 4
1 | QH Costs | 6 | Land Acquisition | 010 | 16010 | Land Access & Conveyancing | 5
1 | QH Costs | 6 | Land Acquisition | 020 | 16020 | Land Acquisition | 5
1 | QH Costs | 6 | Land Acquisition | 030 | 16030 | Land Access - Specialist Advisors | 5
1 | QH Costs | 7 | Indirect | 000 | 17000 | Indirect | 4
1 | QH Costs | 7 | Indirect | 010 | 17010 | Project Expenses – General | 5
1 | QH Costs | 7 | Indirect | 020 | 17020 | PPE | 5 | Split from H&S L4
1 | QH Costs | 7 | Indirect | 030 | 17030 | Emergency Response Plan | 5 | Split from H&S L4
1 | QH Costs | 7 | Indirect | 040 | 17040 | Travel, Accommodation & Disbursements | 5
1 | QH Costs | 7 | Indirect | 050 | 17050 | IT Software, Licenses & Equipment | 5
1 | QH Costs | 7 | Indirect | 060 | 17060 | Training & Development (Delivery) | 5 | Renamed (Delivery)
1 | QH Costs | 7 | Indirect | 070 | 17070 | Mandatory Safety Training | 5 | Split from H&S L4
1 | QH Costs | 7 | Indirect | 080 | 17080 | Site Vehicles and Transport | 5
1 | QH Costs | 7 | Indirect | 090 | 17090 | Project Offices and Facilities | 5
1 | QH Costs | 7 | Indirect | 100 | 17100 | Portable Long Service Leave Levy | 5
1 | QH Costs | 7 | Indirect | 110 | 17110 | Insurances | 5
1 | QH Costs | 7 | Indirect | 120 | 17120 | Bid cost reimbursement | 5
1 | QH Costs | 7 | Indirect | 130 | 17130 | Site Equipment & Tooling | 5
1 | QH Costs | 7 | Indirect | 140 | 17140 | Corporate Overheads | 5
1 | QH Costs | 7 | Indirect | 150 | 17150 | Legal Costs | 5
1 | QH Costs | 7 | Indirect | 160 | 17160 | Site Communications | 5
1 | QH Costs | 7 | Indirect | 170 | 17170 | Finance costs (FBT) | 5
1 | QH Costs | 7 | Indirect | 180 | 17180 | Other Staff Costs (memberships, subscriptions) | 5
1 | QH Costs | 8 | Ops Readiness & Commissioning | 000 | 18000 | Ops Readiness & Commissioning | 4
1 | QH Costs | 8 | Ops Readiness & Commissioning | 010 | 18010 | Op Readiness | 5
1 | QH Costs | 8 | Ops Readiness & Commissioning | 020 | 18020 | Commissioning | 5
1 | QH Costs | 8 | Ops Readiness & Commissioning | 030 | 18030 | Full Load Compliance Testing | 5
2 | Surface Infrastructure and Enabling | 0 | Surface Infrastructure and Enabling | 000 | 20000 | Surface Infrastructure and Enabling | 3
2 | Surface Infrastructure and Enabling | 1 | Surface Infrastructure and Enabling | 100 | 21100 | Contractor Indirect & overheads | 4
2 | Surface Infrastructure and Enabling | 1 | Surface Infrastructure and Enabling | 110 | 21110 | Temporary Camps - Indirects and Overheads | 5
2 | Surface Infrastructure and Enabling | 1 | Surface Infrastructure and Enabling | 120 | 21120 | Main Camps - Indirects and Overheads | 5
2 | Surface Infrastructure and Enabling | 1 | Surface Infrastructure and Enabling | 130 | 21130 | Exploratory Works - Contractor Indirect & overheads | 5
2 | Surface Infrastructure and Enabling | 1 | Surface Infrastructure and Enabling | 140 | 21140 | Enabling Works - Contractor Indirect & overheads | 5
2 | Surface Infrastructure and Enabling | 1 | Surface Infrastructure and Enabling | 200 | 21200 | Design | 4
2 | Surface Infrastructure and Enabling | 1 | Surface Infrastructure and Enabling | 210 | 21210 | Design - Exploratory Works | 5
2 | Surface Infrastructure and Enabling | 1 | Surface Infrastructure and Enabling | 220 | 21220 | Design - Enabling Works | 5
2 | Surface Infrastructure and Enabling | 1 | Surface Infrastructure and Enabling | 230 | 21230 | Temp Camps Design | 5
2 | Surface Infrastructure and Enabling | 1 | Surface Infrastructure and Enabling | 300 | 21300 | Camps | 4
2 | Surface Infrastructure and Enabling | 1 | Surface Infrastructure and Enabling | 310 | 21310 | Temp Camps | 5
2 | Surface Infrastructure and Enabling | 1 | Surface Infrastructure and Enabling | 320 | 21320 | Upper Res Camps Hardstand | 5
2 | Surface Infrastructure and Enabling | 1 | Surface Infrastructure and Enabling | 330 | 21330 | Lower Res Camps Hardstand | 5
2 | Surface Infrastructure and Enabling | 1 | Surface Infrastructure and Enabling | 340 | 21340 | Main Camps Hardstand | 5
2 | Surface Infrastructure and Enabling | 1 | Surface Infrastructure and Enabling | 350 | 21350 | Upper Res Camps Install and Operate | 5
2 | Surface Infrastructure and Enabling | 1 | Surface Infrastructure and Enabling | 360 | 21360 | Lower Res Camps Install and Operate | 5
2 | Surface Infrastructure and Enabling | 1 | Surface Infrastructure and Enabling | 370 | 21370 | Main Camps Install and Operate | 5
2 | Surface Infrastructure and Enabling | 1 | Surface Infrastructure and Enabling | 380 | 21380 | Camp Set up | 5
2 | Surface Infrastructure and Enabling | 1 | Surface Infrastructure and Enabling | 400 | 21400 | Geotechnical | 4
2 | Surface Infrastructure and Enabling | 1 | Surface Infrastructure and Enabling | 410 | 21410 | Contractor Indirect & overheads | 5
2 | Surface Infrastructure and Enabling | 1 | Surface Infrastructure and Enabling | 420 | 21420 | Geotechnical Studies | 5
2 | Surface Infrastructure and Enabling | 1 | Surface Infrastructure and Enabling | 430 | 21430 | Geotechnical Drilling | 5
2 | Surface Infrastructure and Enabling | 1 | Surface Infrastructure and Enabling | 440 | 21440 | Geotechnical Service Management | 5
2 | Surface Infrastructure and Enabling | 1 | Surface Infrastructure and Enabling | 500 | 21500 | Temporary Water Infrastructure | 4
2 | Surface Infrastructure and Enabling | 1 | Surface Infrastructure and Enabling | 510 | 21510 | Preliminaries Temporary Water Infrastructure | 5
2 | Surface Infrastructure and Enabling | 1 | Surface Infrastructure and Enabling | 520 | 21520 | Temporary Water Infrastructure | 5
2 | Surface Infrastructure and Enabling | 1 | Surface Infrastructure and Enabling | 530 | 21530 | Temporary Water Supply | 5
2 | Surface Infrastructure and Enabling | 1 | Surface Infrastructure and Enabling | 600 | 21600 | Communication Infrastructure Upgrade | 4
2 | Surface Infrastructure and Enabling | 1 | Surface Infrastructure and Enabling | 610 | 21610 | Preliminaries Communication Infrastructure Upgrade | 5
2 | Surface Infrastructure and Enabling | 1 | Surface Infrastructure and Enabling | 620 | 21620 | Communication Infrastructure Upgrade | 5
2 | Surface Infrastructure and Enabling | 1 | Surface Infrastructure and Enabling | 700 | 21700 | Power Supply Upgrade | 4
2 | Surface Infrastructure and Enabling | 1 | Surface Infrastructure and Enabling | 710 | 21710 | Preliminaries Power Supply Upgrade | 5
2 | Surface Infrastructure and Enabling | 1 | Surface Infrastructure and Enabling | 720 | 21720 | Power Supply Upgrade | 5
2 | Surface Infrastructure and Enabling | 2 | Yabba Creek Road Option 1 | 000 | 22000 | Yabba Creek Road Option 1 | 4
2 | Surface Infrastructure and Enabling | 2 | Yabba Creek Road Option 1 | 010 | 22010 | Preliminaries Yabba Ck Rd Option 1 | 5
2 | Surface Infrastructure and Enabling | 2 | Yabba Creek Road Option 1 | 020 | 22020 | Bridge 1 (on Yabba Ck Rd - Ana Branche No 1) | 5
2 | Surface Infrastructure and Enabling | 2 | Yabba Creek Road Option 1 | 030 | 22030 | Bridge 2 (on Yabba Ck Rd - Ana Branche No 2) | 5
2 | Surface Infrastructure and Enabling | 2 | Yabba Creek Road Option 1 | 040 | 22040 | Bridge 3 (on Yabba Ck Rd - No 1 Crossing - Neumans Crossing) | 5
2 | Surface Infrastructure and Enabling | 2 | Yabba Creek Road Option 1 | 050 | 22050 | Bridge 4 (on Yabba Ck Rd - No 2 Crossing - Elbow Crossing) | 5
2 | Surface Infrastructure and Enabling | 2 | Yabba Creek Road Option 1 | 060 | 22060 | Bridge 5 (on Yabba Ck Rd - No 3 Crossing - Andrews Crossing) | 5
2 | Surface Infrastructure and Enabling | 2 | Yabba Creek Road Option 1 | 070 | 22070 | Bridge 6 (on Yabba Ck Rd - No ? Crossing - ????) | 5
2 | Surface Infrastructure and Enabling | 2 | Yabba Creek Road Option 1 | 080 | 22080 | Bridge 7 (on Yabba Ck Rd - No 4 Crossing - Boardmans Crossing) | 5
2 | Surface Infrastructure and Enabling | 2 | Yabba Creek Road Option 1 | 090 | 22090 | Bridge 8 (on Yabba Ck Rd - No 5 Crossing - Friends Crossing) | 5
2 | Surface Infrastructure and Enabling | 2 | Yabba Creek Road Option 1 | 100 | 22100 | Bridge 9 (on Yabba Ck Rd - No 6 Crossing - Deep Crossing) | 5
2 | Surface Infrastructure and Enabling | 2 | Yabba Creek Road Option 1 | 110 | 22110 | Bridge 10 (on Yabba Ck Rd - No 7 - Crossing - unknown name) | 5
2 | Surface Infrastructure and Enabling | 2 | Yabba Creek Road Option 1 | 120 | 22120 | Upgrade Bella Creek Road intersection | 5
2 | Surface Infrastructure and Enabling | 2 | Yabba Creek Road Option 1 | 200 | 22200 | Old Forestry Drive Option 2 | 4
2 | Surface Infrastructure and Enabling | 2 | Yabba Creek Road Option 1 | 210 | 22210 | Preliminaries Old Forestry Drive Option 2 | 5
2 | Surface Infrastructure and Enabling | 2 | Yabba Creek Road Option 1 | 220 | 22220 | Old Forestry Drive Option 2 Construction | 5
2 | Surface Infrastructure and Enabling | 2 | Yabba Creek Road Option 1 | 300 | 22300 | Yielo Rd | 4
2 | Surface Infrastructure and Enabling | 2 | Yabba Creek Road Option 1 | 310 | 22310 | Preliminaries Upgrade of Yielo Rd | 5
2 | Surface Infrastructure and Enabling | 2 | Yabba Creek Road Option 1 | 320 | 22320 | Upgrade of Yielo Rd Construction | 5
2 | Surface Infrastructure and Enabling | 2 | Yabba Creek Road Option 1 | 400 | 22400 | Walkers Top Access Track | 4
2 | Surface Infrastructure and Enabling | 2 | Yabba Creek Road Option 1 | 410 | 22410 | Preliminaries Walkers Top Access Track | 5
2 | Surface Infrastructure and Enabling | 2 | Yabba Creek Road Option 1 | 420 | 22420 | Walkers Top Access Track Construction | 5
2 | Surface Infrastructure and Enabling | 2 | Yabba Creek Road Option 1 | 500 | 22500 | Access Roads - The Borgan | 4
2 | Surface Infrastructure and Enabling | 2 | Yabba Creek Road Option 1 | 510 | 22510 | Preliminaries Access Roads - The Borgan | 5
2 | Surface Infrastructure and Enabling | 2 | Yabba Creek Road Option 1 | 520 | 22520 | Access Roads - The Borgan | 5
2 | Surface Infrastructure and Enabling | 2 | Yabba Creek Road Option 1 | 600 | 22600 | Lower Res Access Road | 4
2 | Surface Infrastructure and Enabling | 2 | Yabba Creek Road Option 1 | 610 | 22610 | Lower Res Access Road | 5
2 | Surface Infrastructure and Enabling | 2 | Yabba Creek Road Option 1 | 700 | 22700 | Lower Res Haul Road - Construct and Maintain | 4
2 | Surface Infrastructure and Enabling | 2 | Yabba Creek Road Option 1 | 710 | 22710 | Lower Res Haul Road - Construct and Maintain | 5
2 | Surface Infrastructure and Enabling | 2 | Yabba Creek Road Option 1 | 800 | 22800 | Bella Creek Road | 4
2 | Surface Infrastructure and Enabling | 2 | Yabba Creek Road Option 1 | 810 | 22810 | Bella Creek Road | 5
2 | Surface Infrastructure and Enabling | 2 | Yabba Creek Road Option 1 | 900 | 22900 | Yabba Creek Bridge | 4
2 | Surface Infrastructure and Enabling | 2 | Yabba Creek Road Option 1 | 910 | 22910 | Yabba Creek Bridge | 5
2 | Surface Infrastructure and Enabling | 3 | Kingaham Creek Bridge | 000 | 23000 | Kingaham Creek Bridge | 4
2 | Surface Infrastructure and Enabling | 3 | Kingaham Creek Bridge | 010 | 23010 | Kingaham Creek Bridge | 5
2 | Surface Infrastructure and Enabling | 3 | Kingaham Creek Bridge | 100 | 23100 | Road to Lower Inlet / Outlet Structure | 4
2 | Surface Infrastructure and Enabling | 3 | Kingaham Creek Bridge | 110 | 23110 | Road to Lower Inlet / Outlet Structure | 5
2 | Surface Infrastructure and Enabling | 3 | Kingaham Creek Bridge | 200 | 23200 | Road to Upper Res/Saddle Dam | 4
2 | Surface Infrastructure and Enabling | 3 | Kingaham Creek Bridge | 210 | 23210 | Road to Upper Res/Saddle Dam | 5
2 | Surface Infrastructure and Enabling | 3 | Kingaham Creek Bridge | 300 | 23300 | Ring Road at Upper Res incl. Access to upper intake and Bellmouth | 4
2 | Surface Infrastructure and Enabling | 3 | Kingaham Creek Bridge | 310 | 23310 | Ring Road at Upper Res incl. Access to upper intake and Bellmouth | 5
3 | Underground Waterways | 0 | Underground Waterways | 000 | 30000 | Underground Waterways | 3
3 | Underground Waterways | 1 | Underground Waterways | 100 | 31100 | Contractor Indirect & overheads stage 1 | 4
3 | Underground Waterways | 1 | Underground Waterways | 110 | 31110 | Contractor Indirects & overheads | 5
3 | Underground Waterways | 1 | Underground Waterways | 200 | 31200 | Design | 4
3 | Underground Waterways | 1 | Underground Waterways | 210 | 31210 | Design | 5
3 | Underground Waterways | 2 | North Alignment Waterway | 000 | 32000 | North Alignment Waterway | 4
3 | Underground Waterways | 2 | North Alignment Waterway | 010 | 32010 | Upper Inlet/Outlet Structure Bellmouth - North | 5
3 | Underground Waterways | 2 | North Alignment Waterway | 020 | 32020 | Upper Inlet/Outlet Structure Gate Shaft - North | 5
3 | Underground Waterways | 2 | North Alignment Waterway | 030 | 32030 | Lower Inlet/Outlet Structure Bellmouth - North | 5
3 | Underground Waterways | 2 | North Alignment Waterway | 040 | 32040 | Lower Inlet/Outlet Structure Gate Shaft Middle to Top - North | 5
3 | Underground Waterways | 2 | North Alignment Waterway | 050 | 32050 | Lower Inlet/Outlet Structure Gate Shaft Lower Part/Square Section - North | 5
3 | Underground Waterways | 2 | North Alignment Waterway | 060 | 32060 | Low Pressure Tunnel - North | 5
3 | Underground Waterways | 2 | North Alignment Waterway | 070 | 32070 | Erection Chamber - Upper - North | 5
3 | Underground Waterways | 2 | North Alignment Waterway | 080 | 32080 | Vertical Pressure Shaft - North | 5
3 | Underground Waterways | 2 | North Alignment Waterway | 090 | 32090 | Erection Chamber - Lower - North | 5
3 | Underground Waterways | 2 | North Alignment Waterway | 100 | 32100 | High Pressure Tunnel - North | 5
3 | Underground Waterways | 2 | North Alignment Waterway | 110 | 32110 | Penstock Steel Lined - North | 5
3 | Underground Waterways | 2 | North Alignment Waterway | 120 | 32120 | Tailrace Collector Tunnel - North | 5
3 | Underground Waterways | 2 | North Alignment Waterway | 130 | 32130 | Tailrace Tunnel - North | 5
3 | Underground Waterways | 2 | North Alignment Waterway | 140 | 32140 | Surge Tank - North | 5
3 | Underground Waterways | 3 | South Alignment Waterway | 000 | 33000 | South Alignment Waterway | 4
3 | Underground Waterways | 3 | South Alignment Waterway | 010 | 33010 | Upper Inlet/Outlet Structure Bellmouth - South | 5
3 | Underground Waterways | 3 | South Alignment Waterway | 020 | 33020 | Upper Inlet/Outlet Structure Gate Shaft - South | 5
3 | Underground Waterways | 3 | South Alignment Waterway | 030 | 33030 | Lower Inlet/Outlet Structure Bellmouth - South | 5
3 | Underground Waterways | 3 | South Alignment Waterway | 040 | 33040 | Lower Inlet/Outlet Structure Gate Shaft Middle to Top - South | 5
3 | Underground Waterways | 3 | South Alignment Waterway | 050 | 33050 | Lower Inlet/Outlet Structure Gate Shaft Lower Part/Square Section - South | 5
3 | Underground Waterways | 3 | South Alignment Waterway | 060 | 33060 | Low Pressure Tunnel - South | 5
3 | Underground Waterways | 3 | South Alignment Waterway | 070 | 33070 | Erection Chamber - Upper - South | 5
3 | Underground Waterways | 3 | South Alignment Waterway | 080 | 33080 | Vertical Pressure Shaft - South | 5
3 | Underground Waterways | 3 | South Alignment Waterway | 090 | 33090 | Erection Chamber - Lower - South | 5
3 | Underground Waterways | 3 | South Alignment Waterway | 100 | 33100 | High Pressure Tunnel - South | 5
3 | Underground Waterways | 3 | South Alignment Waterway | 110 | 33110 | Penstock Steel Lined - South | 5
3 | Underground Waterways | 3 | South Alignment Waterway | 120 | 33120 | Tailrace Collector Tunnel - South | 5
3 | Underground Waterways | 3 | South Alignment Waterway | 130 | 33130 | Tailrace Tunnel - South | 5
3 | Underground Waterways | 3 | South Alignment Waterway | 140 | 33140 | Surge Tank - South | 5
3 | Underground Waterways | 4 | Platform and Control Buildings | 000 | 34000 | Platform and Control Buildings | 4
3 | Underground Waterways | 4 | Platform and Control Buildings | 010 | 34010 | Upper Inlet/Outlet Platform and Control Building | 5
3 | Underground Waterways | 4 | Platform and Control Buildings | 020 | 34020 | Lower Inlet/Outlet Platform and Control Building | 5
3 | Underground Waterways | 5 | Lower Inlet Structure Approach | 000 | 35000 | Lower Inlet Structure Approach | 4
3 | Underground Waterways | 5 | Lower Inlet Structure Approach | 010 | 35010 | Lower Inlet/Outlet Structure - Approach | 5
3 | Underground Waterways | 6 | Surge Tanks Permanent access tunnel | 000 | 36000 | Surge Tanks Permanent access tunnel | 4
3 | Underground Waterways | 6 | Surge Tanks Permanent access tunnel | 010 | 36010 | Surge Tanks Permanent access tunnel | 5
3 | Underground Waterways | 7 | Assembly Chambers | 000 | 37000 | Assembly Chambers | 4
3 | Underground Waterways | 7 | Assembly Chambers | 010 | 37010 | Upstream Assembly Chambers, Connection Tunnels and Adit | 5
3 | Underground Waterways | 7 | Assembly Chambers | 020 | 37020 | Downstream Assembly Chambers, Connection Tunnels and Adit | 5
3 | Underground Waterways | 8 | Site Rehabilitation | 000 | 38000 | Site Rehabilitation | 4
3 | Underground Waterways | 8 | Site Rehabilitation | 010 | 38010 | Site Rehabilitation | 5
4 | Underground Access & Caverns | 0 | Underground Access & Caverns | 000 | 40000 | Underground Access & Caverns | 3 | More than 10 level 4 WBS, so an extra integer has been created
4 | Underground Access & Caverns | 1 | Underground Access & Caverns | 100 | 41100 | Contractor Indirect & overheads | 4
4 | Underground Access & Caverns | 1 | Underground Access & Caverns | 110 | 41110 | Contractor Indirects & overheads | 5
4 | Underground Access & Caverns | 1 | Underground Access & Caverns | 200 | 41200 | Design | 4
4 | Underground Access & Caverns | 1 | Underground Access & Caverns | 210 | 41210 | Detail Design - Main Facility | 5
4 | Underground Access & Caverns | 1 | Underground Access & Caverns | 220 | 41220 | Detail Design - OEM | 5
4 | Underground Access & Caverns | 1 | Underground Access & Caverns | 300 | 41300 | Site Clearing | 4
4 | Underground Access & Caverns | 1 | Underground Access & Caverns | 310 | 41310 | Site Clearing | 5
4 | Underground Access & Caverns | 1 | Underground Access & Caverns | 400 | 41400 | Construction Surface Facilities | 4
4 | Underground Access & Caverns | 1 | Underground Access & Caverns | 410 | 41410 | Construction Site Facilities - Platform Areas | 5
4 | Underground Access & Caverns | 1 | Underground Access & Caverns | 420 | 41420 | Grout plant - mobilise and demobilise | 5
4 | Underground Access & Caverns | 1 | Underground Access & Caverns | 430 | 41430 | Construction Site Facilities - Platform 2 - Concrete Plant | 5
4 | Underground Access & Caverns | 1 | Underground Access & Caverns | 440 | 41440 | Concrete batching plant - mobilise and demobilise | 5
4 | Underground Access & Caverns | 1 | Underground Access & Caverns | 450 | 41450 | Construction Site Facilities - Upper inlet / outlet - Concrete Plant | 5
4 | Underground Access & Caverns | 1 | Underground Access & Caverns | 500 | 41500 | ECTV Exploratory Drilling | 4
4 | Underground Access & Caverns | 1 | Underground Access & Caverns | 510 | 41510 | Exploratory Tunnel - Surface Works | 5
4 | Underground Access & Caverns | 1 | Underground Access & Caverns | 520 | 41520 | Exploratory Tunnel - Underground Works | 5
4 | Underground Access & Caverns | 1 | Underground Access & Caverns | 530 | 41530 | Exploratory Tunnel - Caverns Investigation | 5
4 | Underground Access & Caverns | 1 | Underground Access & Caverns | 540 | 41540 | Exploratory Tunnel - Management Services | 5
4 | Underground Access & Caverns | 1 | Underground Access & Caverns | 600 | 41600 | MAT and ECVT | 4
4 | Underground Access & Caverns | 1 | Underground Access & Caverns | 610 | 41610 | Main Access Tunnel (MAT) | 5
4 | Underground Access & Caverns | 1 | Underground Access & Caverns | 620 | 41620 | Emergency, Cable and Ventilation Tunnel (ECVT) Completion | 5
4 | Underground Access & Caverns | 1 | Underground Access & Caverns | 700 | 41700 | Power Cavern | 4
4 | Underground Access & Caverns | 1 | Underground Access & Caverns | 710 | 41710 | Power Cavern | 5
4 | Underground Access & Caverns | 1 | Underground Access & Caverns | 800 | 41800 | Transformer Cavern | 4
4 | Underground Access & Caverns | 1 | Underground Access & Caverns | 810 | 41810 | Transformer Cavern | 5
4 | Underground Access & Caverns | 1 | Underground Access & Caverns | 900 | 41900 | IPB Galleries (x 6) | 4
4 | Underground Access & Caverns | 1 | Underground Access & Caverns | 910 | 41910 | IPB Galleries (x 6) | 5
4 | Underground Access & Caverns | 1 | MAT Tunnels between Power Cavern and Transformer Cavern | 000 | 41000 | MAT Tunnels between Power Cavern and Transformer Cavern | 4
4 | Underground Access & Caverns | 1 | MAT Tunnels between Power Cavern and Transformer Cavern | 010 | 41010 | MAT Tunnels between Power Cavern and Transformer Cavern | 5
4 | Underground Access & Caverns | 1 | MAT Tunnels between Power Cavern and Transformer Cavern | 100 | 41100 | Site Rehabilitation | 4
4 | Underground Access & Caverns | 1 | MAT Tunnels between Power Cavern and Transformer Cavern | 110 | 41110 | Site Rehabilitation | 5
5 | Powerhouse Mech & Elec | 0 | Powerhouse Mech & Elec | 000 | 50000 | Powerhouse Mech & Elec | 3
5 | Powerhouse Mech & Elec | 0 | Powerhouse Mech & Elec | 100 | 50100 | Contractor Indirect & overheads | 4
5 | Powerhouse Mech & Elec | 0 | Powerhouse Mech & Elec | 110 | 50110 | Contractor Indirects & overheads | 5
5 | Powerhouse Mech & Elec | 0 | Powerhouse Mech & Elec | 200 | 50200 | Design | 4
5 | Powerhouse Mech & Elec | 0 | Powerhouse Mech & Elec | 210 | 50210 | Design | 5
5 | Powerhouse Mech & Elec | 0 | Powerhouse Mech & Elec | 300 | 50300 | Mech & Elec | 4
5 | Powerhouse Mech & Elec | 0 | Powerhouse Mech & Elec | 310 | 50310 | Mech & Elec | 5
5 | Powerhouse Mech & Elec | 0 | Powerhouse Mech & Elec | 400 | 50400 | Power Turbines | 4
5 | Powerhouse Mech & Elec | 0 | Powerhouse Mech & Elec | 410 | 50410 | Power Turbines | 5
5 | Powerhouse Mech & Elec | 0 | Powerhouse Mech & Elec | 500 | 50500 | Transformers | 4
5 | Powerhouse Mech & Elec | 0 | Powerhouse Mech & Elec | 510 | 50510 | Transformers | 5
5 | Powerhouse Mech & Elec | 0 | Powerhouse Mech & Elec | 600 | 50600 | Hydro-Mechanical Works | 4
5 | Powerhouse Mech & Elec | 0 | Powerhouse Mech & Elec | 610 | 50610 | Hydro-Mechanical Works | 5
5 | Powerhouse Mech & Elec | 0 | Powerhouse Mech & Elec | 700 | 50700 | Electrical Install | 4
5 | Powerhouse Mech & Elec | 0 | Powerhouse Mech & Elec | 710 | 50710 | Electrical Install | 5
5 | Powerhouse Mech & Elec | 0 | Powerhouse Mech & Elec | 800 | 50800 | Power Evacuation and Grid Connection | 4
5 | Powerhouse Mech & Elec | 0 | Powerhouse Mech & Elec | 810 | 50810 | Power Evacuation and Grid Connection | 5
5 | Powerhouse Mech & Elec | 0 | Powerhouse Mech & Elec | 900 | 50900 | Commissioning OEM | 4
5 | Powerhouse Mech & Elec | 0 | Powerhouse Mech & Elec | 910 | 50910 | Commissioning OEM | 5
5 | Powerhouse Mech & Elec | 1 | Site Rehabilitation | 000 | 51000 | Site Rehabilitation | 4
5 | Powerhouse Mech & Elec | 1 | Site Rehabilitation | 010 | 51010 | Site Rehabilitation | 5
6 | Lower Reservoir | 0 | Lower Reservoir | 000 | 60000 | Lower Reservoir | 3
6 | Lower Reservoir | 0 | Lower Reservoir | 100 | 60100 | Contractor Indirect & overheads | 4
6 | Lower Reservoir | 0 | Lower Reservoir | 110 | 60110 | Contractor Indirect & overheads | 5
6 | Lower Reservoir | 0 | Lower Reservoir | 200 | 60200 | Design | 4
6 | Lower Reservoir | 0 | Lower Reservoir | 210 | 60210 | Design | 5
6 | Lower Reservoir | 0 | Lower Reservoir | 300 | 60300 | Site Clearing | 4
6 | Lower Reservoir | 0 | Lower Reservoir | 310 | 60310 | Site Clearing | 5
6 | Lower Reservoir | 0 | Lower Reservoir | 400 | 60400 | Quarry Development and Material Operations | 4
6 | Lower Reservoir | 0 | Lower Reservoir | 410 | 60410 | Quarry Development and Material Operations | 5
6 | Lower Reservoir | 0 | Lower Reservoir | 500 | 60500 | Diversion and Watering | 4
6 | Lower Reservoir | 0 | Lower Reservoir | 510 | 60510 | Diversion and Watering | 5
6 | Lower Reservoir | 0 | Lower Reservoir | 600 | 60600 | Foundations | 4
6 | Lower Reservoir | 0 | Lower Reservoir | 610 | 60610 | Foundations | 5
6 | Lower Reservoir | 0 | Lower Reservoir | 700 | 60700 | Dam Construction | 4
6 | Lower Reservoir | 0 | Lower Reservoir | 710 | 60710 | Dam Construction | 5
6 | Lower Reservoir | 0 | Lower Reservoir | 800 | 60800 | Spillway | 4
6 | Lower Reservoir | 0 | Lower Reservoir | 810 | 60810 | Spillway | 5
6 | Lower Reservoir | 0 | Lower Reservoir | 900 | 60900 | Intake Tower | 4
6 | Lower Reservoir | 0 | Lower Reservoir | 910 | 60910 | Intake Tower | 5
6 | Lower Reservoir | 1 | Outlet Works | 000 | 61000 | Outlet Works | 4
6 | Lower Reservoir | 1 | Outlet Works | 010 | 61010 | Outlet Works | 5
6 | Lower Reservoir | 1 | Outlet Works | 100 | 61100 | Fishway | 4
6 | Lower Reservoir | 1 | Outlet Works | 110 | 61110 | Fishway | 5
6 | Lower Reservoir | 1 | Outlet Works | 200 | 61200 | Over topping Event of the Lower Dam | 4
6 | Lower Reservoir | 1 | Outlet Works | 210 | 61210 | Over topping Event of the Lower Dam | 5
6 | Lower Reservoir | 1 | Outlet Works | 300 | 61300 | Traffic Control | 4
6 | Lower Reservoir | 1 | Outlet Works | 310 | 61310 | Traffic Control | 5
6 | Lower Reservoir | 1 | Outlet Works | 400 | 61400 | Site Rehabilitation | 4
6 | Lower Reservoir | 1 | Outlet Works | 410 | 61410 | Site Rehabilitation | 5
7 | Upper Reservoir | 0 | Upper Reservoir | 000 | 70000 | Upper Reservoir | 3
7 | Upper Reservoir | 0 | Upper Reservoir | 100 | 70100 | Contractor Indirect & overheads | 4
7 | Upper Reservoir | 0 | Upper Reservoir | 110 | 70110 | Contractor Indirect & overheads | 5
7 | Upper Reservoir | 0 | Upper Reservoir | 200 | 70200 | Design | 4
7 | Upper Reservoir | 0 | Upper Reservoir | 210 | 70210 | Design | 5
7 | Upper Reservoir | 0 | Upper Reservoir | 300 | 70300 | Site Clearing | 4
7 | Upper Reservoir | 0 | Upper Reservoir | 310 | 70310 | Site Clearing | 5
7 | Upper Reservoir | 0 | Upper Reservoir | 400 | 70400 | Quarry Development and Material Operations | 4
7 | Upper Reservoir | 0 | Upper Reservoir | 410 | 70410 | Quarry Development and Material Operations | 5
7 | Upper Reservoir | 0 | Upper Reservoir | 500 | 70500 | Diversion and Watering | 4
7 | Upper Reservoir | 0 | Upper Reservoir | 510 | 70510 | Diversion and Watering | 5
7 | Upper Reservoir | 0 | Upper Reservoir | 600 | 70600 | Foundations | 4
7 | Upper Reservoir | 0 | Upper Reservoir | 610 | 70610 | Foundations | 5
7 | Upper Reservoir | 0 | Upper Reservoir | 700 | 70700 | Dam Construction | 4
7 | Upper Reservoir | 0 | Upper Reservoir | 710 | 70710 | Main CFRD Dam | 5
7 | Upper Reservoir | 0 | Upper Reservoir | 720 | 70720 | Main Saddle (CFRD) Dam | 5
7 | Upper Reservoir | 0 | Upper Reservoir | 730 | 70730 | Secondary Saddle (CFRD) Dam A | 5
7 | Upper Reservoir | 0 | Upper Reservoir | 740 | 70740 | Secondary Saddle (CFRD) Dam B1 | 5
7 | Upper Reservoir | 0 | Upper Reservoir | 750 | 70750 | Secondary Saddle (CFRD) Dam B2 | 5
7 | Upper Reservoir | 0 | Upper Reservoir | 760 | 70760 | Secondary Saddle (CFRD) Dam No.B3 | 5
7 | Upper Reservoir | 0 | Upper Reservoir | 800 | 70800 | Emergency Spillway | 4
7 | Upper Reservoir | 0 | Upper Reservoir | 810 | 70810 | Emergency Spillway | 5
7 | Upper Reservoir | 0 | Upper Reservoir | 900 | 70900 | Traffic Control | 4
7 | Upper Reservoir | 0 | Upper Reservoir | 910 | 70910 | Traffic Control | 5
7 | Upper Reservoir | 1 | Site Rehabilitation | 000 | 71000 | Site Rehabilitation | 4
7 | Upper Reservoir | 1 | Site Rehabilitation | 010 | 71010 | Site Rehabilitation | 5
8 | Transmissions | 0 | Transmissions | 000 | 80000 | Transmissions | 3
8 | Transmissions | 1 | Transmissions - Tarong | 000 | 81000 | Borumba - Tarong 275kV | 4 | Renumbered L4 to remove double up
8 | Transmissions | 1 | Transmissions - Tarong | 010 | 81010 | Borumba - Tarong 275kV | 5
8 | Transmissions | 2 | Transmissions - Woolooga | 100 | 82100 | Borumba - Woolooga 275kV | 4 | Renumbered L4 to remove double up
8 | Transmissions | 2 | Transmissions - Woolooga | 110 | 82110 | Borumba - Woolooga 275kV | 5
9 | Contingency & Escalation | 0 | Contingency & Escalation | 000 | 90000 | Contingency & Escalation | 3 | Need to amend L3
9 | Contingency & Escalation | 9 | Contingency & Escalation | 000 | 99000 | Contingency & Escalation | 4 | Need to add
9 | Contingency & Escalation | 9 | Contingency & Escalation | 100 | 99100 | Contingency | 4 | Doesn’t fit
9 | Contingency & Escalation | 9 | Contingency & Escalation | 110 | 99110 | P50 Contingency QH Costs | 5
9 | Contingency & Escalation | 9 | Contingency & Escalation | 120 | 99120 | P90 Contingency QH Costs | 5
9 | Contingency & Escalation | 9 | Contingency & Escalation | 130 | 99130 | P50 Contingency Surface Infrastructure and Enabling | 5
9 | Contingency & Escalation | 9 | Contingency & Escalation | 140 | 99140 | P90 Contingency Surface Infrastructure and Enabling | 5
9 | Contingency & Escalation | 9 | Contingency & Escalation | 150 | 99150 | P50 Contingency Underground Waterways | 5
9 | Contingency & Escalation | 9 | Contingency & Escalation | 160 | 99160 | P90 Contingency Underground Waterways | 5
9 | Contingency & Escalation | 9 | Contingency & Escalation | 170 | 99170 | P50 Contingency Underground Access & Caverns | 5
9 | Contingency & Escalation | 9 | Contingency & Escalation | 180 | 99180 | P90 Contingency Underground Access & Caverns | 5
9 | Contingency & Escalation | 9 | Contingency & Escalation | 190 | 99190 | P50 Contingency Powerhouse Mech & Elec | 5
9 | Contingency & Escalation | 9 | Contingency & Escalation | 200 | 99200 | P90 Contingency Powerhouse Mech & Elec | 5
9 | Contingency & Escalation | 9 | Contingency & Escalation | 210 | 99210 | P50 Contingency Lower Reservoir | 5
9 | Contingency & Escalation | 9 | Contingency & Escalation | 220 | 99220 | P90 Contingency Lower Reservoir | 5
9 | Contingency & Escalation | 9 | Contingency & Escalation | 230 | 99230 | P50 Contingency Upper Reservoir | 5
9 | Contingency & Escalation | 9 | Contingency & Escalation | 240 | 99240 | P90 Contingency Upper Reservoir | 5
9 | Contingency & Escalation | 9 | Contingency & Escalation | 500 | 99500 | Escalation | 4 | Doesn’t fit
9 | Contingency & Escalation | 9 | Contingency & Escalation | 510 | 99510 | Escalation QH Costs | 5
9 | Contingency & Escalation | 9 | Contingency & Escalation | 520 | 99520 | Escalation Surface Infrastructure and Enabling | 5
9 | Contingency & Escalation | 9 | Contingency & Escalation | 530 | 99530 | Escalation Underground Waterways | 5
9 | Contingency & Escalation | 9 | Contingency & Escalation | 540 | 99540 | Escalation Underground Access & Caverns | 5
9 | Contingency & Escalation | 9 | Contingency & Escalation | 550 | 99550 | Escalation Powerhouse Mech & Elec | 5
9 | Contingency & Escalation | 9 | Contingency & Escalation | 560 | 99560 | Escalation Lower Reservoir | 5
9 | Contingency & Escalation | 9 | Contingency & Escalation | 570 | 99570 | Escalation Upper Reservoir | 5

## WBS Master
QldHydro Revised WBS Structure | [9 empty] | Sample Control Account
[10 empty] | BRP4-A2-17-010 |  | 0
Current at 02/04/2024
ENTERPRISE
L0 - Program |  | L1 - Projects |  | L2 - Phases |  | L3 - Area |  | L3-L4 - Element |  |  | L3-L5 - Sub Element | L3-L5 - Sub Element | BORUMBA WBS | L3-L5 - Sub Element | Pioneer-Burdekin Control Account TBA
Group ID | Group Description | Group ID | Group Description | Group ID | Group Description | Group ID | Group Description | Group ID |  | Group Description | Group ID | Group ID | Group Description | Group ID | Group Description
QH | QLD Hydro PHES | BR | Borumba PHES | P0 | Program | A1 | QH Costs | A1-10 | 110000 | QH Delivery (Staff) | A1-10-010 | A110010 | Project (Staff)
|  | PB | Pioneer-Burdekin PHES | P1 | Feasibility Studies | A2 | Surface Infrastructure and Enabling | A1-20 | 120000 | Project Contractors | A1-10-020 | A110020 | Commercial (Staff)
|  | QH | Program / Corporate | P2 | Options Analysis & DAR | A3 | Underground Waterways | A1-30 | 130000 | Engineering | A1-10-030 | A110030 | Engineering Assurance (Staff) |  | TBD during DAR Phase
|  |  |  | P3 | Design Development & Procurement | A4 | Underground Access & Caverns | A1-40 | 140000 | Environment and Approvals | A1-10-040 | A110040 | Health & Safety (Staff)
|  |  |  | P4 | Delivery | A5 | Powerhouse Mech & Elec | A1-50 | 150000 | Community Development and Stakeholder | A1-10-050 | A110050 | Project Controls (Staff)
|  |  |  | P5 | Transition to Operations | A6 | Lower Reservoir | A1-60 | 160000 | Land Acquisition | A1-10-060 | A110060 | Environment (Staff)
|  |  |  | P6 | Close-out | A7 | Upper Reservoir | A1-70 | 170000 | Indirect | A1-10-070 | A110070 | Community and Stakeholder (Staff)
[6 empty] | A8 | Transmissions | A1-80 | 180000 | Ops Readiness & Commissioning | A1-10-080 | A110080 | Land (Staff)
[6 empty] | A9 | Contingency & Escalation | A2-01 | 201000 | Contractor Indirect & overheads | A1-10-090 | A110090 | Regional Development (Staff)
[8 empty] | A2-02 | 202000 | Design | A1-10-100 | A110100 | Quality (Staff)
[8 empty] | A2-03 | 203000 | Camps | A1-20-010 | A120010 | Project Support
[8 empty] | A2-04 | 204000 | Geotechnical | A1-20-020 | A120020 | Commercial Pre-Contracts
[8 empty] | A2-05 | 205000 | Temporary Water Infrastructure | A1-20-030 | A120030 | Commercial - Contracts Admin
[8 empty] | A2-06 | 206000 | Communication Infrastructure Upgrade | A1-20-040 | A120040 | Project Controls
[8 empty] | A2-07 | 207000 | Power Supply Upgrade | A1-20-050 | A120050 | Legal
[8 empty] | A2-10 | 210000 | Yabba Creek Road Option 1 | A1-20-060 | A120060 | Health and Safety Consultants
[8 empty] | A2-12 | 212000 | Old Forestry Drive Option 2 | A1-20-070 | A120070 | Engineering Assurance
[8 empty] | A2-13 | 213000 | Yielo Rd | A1-20-080 | A120080 | Operation and Maintenance Strategy
[6 empty] | DAR (Pioneer-Burdekin Only) |  | A2-14 | 214000 | Walkers Top Access Track | A1-30-010 | A130010 | Specialist Engineering - External Advisory Services
[6 empty] | W01 | Project Management & Overheads | A2-15 | 215000 | Access Roads - The Borgan | A1-30-020 | A130020 | Specialist Engineering - Owners Engineer
[6 empty] | W02 | Health Safety & Environment | A2-16 | 216000 | Lower Res Access Road | A1-30-030 | A130030 | Specialist Engineering - Design for Procurement
[6 empty] | W03 | Community & Stakeholder Engagement | A2-17 | 217000 | Lower Res Haul Road - Construct and Maintain | A1-30-040 | A130040 | Specialist Engineering - FEED
[6 empty] | W04 | Cultural Heritage & Native Title | A2-18 | 218000 | Bella Creek Road | A1-30-050 | A130050 | Specialist Engineering - Exploratory Works
[6 empty] | W05 | Environment & Approvals | A2-19 | 219000 | Yabba Creek Bridge | A1-30-060 | A130060 | Specialist Advisors - Technical Assurance
[6 empty] | W06 | Geotechnical Drilling | A2-20 | 220000 | Kingaham Creek Bridge | A1-30-070 | A130070 | Connection Application Process/Services
[6 empty] | W07 | Detailed Analytical Report | A2-21 | 221000 | Road to Lower Inlet / Outlet Structure | A1-30-080 | A130080 | Independent certifier
[6 empty] | W08 | Engineering & Design | A2-22 | 222000 | Road to Upper Res/Saddle Dam | A1-40-010 | A140010 | Technical Advisors - EIS Approvals and Studies
[6 empty] | W09 | Land Access & Acquisition | A2-23 | 223000 | Ring Road at Upper Res incl. Access to upper intake and Bellmouth | A1-40-020 | A140020 | EIS - Engineering Input
[6 empty] | W10 | Procurement & Commercial | A3-01 | 301000 | Contractor Indirect & overheads stage 1 | A1-40-030 | A140030 | EIS - Technical Studies
[6 empty] | W11 | Quality Assurance and Gateway Reviews | A3-02 | 302000 | Design | A1-40-040 | A140040 | Exploratory Works Approvals
[6 empty] | W12 | Contingency & Escalation | A3-10 | 310000 | North Alignment Waterway | A1-40-050 | A140050 | Main Works - Approvals
[8 empty] | A3-20 | 320000 | South Alignment Waterway | A1-40-060 | A140060 | Offset Implementation
[8 empty] | A3-30 | 330000 | Platform and Control Buildings | A1-40-070 | A140070 | Sustainability
[8 empty] | A3-40 | 340000 | Lower Inlet Structure Approach | A1-40-080 | A140080 | Office of the Coordinator-General (OCG Costs)
[8 empty] | A3-50 | 350000 | Surge Tanks Permanent access tunnel | A1-40-090 | A140090 | EIS - Delivery
[8 empty] | A3-60 | 360000 | Assembly Chambers | A1-40-100 | A140100 | GIS Support
[8 empty] | A3-70 | 370000 | Site Rehabilitation | A1-40-110 | A140110 | Cultural Heritage - Investigations and Monitoring
[8 empty] | A4-01 | 401000 | Contractor Indirect & overheads | A1-40-120 | A140120 | Indigenous Land Use Agreement
[8 empty] | A4-02 | 402000 | Design | A1-40-130 | A140130 | Compliance Monitoring
[8 empty] | A4-03 | 403000 | Site Clearing | A1-40-140 | A140140 | Indigenous Partnerships
[8 empty] | A4-04 | 404000 | Construction Surface Facilities | A1-50-010 | A150010 | Community and Stakeholder Consultants
[8 empty] | A4-05 | 405000 | ECTV Exploratory Drilling | A1-50-020 | A150020 | Community Benefits Program
[8 empty] | A4-06 | 406000 | MAT and ECVT | A1-50-030 | A150030 | Sponsorships
[8 empty] | A4-07 | 407000 | Power Cavern | A1-50-040 | A150040 | Community Engagement Program
[8 empty] | A4-08 | 408000 | Transformer Cavern | A1-50-050 | A150050 | Regional Development
[8 empty] | A4-09 | 409000 | IPB Galleries (x 6) | A1-50-060 | A150060 | Regional Development Accommodation Partners
[5 empty] | l |  |  | A4-10 | 410000 | MAT Tunnels between Power Cavern and Transformer Cavern | A1-50-070 | A150070 | Regional Development Community Infrastructure
[8 empty] | A4-12 | 412000 | Site Rehabilitation | A1-50-080 | A150080 | Regional Development - Community Development Initiatives (GRC)
[8 empty] | A5-01 | 501000 | Contractor Indirect & overheads | A1-50-090 | A150090 | Regional Development - Community Development Initiatives (SRC)
[8 empty] | A5-02 | 502000 | Design | A1-60-010 | A160010 | Land Access & Conveyancing
[8 empty] | A5-03 | 503000 | Mech & Elec | A1-60-020 | A160020 | Land Acquisition
[8 empty] | A5-04 | 504000 | Power Turbines | A1-60-030 | A160030 | Land Access - Specialist Advisors
[8 empty] | A5-05 | 505000 | Transformers | A1-70-010 | A170010 | Project Expenses – General
[8 empty] | A5-06 | 506000 | Hydro-Mechanical Works | A1-70-020 | A170020 | PPE
[8 empty] | A5-07 | 507000 | Electrical Install | A1-70-030 | A170030 | Emergency Response Plan
[8 empty] | A5-08 | 508000 | Power Evacuation and Grid Connection | A1-70-040 | A170040 | Travel, Accommodation & Disbursements
[8 empty] | A5-09 | 509000 | Commissioning OEM | A1-70-050 | A170050 | IT Software, Licenses & Equipment
[8 empty] | A5-10 | 510000 | Site Rehabilitation | A1-70-060 | A170060 | Training & Development (Delivery)
[8 empty] | A6-01 | 601000 | Contractor Indirect & overheads | A1-70-070 | A170070 | Mandatory Safety Training
[8 empty] | A6-02 | 602000 | Design | A1-70-080 | A170080 | Site Vehicles and Transport
[8 empty] | A6-03 | 603000 | Site Clearing | A1-70-090 | A170090 | Project Offices and Facilities
[8 empty] | A6-04 | 604000 | Quarry Development and Material Operations | A1-70-100 | A170100 | Portable Long Service Leave Levy
[8 empty] | A6-05 | 605000 | Diversion and Watering | A1-70-110 | A170110 | Insurances
[8 empty] | A6-06 | 606000 | Foundations | A1-70-120 | A170120 | Bid cost reimbursement
[8 empty] | A6-07 | 607000 | Dam Construction | A1-70-130 | A170130 | Site Equipment & Tooling
[8 empty] | A6-08 | 608000 | Spillway | A1-70-140 | A170140 | Corporate Overheads
[8 empty] | A6-09 | 609000 | Intake Tower | A1-70-150 | A170150 | Legal Costs
[8 empty] | A6-10 | 610000 | Outlet Works | A1-70-160 | A170160 | Site Communications
[8 empty] | A6-11 | 611000 | Fishway | A1-70-170 | A170170 | Finance costs (FBT)
[8 empty] | A6-12 | 612000 | Over topping Event of the Lower Dam | A1-70-180 | A170180 | Other Staff Costs (memberships, subscriptions)
[8 empty] | A6-13 | 613000 | Traffic Control | A1-80-010 | A180010 | Op Readiness
[8 empty] | A6-14 | 614000 | Site Rehabilitation | A1-80-020 | A180020 | Commissioning
[8 empty] | A7-01 | 701000 | Contractor Indirect & overheads | A1-80-030 | A180030 | Full Load Compliance Testing
[8 empty] | A7-02 | 702000 | Design | A2-01-010 | A201010 | Temporary Camps - Indirects and Overheads
[8 empty] | A7-03 | 703000 | Site Clearing | A2-01-020 | A201020 | Main Camps - Indirects and Overheads
[8 empty] | A7-04 | 704000 | Quarry Development and Material Operations | A2-01-030 | A201030 | Exploratory Works - Contractor Indirect & overheads
[8 empty] | A7-05 | 705000 | Diversion and Watering | A2-01-040 | A201040 | Enabling Works - Contractor Indirect & overheads
[8 empty] | A7-06 | 706000 | Foundations | A2-02-010 | A202010 | Design - Exploratory Works
[8 empty] | A7-07 | 707000 | Dam Construction | A2-02-020 | A202020 | Design - Enabling Works
[8 empty] | A7-08 | 708000 | Emergency Spillway | A2-02-030 | A202030 | Temp Camps Design
[8 empty] | A7-09 | 709000 | Traffic Control | A2-03-010 | A203010 | Temp Camps
[8 empty] | A7-10 | 710000 | Site Rehabilitation | A2-03-020 | A203020 | Upper Res Camps Hardstand
[8 empty] | A8-01 | 801000 | Borumba - Tarong 275kV | A2-03-030 | A203030 | Lower Res Camps Hardstand
[8 empty] | A8-02 | 802000 | Borumba - Woolooga 275kV | A2-03-040 | A203040 | Main Camps Hardstand
[8 empty] | A9-91 | 991000 | Contingency | A2-03-050 | A203050 | Upper Res Camps Install and Operate
[8 empty] | A9-95 | 995000 | Escalation | A2-03-060 | A203060 | Lower Res Camps Install and Operate
[11 empty] | A2-03-070 | A203070 | Main Camps Install and Operate
[11 empty] | A2-03-080 | A203080 | Camp Set up
[11 empty] | A2-04-010 | A204010 | Contractor Indirect & overheads
[11 empty] | A2-04-020 | A204020 | Geotechnical Studies
[11 empty] | A2-04-030 | A204030 | Geotechnical Drilling
[11 empty] | A2-04-040 | A204040 | Geotechnical Service Management
[11 empty] | A2-05-010 | A205010 | Preliminaries Temporary Water Infrastructure
[11 empty] | A2-05-020 | A205020 | Temporary Water Infrastructure
[11 empty] | A2-05-030 | A205030 | Temporary Water Supply
[11 empty] | A2-06-010 | A206010 | Preliminaries Communication Infrastructure Upgrade
[11 empty] | A2-06-020 | A206020 | Communication Infrastructure Upgrade
[11 empty] | A2-07-010 | A207010 | Preliminaries Power Supply Upgrade
[11 empty] | A2-07-020 | A207020 | Power Supply Upgrade
[11 empty] | A2-10-010 | A210010 | Preliminaries Yabba Ck Rd Option 1
[11 empty] | A2-10-020 | A210020 | Bridge 1 (on Yabba Ck Rd - Ana Branche No 1)
[11 empty] | A2-10-030 | A210030 | Bridge 2 (on Yabba Ck Rd - Ana Branche No 2)
[11 empty] | A2-10-040 | A210040 | Bridge 3 (on Yabba Ck Rd - No 1 Crossing - Neumans Crossing)
[11 empty] | A2-10-050 | A210050 | Bridge 4 (on Yabba Ck Rd - No 2 Crossing - Elbow Crossing)
[11 empty] | A2-10-060 | A210060 | Bridge 5 (on Yabba Ck Rd - No 3 Crossing - Andrews Crossing)
[11 empty] | A2-10-070 | A210070 | Bridge 6 (on Yabba Ck Rd - No ? Crossing - ????)
[11 empty] | A2-10-080 | A210080 | Bridge 7 (on Yabba Ck Rd - No 4 Crossing - Boardmans Crossing)
[11 empty] | A2-10-090 | A210090 | Bridge 8 (on Yabba Ck Rd - No 5 Crossing - Friends Crossing)
[11 empty] | A2-10-100 | A210100 | Bridge 9 (on Yabba Ck Rd - No 6 Crossing - Deep Crossing)
[11 empty] | A2-10-110 | A210110 | Bridge 10 (on Yabba Ck Rd - No 7 - Crossing - unknown name)
[11 empty] | A2-10-120 | A210120 | Upgrade Bella Creek Road intersection
[11 empty] | A2-12-010 | A212010 | Preliminaries Old Forestry Drive Option 2
[11 empty] | A2-12-020 | A212020 | Old Forestry Drive Option 2 Construction
[11 empty] | A2-13-010 | A213010 | Preliminaries Upgrade of Yielo Rd
[11 empty] | A2-13-020 | A213020 | Upgrade of Yielo Rd Construction
[11 empty] | A2-14-010 | A214010 | Preliminaries Walkers Top Access Track
[11 empty] | A2-14-020 | A214020 | Walkers Top Access Track Construction
[11 empty] | A2-15-010 | A215010 | Preliminaries Access Roads - The Borgan
[11 empty] | A2-15-020 | A215020 | Access Roads - The Borgan
[11 empty] | A2-16-010 | A216010 | Lower Res Access Road
[11 empty] | A2-17-010 | A217010 | Lower Res Haul Road - Construct and Maintain
[11 empty] | A2-18-010 | A218010 | Bella Creek Road
[11 empty] | A2-19-010 | A219010 | Yabba Creek Bridge
[11 empty] | A2-20-010 | A220010 | Kingaham Creek Bridge
[11 empty] | A2-21-010 | A221010 | Road to Lower Inlet / Outlet Structure
[11 empty] | A2-22-010 | A222010 | Road to Upper Res/Saddle Dam
[11 empty] | A2-23-010 | A223010 | Ring Road at Upper Res incl. Access to upper intake and Bellmouth
[11 empty] | A2-24-010 | A224010 | MAT / ECVT Portal Pad Excavation
[11 empty] | A3-01-110 | A301110 | Contractor Indirects & overheads
[11 empty] | A3-02-210 | A302210 | Design
[11 empty] | A3-10-010 | A310010 | Upper Inlet/Outlet Structure Bellmouth - North
[11 empty] | A3-10-020 | A310020 | Upper Inlet/Outlet Structure Gate Shaft - North
[11 empty] | A3-10-030 | A310030 | Lower Inlet/Outlet Structure Bellmouth - North
[11 empty] | A3-10-040 | A310040 | Lower Inlet/Outlet Structure Gate Shaft Middle to Top - North
[11 empty] | A3-10-050 | A310050 | Lower Inlet/Outlet Structure Gate Shaft Lower Part/Square Section - North
[11 empty] | A3-10-060 | A310060 | Low Pressure Tunnel - North
[11 empty] | A3-10-070 | A310070 | Erection Chamber - Upper - North
[11 empty] | A3-10-080 | A310080 | Vertical Pressure Shaft - North
[11 empty] | A3-10-090 | A310090 | Erection Chamber - Lower - North
[11 empty] | A3-10-100 | A310100 | High Pressure Tunnel - North
[11 empty] | A3-10-110 | A310110 | Penstock Steel Lined - North
[11 empty] | A3-10-120 | A310120 | Tailrace Collector Tunnel - North
[11 empty] | A3-10-130 | A310130 | Tailrace Tunnel - North
[11 empty] | A3-10-140 | A310140 | Surge Tank - North
[11 empty] | A3-20-010 | A320010 | Upper Inlet/Outlet Structure Bellmouth - South
[11 empty] | A3-20-020 | A320020 | Upper Inlet/Outlet Structure Gate Shaft - South
[11 empty] | A3-20-030 | A320030 | Lower Inlet/Outlet Structure Bellmouth - South
[11 empty] | A3-20-040 | A320040 | Lower Inlet/Outlet Structure Gate Shaft Middle to Top - South
[11 empty] | A3-20-050 | A320050 | Lower Inlet/Outlet Structure Gate Shaft Lower Part/Square Section - South
[11 empty] | A3-20-060 | A320060 | Low Pressure Tunnel - South
[11 empty] | A3-20-070 | A320070 | Erection Chamber - Upper - South
[11 empty] | A3-20-080 | A320080 | Vertical Pressure Shaft - South
[11 empty] | A3-20-090 | A320090 | Erection Chamber - Lower - South
[11 empty] | A3-20-100 | A320100 | High Pressure Tunnel - South
[11 empty] | A3-20-110 | A320110 | Penstock Steel Lined - South
[11 empty] | A3-20-120 | A320120 | Tailrace Collector Tunnel - South
[11 empty] | A3-20-130 | A320130 | Tailrace Tunnel - South
[11 empty] | A3-20-140 | A320140 | Surge Tank - South
[11 empty] | A3-30-010 | A330010 | Upper Inlet/Outlet Platform and Control Building
[11 empty] | A3-30-020 | A330020 | Lower Inlet/Outlet Platform and Control Building
[11 empty] | A3-40-010 | A340010 | Lower Inlet/Outlet Structure - Approach
[11 empty] | A3-50-010 | A350010 | Surge Tanks Permanent access tunnel
[11 empty] | A3-60-010 | A360010 | Upstream Assembly Chambers, Connection Tunnels and Adit
[11 empty] | A3-60-020 | A360020 | Downstream Assembly Chambers, Connection Tunnels and Adit
[11 empty] | A3-70-010 | A370010 | Site Rehabilitation
[11 empty] | A4-01-010 | A401010 | Contractor Indirects & overheads
[11 empty] | A4-02-010 | A402010 | Detail Design - Main Facility
[11 empty] | A4-02-020 | A402020 | Detail Design - OEM
[11 empty] | A4-03-010 | A403010 | Site Clearing
[11 empty] | A4-04-010 | A404010 | Construction Site Facilities - Platform Areas
[11 empty] | A4-04-020 | A404020 | Grout plant - mobilise and demobilise
[11 empty] | A4-04-030 | A404030 | Construction Site Facilities - Platform 2 - Concrete Plant
[11 empty] | A4-04-040 | A404040 | Concrete batching plant - mobilise and demobilise
[11 empty] | A4-04-050 | A404050 | Construction Site Facilities - Upper inlet / outlet - Concrete Plant
[11 empty] | A4-05-010 | A405010 | Exploratory Tunnel - Surface Works
[11 empty] | A4-05-020 | A405020 | Exploratory Tunnel - Underground Works
[11 empty] | A4-05-030 | A405030 | Exploratory Tunnel - Caverns Investigation
[11 empty] | A4-05-040 | A405040 | Exploratory Tunnel - Management Services
[11 empty] | A4-06-010 | A406010 | Main Access Tunnel (MAT)
[11 empty] | A4-06-020 | A406020 | Emergency, Cable and Ventilation Tunnel (ECVT) Completion
[11 empty] | A4-07-010 | A407010 | Power Cavern
[11 empty] | A4-08-010 | A408010 | Transformer Cavern
[11 empty] | A4-09-010 | A409010 | IPB Galleries (x 6)
[11 empty] | A4-10-010 | A410010 | MAT Tunnels between Power Cavern and Transformer Cavern
[11 empty] | A4-12-010 | A412010 | Site Rehabilitation
[11 empty] | A5-01-010 | A501010 | Contractor Indirects & overheads
[11 empty] | A5-02-010 | A502010 | Design
[11 empty] | A5-03-010 | A503010 | Mech & Elec
[11 empty] | A5-04-010 | A504010 | Power Turbines
[11 empty] | A5-05-010 | A505010 | Transformers
[11 empty] | A5-06-010 | A506010 | Hydro-Mechanical Works
[11 empty] | A5-07-010 | A507010 | Electrical Install
[11 empty] | A5-08-010 | A508010 | Power Evacuation and Grid Connection
[11 empty] | A5-09-010 | A509010 | Commissioning OEM
[11 empty] | A5-10-010 | A510010 | Site Rehabilitation
[11 empty] | A6-01-010 | A601010 | Contractor Indirect & overheads
[11 empty] | A6-02-010 | A602010 | Design
[11 empty] | A6-03-010 | A603010 | Site Clearing
[11 empty] | A6-04-010 | A604010 | Quarry Development and Material Operations
[11 empty] | A6-05-010 | A605010 | Diversion and Watering
[11 empty] | A6-06-010 | A606010 | Foundations
[11 empty] | A6-07-010 | A607010 | Dam Construction
[11 empty] | A6-08-010 | A608010 | Spillway
[11 empty] | A6-09-010 | A609010 | Intake Tower
[11 empty] | A6-10-010 | A610010 | Outlet Works
[11 empty] | A6-11-010 | A611010 | Fishway
[11 empty] | A6-12-010 | A612010 | Over topping Event of the Lower Dam
[11 empty] | A6-13-010 | A613010 | Traffic Control
[11 empty] | A6-14-010 | A614010 | Site Rehabilitation
[11 empty] | A7-01-010 | A701010 | Contractor Indirect & overheads
[11 empty] | A7-02-010 | A702010 | Design
[11 empty] | A7-03-010 | A703010 | Site Clearing
[11 empty] | A7-04-010 | A704010 | Quarry Development and Material Operations
[11 empty] | A7-05-010 | A705010 | Diversion and Watering
[11 empty] | A7-06-010 | A706010 | Foundations
[11 empty] | A7-07-010 | A707010 | Main CFRD Dam
[11 empty] | A7-07-020 | A707020 | Main Saddle (CFRD) Dam
[11 empty] | A7-07-030 | A707030 | Secondary Saddle (CFRD) Dam A
[11 empty] | A7-07-040 | A707040 | Secondary Saddle (CFRD) Dam B1
[11 empty] | A7-07-050 | A707050 | Secondary Saddle (CFRD) Dam B2
[11 empty] | A7-07-060 | A707060 | Secondary Saddle (CFRD) Dam No.B3
[11 empty] | A7-08-010 | A708010 | Emergency Spillway
[11 empty] | A7-09-010 | A709010 | Traffic Control
[11 empty] | A7-10-010 | A710010 | Site Rehabilitation
[11 empty] | A8-01-010 | A801010 | Borumba - Tarong 275kV
[11 empty] | A8-02-110 | A802110 | Borumba - Woolooga 275kV
[11 empty] | A9-91-010 | A991010 | P50 Contingency QH Costs
[11 empty] | A9-91-020 | A991020 | P90 Contingency QH Costs
[11 empty] | A9-91-030 | A991030 | P50 Contingency Surface Infrastructure and Enabling
[11 empty] | A9-91-040 | A991040 | P90 Contingency Surface Infrastructure and Enabling
[11 empty] | A9-91-050 | A991050 | P50 Contingency Underground Waterways
[11 empty] | A9-91-060 | A991060 | P90 Contingency Underground Waterways
[11 empty] | A9-91-070 | A991070 | P50 Contingency Underground Access & Caverns
[11 empty] | A9-91-080 | A991080 | P90 Contingency Underground Access & Caverns
[11 empty] | A9-91-090 | A991090 | P50 Contingency Powerhouse Mech & Elec
[11 empty] | A9-91-100 | A991100 | P90 Contingency Powerhouse Mech & Elec
[11 empty] | A9-91-110 | A991110 | P50 Contingency Lower Reservoir
[11 empty] | A9-91-120 | A991120 | P90 Contingency Lower Reservoir
[11 empty] | A9-91-130 | A991130 | P50 Contingency Upper Reservoir
[11 empty] | A9-91-140 | A991140 | P90 Contingency Upper Reservoir
[11 empty] | A9-95-010 | A995010 | Escalation QH Costs
[11 empty] | A9-95-020 | A995020 | Escalation Surface Infrastructure and Enabling
[11 empty] | A9-95-030 | A995030 | Escalation Underground Waterways
[11 empty] | A9-95-040 | A995040 | Escalation Underground Access & Caverns
[11 empty] | A9-95-050 | A995050 | Escalation Powerhouse Mech & Elec
[11 empty] | A9-95-060 | A995060 | Escalation Lower Reservoir
[11 empty] | A9-95-070 | A995070 | Escalation Upper Reservoir

## Borumba WBS
L3 | L3 Desc | L4 | L4 Desc | L5 | Item | Description | Level | Responsible (From OBS) | Commentary | Proposed Control Account |  |  |  | #VALUE!
A1 | QH Costs | 00 | QH Costs | 000 | 100000 | QH Costs | 3 |  | Double up with Staff | BR-P4-A1-00-000 | BRIP4100000 |  | BRIP4100000 | #VALUE!
A1 | QH Costs | 10 | QH Delivery (Staff) | 000 | A110000 | QH Delivery (Staff) | 4 |  | Renumbered from zero to 1 | BR-P4-A1-10-000 | BRIP4A110000 | BRIP410000 | BRIP4A110000 | #VALUE!
A1 | QH Costs | 10 | QH Delivery (Staff) | 010 | A110010 | Project (Staff) | 5 | Leah Mckenzie |  | BR-P4-A1-10-010 | BRIP4A110010 | BRIP410010 | BRIP4A110010 | #VALUE!
A1 | QH Costs | 10 | QH Delivery (Staff) | 020 | A110020 | Commercial (Staff) | 5 | Jason Long |  | BR-P4-A1-10-020 | BRIP4A110020 | BRIP410020 | BRIP4A110020 | #VALUE!
A1 | QH Costs | 10 | QH Delivery (Staff) | 030 | A110030 | Engineering Assurance (Staff) | 5 | Head of Assets & Engineering |  | BR-P4-A1-10-030 | BRIP4A110030 | BRIP410030 | BRIP4A110030 | #VALUE!
A1 | QH Costs | 10 | QH Delivery (Staff) | 040 | A110040 | Health & Safety (Staff) | 5 | Kelly Palmer |  | BR-P4-A1-10-040 | BRIP4A110040 | BRIP410040 | BRIP4A110040 | #VALUE!
A1 | QH Costs | 10 | QH Delivery (Staff) | 050 | A110050 | Project Controls (Staff) | 5 | Mike Wells |  | BR-P4-A1-10-050 | BRIP4A110050 | BRIP410050 | BRIP4A110050 | #VALUE!
A1 | QH Costs | 10 | QH Delivery (Staff) | 060 | A110060 | Environment (Staff) | 5 | Andrew Nolan |  | BR-P4-A1-10-060 | BRIP4A110060 | BRIP410060 | BRIP4A110060 | #VALUE!
A1 | QH Costs | 10 | QH Delivery (Staff) | 070 | A110070 | Community and Stakeholder (Staff) | 5 | Julie Spencer |  | BR-P4-A1-10-070 | BRIP4A110070 | BRIP410070 | BRIP4A110070 | #VALUE!
A1 | QH Costs | 10 | QH Delivery (Staff) | 080 | A110080 | Land (Staff) | 5 | Head of Land (Darryl Pascal) |  | BR-P4-A1-10-080 | BRIP4A110080 | BRIP410080 | BRIP4A110080 | #VALUE!
A1 | QH Costs | 10 | QH Delivery (Staff) | 090 | A110090 | Regional Development (Staff) | 5 | Tracey Lyons |  | BR-P4-A1-10-090 | BRIP4A110090 | BRIP410090 | BRIP4A110090 | #VALUE!
A1 | QH Costs | 10 | QH Delivery (Staff) | 100 | A110100 | Quality (Staff) | 5 | Finton Moore |  | BR-P4-A1-10-100 | BRIP4A110100 | BRIP410100 | BRIP4A110100 | #VALUE!
A1 | QH Costs | 20 | Project Contractors | 000 | A120000 | Project Contractors | 4 |  |  | BR-P4-A1-20-000 | BRIP4A120000 | BRIP411000 | BRIP4A120000 | #VALUE!
A1 | QH Costs | 20 | Project Contractors | 010 | A120010 | Project Support | 5 | Leah Mckenzie |  | BR-P4-A1-20-010 | BRIP4A120010 | BRIP411010 | BRIP4A120010 | #VALUE!
A1 | QH Costs | 20 | Project Contractors | 020 | A120020 | Commercial Pre-Contracts | 5 | Jason Long |  | BR-P4-A1-20-020 | BRIP4A120020 | BRIP411020 | BRIP4A120020 | #VALUE!
A1 | QH Costs | 20 | Project Contractors | 030 | A120030 | Commercial - Contracts Admin | 5 | Jason Long |  | BR-P4-A1-20-030 | BRIP4A120030 | BRIP411030 | BRIP4A120030 | #VALUE!
A1 | QH Costs | 20 | Project Contractors | 040 | A120040 | Project Controls | 5 | Mike Wells |  | BR-P4-A1-20-040 | BRIP4A120040 | BRIP411040 | BRIP4A120040 | #VALUE!
A1 | QH Costs | 20 | Project Contractors | 050 | A120050 | Legal | 5 | Erin McCormick |  | BR-P4-A1-20-050 | BRIP4A120050 | BRIP411050 | BRIP4A120050 | #VALUE!
A1 | QH Costs | 20 | Project Contractors | 060 | A120060 | Health and Safety Consultants | 5 | Kelly Palmer | Split from H&S L4 | BR-P4-A1-20-060 | BRIP4A120060 | BRIP415020 | BRIP4A120060 | #VALUE!
A1 | QH Costs | 20 | Project Contractors | 070 | A120070 | Engineering Assurance | 5 | Head of Assets & Engineering |  | BR-P4-A1-20-070 | BRIP4A120070 | BRIP411060 | BRIP4A120070 | #VALUE!
A1 | QH Costs | 20 | Project Contractors | 080 | A120080 | Operation and Maintenance Strategy | 5 | Head of Assets & Engineering |  | BR-P4-A1-20-080 | BRIP4A120080 | BRIP411070 | BRIP4A120080 | #VALUE!
A1 | QH Costs | 30 | Engineering | 000 | A130000 | Engineering | 4 |  |  | BR-P4-A1-30-000 | BRIP4A130000 | BRIP412000 | BRIP4A130000 | #VALUE!
A1 | QH Costs | 30 | Engineering | 010 | A130010 | Specialist Engineering - External Advisory Services | 5 | Bradley Norwood |  | BR-P4-A1-30-010 | BRIP4A130010 | BRIP412010 | BRIP4A130010 | #VALUE!
A1 | QH Costs | 30 | Engineering | 020 | A130020 | Specialist Engineering - Owners Engineer | 5 | Bradley Norwood |  | BR-P4-A1-30-020 | BRIP4A130020 | BRIP412020 | BRIP4A130020 | #VALUE!
A1 | QH Costs | 30 | Engineering | 030 | A130030 | Specialist Engineering - Design for Procurement | 5 | Bradley Norwood |  | BR-P4-A1-30-030 | BRIP4A130030 | BRIP412030 | BRIP4A130030 | #VALUE!
A1 | QH Costs | 30 | Engineering | 040 | A130040 | Specialist Engineering - FEED | 5 | Bradley Norwood |  | BR-P4-A1-30-040 | BRIP4A130040 | BRIP412040 | BRIP4A130040 | #VALUE!
A1 | QH Costs | 30 | Engineering | 050 | A130050 | Specialist Engineering - Exploratory Works | 5 | Bradley Norwood |  | BR-P4-A1-30-050 | BRIP4A130050 | BRIP412050 | BRIP4A130050 | #VALUE!
A1 | QH Costs | 30 | Engineering | 060 | A130060 | Specialist Advisors - Technical Assurance | 5 | Bradley Norwood |  | BR-P4-A1-30-060 | BRIP4A130060 | BRIP412060 | BRIP4A130060 | #VALUE!
A1 | QH Costs | 30 | Engineering | 070 | A130070 | Connection Application Process/Services | 5 | Bradley Norwood |  | BR-P4-A1-30-070 | BRIP4A130070 | BRIP412070 | BRIP4A130070 | #VALUE!
A1 | QH Costs | 30 | Engineering | 080 | A130080 | Independent certifier | 5 | Bradley Norwood |  | BR-P4-A1-30-080 | BRIP4A130080 | BRIP412080 | BRIP4A130080 | #VALUE!
A1 | QH Costs | 40 | Environment and Approvals | 000 | A140000 | Environment and Approvals | 4 |  |  | BR-P4-A1-40-000 | BRIP4A140000 | BRIP413000 | BRIP4A140000 | #VALUE!
A1 | QH Costs | 40 | Environment and Approvals | 010 | A140010 | Technical Advisors - EIS Approvals and Studies | 5 | Andrew Nolan |  | BR-P4-A1-40-010 | BRIP4A140010 | BRIP413010 | BRIP4A140010 | #VALUE!
A1 | QH Costs | 40 | Environment and Approvals | 020 | A140020 | EIS - Engineering Input | 5 | Andrew Nolan |  | BR-P4-A1-40-020 | BRIP4A140020 | BRIP413020 | BRIP4A140020 | #VALUE!
A1 | QH Costs | 40 | Environment and Approvals | 030 | A140030 | EIS - Technical Studies | 5 | Andrew Nolan |  | BR-P4-A1-40-030 | BRIP4A140030 | BRIP413030 | BRIP4A140030 | #VALUE!
A1 | QH Costs | 40 | Environment and Approvals | 040 | A140040 | Exploratory Works Approvals | 5 | Andrew Nolan |  | BR-P4-A1-40-040 | BRIP4A140040 | BRIP413040 | BRIP4A140040 | #VALUE!
A1 | QH Costs | 40 | Environment and Approvals | 050 | A140050 | Main Works - Approvals | 5 | Andrew Nolan |  | BR-P4-A1-40-050 | BRIP4A140050 | BRIP413050 | BRIP4A140050 | #VALUE!
A1 | QH Costs | 40 | Environment and Approvals | 060 | A140060 | Offset Implementation | 5 | Andrew Nolan |  | BR-P4-A1-40-060 | BRIP4A140060 | BRIP413060 | BRIP4A140060 | #VALUE!
A1 | QH Costs | 40 | Environment and Approvals | 070 | A140070 | Sustainability | 5 | Andrew Nolan |  | BR-P4-A1-40-070 | BRIP4A140070 | BRIP413070 | BRIP4A140070 | #VALUE!
A1 | QH Costs | 40 | Environment and Approvals | 080 | A140080 | Office of the Coordinator-General (OCG Costs) | 5 | Andrew Nolan |  | BR-P4-A1-40-080 | BRIP4A140080 | BRIP413080 | BRIP4A140080 | #VALUE!
A1 | QH Costs | 40 | Environment and Approvals | 090 | A140090 | EIS - Delivery | 5 | Andrew Nolan |  | BR-P4-A1-40-090 | BRIP4A140090 | BRIP413090 | BRIP4A140090 | #VALUE!
A1 | QH Costs | 40 | Environment and Approvals | 100 | A140100 | GIS Support | 5 | Finton Moore |  | BR-P4-A1-40-100 | BRIP4A140100 | BRIP413100 | BRIP4A140100 | #VALUE!
A1 | QH Costs | 40 | Environment and Approvals | 110 | A140110 | Cultural Heritage - Investigations and Monitoring | 5 | Andrew Nolan |  | BR-P4-A1-40-110 | BRIP4A140110 | BRIP413110 | BRIP4A140110 | #VALUE!
A1 | QH Costs | 40 | Environment and Approvals | 120 | A140120 | Indigenous Land Use Agreement | 5 | Head of Indigeneous Partnerships Vacant |  | BR-P4-A1-40-120 | BRIP4A140120 | BRIP413120 | BRIP4A140120 | #VALUE!
A1 | QH Costs | 40 | Environment and Approvals | 130 | A140130 | Compliance Monitoring | 5 | Andrew Nolan |  | BR-P4-A1-40-130 | BRIP4A140130 | BRIP413130 | BRIP4A140130 | #VALUE!
A1 | QH Costs | 40 | Environment and Approvals | 140 | A140140 | Indigenous Partnerships | 5 | Head of Indigeneous Partnerships Vacant |  | BR-P4-A1-40-140 | BRIP4A140140 | BRIP413140 | BRIP4A140140 | #VALUE!
A1 | QH Costs | 50 | Community Development and Stakeholder | 000 | A150000 | Community Development and Stakeholder | 4 |  |  | BR-P4-A1-50-000 | BRIP4A150000 | BRIP414000 | BRIP4A150000 | #VALUE!
A1 | QH Costs | 50 | Community Development and Stakeholder | 010 | A150010 | Community and Stakeholder Consultants | 5 | Julie Spencer |  | BR-P4-A1-50-010 | BRIP4A150010 | BRIP414010 | BRIP4A150010 | #VALUE!
A1 | QH Costs | 50 | Community Development and Stakeholder | 020 | A150020 | Community Benefits Program | 5 | Julie Spencer |  | BR-P4-A1-50-020 | BRIP4A150020 | BRIP414020 | BRIP4A150020 | #VALUE!
A1 | QH Costs | 50 | Community Development and Stakeholder | 030 | A150030 | Sponsorships | 5 | Julie Spencer |  | BR-P4-A1-50-030 | BRIP4A150030 | BRIP414030 | BRIP4A150030 | #VALUE!
A1 | QH Costs | 50 | Community Development and Stakeholder | 040 | A150040 | Community Engagement Program | 5 | Julie Spencer |  | BR-P4-A1-50-040 | BRIP4A150040 | BRIP414040 | BRIP4A150040 | #VALUE!
A1 | QH Costs | 50 | Community Development and Stakeholder | 050 | A150050 | Regional Development | 5 | Tracey Lyons |  | BR-P4-A1-50-050 | BRIP4A150050 | BRIP414050 | BRIP4A150050 | #VALUE!
A1 | QH Costs | 50 | Community Development and Stakeholder | 060 | A150060 | Regional Development Accommodation Partners | 5 | Tracey Lyons |  | BR-P4-A1-50-060 | BRIP4A150060 | BRIP414060 | BRIP4A150060 | #VALUE!
A1 | QH Costs | 50 | Community Development and Stakeholder | 070 | A150070 | Regional Development Community Infrastructure | 5 | Tracey Lyons |  | BR-P4-A1-50-070 | BRIP4A150070 | BRIP414070 | BRIP4A150070 | #VALUE!
A1 | QH Costs | 50 | Community Development and Stakeholder | 080 | A150080 | Regional Development - Community Development Initiatives (GRC) | 5 | Tracey Lyons |  | BR-P4-A1-50-080 | BRIP4A150080 | BRIP414080 | BRIP4A150080 | #VALUE!
A1 | QH Costs | 50 | Community Development and Stakeholder | 090 | A150090 | Regional Development - Community Development Initiatives (SRC) | 5 | Tracey Lyons |  | BR-P4-A1-50-090 | BRIP4A150090 | BRIP414090 | BRIP4A150090 | #VALUE!
A1 | QH Costs |  | Heath and Safety |  | A1 | Heath and Safety | 4 |  | Reallocated to Indirect & Project Contractors | BR-P4-A1-- | BRIP4A1 |  | BRIP4A1 | #VALUE!
A1 | QH Costs | 60 | Land Acquisition | 000 | A160000 | Land Acquisition | 4 |  |  | BR-P4-A1-60-000 | BRIP4A160000 | BRIP416000 | BRIP4A160000 | #VALUE!
A1 | QH Costs | 60 | Land Acquisition | 010 | A160010 | Land Access & Conveyancing | 5 | Head of Land |  | BR-P4-A1-60-010 | BRIP4A160010 | BRIP416010 | BRIP4A160010 | #VALUE!
A1 | QH Costs | 60 | Land Acquisition | 020 | A160020 | Land Acquisition | 5 | Head of Land |  | BR-P4-A1-60-020 | BRIP4A160020 | BRIP416020 | BRIP4A160020 | #VALUE!
A1 | QH Costs | 60 | Land Acquisition | 030 | A160030 | Land Access - Specialist Advisors | 5 | Head of Land |  | BR-P4-A1-60-030 | BRIP4A160030 | BRIP416030 | BRIP4A160030 | #VALUE!
A1 | QH Costs | 70 | Indirect | 000 | A170000 | Indirect | 4 |  |  | BR-P4-A1-70-000 | BRIP4A170000 | BRIP417000 | BRIP4A170000 | #VALUE!
A1 | QH Costs | 70 | Indirect | 010 | A170010 | Project Expenses – General | 5 | Head of Land |  | BR-P4-A1-70-010 | BRIP4A170010 | BRIP417010 | BRIP4A170010 | #VALUE!
A1 | QH Costs | 70 | Indirect | 020 | A170020 | PPE | 5 | Kelly Palmer | Split from H&S L4 | BR-P4-A1-70-020 | BRIP4A170020 | BRIP415010 | BRIP4A170020 | #VALUE!
A1 | QH Costs | 70 | Indirect | 030 | A170030 | Emergency Response Plan | 5 | Kelly Palmer | Split from H&S L4 | BR-P4-A1-70-030 | BRIP4A170030 | BRIP415040 | BRIP4A170030 | #VALUE!
A1 | QH Costs | 70 | Indirect | 040 | A170040 | Travel, Accommodation & Disbursements | 5 | Leah Mckenzie |  | BR-P4-A1-70-040 | BRIP4A170040 | BRIP417020 | BRIP4A170040 | #VALUE!
A1 | QH Costs | 70 | Indirect | 050 | A170050 | IT Software, Licenses & Equipment | 5 | Leah Mckenzie |  | BR-P4-A1-70-050 | BRIP4A170050 | BRIP417030 | BRIP4A170050 | #VALUE!
A1 | QH Costs | 70 | Indirect | 060 | A170060 | Training & Development (Delivery) | 5 | Ashlen Naicker | Renamed (Delivery) | BR-P4-A1-70-060 | BRIP4A170060 | BRIP417040 | BRIP4A170060 | #VALUE!
A1 | QH Costs | 70 | Indirect | 070 | A170070 | Mandatory Safety Training | 5 | Head of People and Capability | Split from H&S L4 | BR-P4-A1-70-070 | BRIP4A170070 | BRIP415030 | BRIP4A170070 | #VALUE!
A1 | QH Costs | 70 | Indirect | 080 | A170080 | Site Vehicles and Transport | 5 | Leah Mckenzie |  | BR-P4-A1-70-080 | BRIP4A170080 | BRIP417050 | BRIP4A170080 | #VALUE!
A1 | QH Costs | 70 | Indirect | 090 | A170090 | Project Offices and Facilities | 5 | Leah Mckenzie |  | BR-P4-A1-70-090 | BRIP4A170090 | BRIP417060 | BRIP4A170090 | #VALUE!
A1 | QH Costs | 70 | Indirect | 100 | A170100 | Portable Long Service Leave Levy | 5 | Amy Treble |  | BR-P4-A1-70-100 | BRIP4A170100 | BRIP417070 | BRIP4A170100 | #VALUE!
A1 | QH Costs | 70 | Indirect | 110 | A170110 | Insurances | 5 | Amy Treble |  | BR-P4-A1-70-110 | BRIP4A170110 | BRIP417080 | BRIP4A170110 | #VALUE!
A1 | QH Costs | 70 | Indirect | 120 | A170120 | Bid cost reimbursement | 5 | Jason Long |  | BR-P4-A1-70-120 | BRIP4A170120 | BRIP417090 | BRIP4A170120 | #VALUE!
A1 | QH Costs | 70 | Indirect | 130 | A170130 | Site Equipment & Tooling | 5 | Leah Mckenzie |  | BR-P4-A1-70-130 | BRIP4A170130 | BRIP417100 | BRIP4A170130 | #VALUE!
A1 | QH Costs | 70 | Indirect | 140 | A170140 | Corporate Overheads | 5 | Amy Treble |  | BR-P4-A1-70-140 | BRIP4A170140 | BRIP417110 | BRIP4A170140 | #VALUE!
A1 | QH Costs | 70 | Indirect | 150 | A170150 | Legal Costs | 5 | Erin McCormick |  | BR-P4-A1-70-150 | BRIP4A170150 | BRIP417120 | BRIP4A170150 | #VALUE!
A1 | QH Costs | 70 | Indirect | 160 | A170160 | Site Communications | 5 | Ashlen Naicker |  | BR-P4-A1-70-160 | BRIP4A170160 | BRIP417130 | BRIP4A170160 | #VALUE!
A1 | QH Costs | 70 | Indirect | 170 | A170170 | Finance costs (FBT) | 5 | Amy Treble |  | BR-P4-A1-70-170 | BRIP4A170170 | BRIP417140 | BRIP4A170170 | #VALUE!
A1 | QH Costs | 70 | Indirect | 180 | A170180 | Other Staff Costs (memberships, subscriptions) | 5 | Amy Treble |  | BR-P4-A1-70-180 | BRIP4A170180 | BRIP417150 | BRIP4A170180 | #VALUE!
A1 | QH Costs | 80 | Ops Readiness & Commissioning | 000 | A180000 | Ops Readiness & Commissioning | 4 |  |  | BR-P4-A1-80-000 | BRIP4A180000 | BRIP418000 | BRIP4A180000 | #VALUE!
A1 | QH Costs | 80 | Ops Readiness & Commissioning | 010 | A180010 | Op Readiness | 5 | Leah Mckenzie |  | BR-P4-A1-80-010 | BRIP4A180010 | BRIP418010 | BRIP4A180010 | #VALUE!
A1 | QH Costs | 80 | Ops Readiness & Commissioning | 020 | A180020 | Commissioning | 5 | Leah Mckenzie |  | BR-P4-A1-80-020 | BRIP4A180020 | BRIP418020 | BRIP4A180020 | #VALUE!
A1 | QH Costs | 80 | Ops Readiness & Commissioning | 030 | A180030 | Full Load Compliance Testing | 5 | Leah Mckenzie |  | BR-P4-A1-80-030 | BRIP4A180030 | BRIP418030 | BRIP4A180030 | #VALUE!
A2 | Surface Infrastructure and Enabling | 00 | Surface Infrastructure and Enabling | 000 | A200000 | Surface Infrastructure and Enabling | 3 |  |  | BR-P4-A2-00-000 | BRIP4A200000 |  | BRIP4A200000 | #VALUE!
A2 | Surface Infrastructure and Enabling | 01 | Contractor Indirect & overheads | 000 | A201000 | Contractor Indirect & overheads | 4 |  |  | BR-P4-A2-01-000 | BRIP4A201000 | BRIP420100 | BRIP4A201000 | #VALUE!
A2 | Surface Infrastructure and Enabling | 01 | Surface Infrastructure and Enabling | 010 | A201010 | Temporary Camps - Indirects and Overheads | 5 | Aiden Goggins |  | BR-P4-A2-01-010 | BRIP4A201010 | BRIP420110 | BRIP4A201010 | #VALUE!
A2 | Surface Infrastructure and Enabling | 01 | Surface Infrastructure and Enabling | 020 | A201020 | Main Camps - Indirects and Overheads | 5 | Aiden Goggins |  | BR-P4-A2-01-020 | BRIP4A201020 | BRIP420120 | BRIP4A201020 | #VALUE!
A2 | Surface Infrastructure and Enabling | 01 | Surface Infrastructure and Enabling | 030 | A201030 | Exploratory Works - Contractor Indirect & overheads | 5 | Aiden Goggins |  | BR-P4-A2-01-030 | BRIP4A201030 | BRIP420130 | BRIP4A201030 | #VALUE!
A2 | Surface Infrastructure and Enabling | 01 | Surface Infrastructure and Enabling | 040 | A201040 | Enabling Works - Contractor Indirect & overheads | 5 | Aiden Goggins |  | BR-P4-A2-01-040 | BRIP4A201040 | BRIP420140 | BRIP4A201040 | #VALUE!
A2 | Surface Infrastructure and Enabling | 02 | Design | 000 | A202000 | Design | 4 |  |  | BR-P4-A2-02-000 | BRIP4A202000 | BRIP420200 | BRIP4A202000 | #VALUE!
A2 | Surface Infrastructure and Enabling | 02 | Surface Infrastructure and Enabling | 010 | A202010 | Design - Exploratory Works | 5 | Bradley Norwood |  | BR-P4-A2-02-010 | BRIP4A202010 | BRIP420210 | BRIP4A202010 | #VALUE!
A2 | Surface Infrastructure and Enabling | 02 | Surface Infrastructure and Enabling | 020 | A202020 | Design - Enabling Works | 5 | Bradley Norwood |  | BR-P4-A2-02-020 | BRIP4A202020 | BRIP420220 | BRIP4A202020 | #VALUE!
A2 | Surface Infrastructure and Enabling | 02 | Surface Infrastructure and Enabling | 030 | A202030 | Temp Camps Design | 5 | Bradley Norwood |  | BR-P4-A2-02-030 | BRIP4A202030 | BRIP420230 | BRIP4A202030 | #VALUE!
A2 | Surface Infrastructure and Enabling | 03 | Camps | 000 | A203000 | Camps | 4 |  |  | BR-P4-A2-03-000 | BRIP4A203000 | BRIP420300 | BRIP4A203000 | #VALUE!
A2 | Surface Infrastructure and Enabling | 03 | Surface Infrastructure and Enabling | 010 | A203010 | Temp Camps | 5 | Aiden Goggins |  | BR-P4-A2-03-010 | BRIP4A203010 | BRIP420310 | BRIP4A203010 | #VALUE!
A2 | Surface Infrastructure and Enabling | 03 | Surface Infrastructure and Enabling | 020 | A203020 | Upper Res Camps Hardstand | 5 | Aiden Goggins |  | BR-P4-A2-03-020 | BRIP4A203020 | BRIP420320 | BRIP4A203020 | #VALUE!
A2 | Surface Infrastructure and Enabling | 03 | Surface Infrastructure and Enabling | 030 | A203030 | Lower Res Camps Hardstand | 5 | Aiden Goggins |  | BR-P4-A2-03-030 | BRIP4A203030 | BRIP420330 | BRIP4A203030 | #VALUE!
A2 | Surface Infrastructure and Enabling | 03 | Surface Infrastructure and Enabling | 040 | A203040 | Main Camps Hardstand | 5 | Aiden Goggins |  | BR-P4-A2-03-040 | BRIP4A203040 | BRIP420340 | BRIP4A203040 | #VALUE!
A2 | Surface Infrastructure and Enabling | 03 | Surface Infrastructure and Enabling | 050 | A203050 | Upper Res Camps Install and Operate | 5 | Clifford Hookham |  | BR-P4-A2-03-050 | BRIP4A203050 | BRIP420350 | BRIP4A203050 | #VALUE!
A2 | Surface Infrastructure and Enabling | 03 | Surface Infrastructure and Enabling | 060 | A203060 | Lower Res Camps Install and Operate | 5 | Aiden Goggins |  | BR-P4-A2-03-060 | BRIP4A203060 | BRIP420360 | BRIP4A203060 | #VALUE!
A2 | Surface Infrastructure and Enabling | 03 | Surface Infrastructure and Enabling | 070 | A203070 | Main Camps Install and Operate | 5 | Aiden Goggins |  | BR-P4-A2-03-070 | BRIP4A203070 | BRIP420370 | BRIP4A203070 | #VALUE!
A2 | Surface Infrastructure and Enabling | 03 | Surface Infrastructure and Enabling | 080 | A203080 | Camp Set up | 5 | Aiden Goggins |  | BR-P4-A2-03-080 | BRIP4A203080 | BRIP420380 | BRIP4A203080 | #VALUE!
A2 | Surface Infrastructure and Enabling | 04 | Geotechnical | 000 | A204000 | Geotechnical | 4 |  |  | BR-P4-A2-04-000 | BRIP4A204000 | BRIP420400 | BRIP4A204000 | #VALUE!
A2 | Surface Infrastructure and Enabling | 04 | Geotechnical | 010 | A204010 | Contractor Indirect & overheads | 5 | Clifford Hookham |  | BR-P4-A2-04-010 | BRIP4A204010 | BRIP420410 | BRIP4A204010 | #VALUE!
A2 | Surface Infrastructure and Enabling | 04 | Geotechnical | 020 | A204020 | Geotechnical Studies | 5 | Head of Assets & Engineering |  | BR-P4-A2-04-020 | BRIP4A204020 | BRIP420420 | BRIP4A204020 | #VALUE!
A2 | Surface Infrastructure and Enabling | 04 | Geotechnical | 030 | A204030 | Geotechnical Drilling | 5 | Clifford Hookham |  | BR-P4-A2-04-030 | BRIP4A204030 | BRIP420430 | BRIP4A204030 | #VALUE!
A2 | Surface Infrastructure and Enabling | 04 | Geotechnical | 040 | A204040 | Geotechnical Service Management | 5 | Clifford Hookham |  | BR-P4-A2-04-040 | BRIP4A204040 | BRIP420440 | BRIP4A204040 | #VALUE!
A2 | Surface Infrastructure and Enabling | 05 | Temporary Water Infrastructure | 000 | A205000 | Temporary Water Infrastructure | 4 |  |  | BR-P4-A2-05-000 | BRIP4A205000 | BRIP420500 | BRIP4A205000 | #VALUE!
A2 | Surface Infrastructure and Enabling | 05 | Temporary Water Infrastructure | 010 | A205010 | Preliminaries Temporary Water Infrastructure | 5 | Aiden Goggins |  | BR-P4-A2-05-010 | BRIP4A205010 | BRIP420510 | BRIP4A205010 | #VALUE!
A2 | Surface Infrastructure and Enabling | 05 | Temporary Water Infrastructure | 020 | A205020 | Temporary Water Infrastructure | 5 | Aiden Goggins |  | BR-P4-A2-05-020 | BRIP4A205020 | BRIP420520 | BRIP4A205020 | #VALUE!
A2 | Surface Infrastructure and Enabling | 05 | Temporary Water Infrastructure | 030 | A205030 | Temporary Water Supply | 5 | Aiden Goggins |  | BR-P4-A2-05-030 | BRIP4A205030 | BRIP420530 | BRIP4A205030 | #VALUE!
A2 | Surface Infrastructure and Enabling | 06 | Communication Infrastructure Upgrade | 000 | A206000 | Communication Infrastructure Upgrade | 4 |  |  | BR-P4-A2-06-000 | BRIP4A206000 | BRIP420600 | BRIP4A206000 | #VALUE!
A2 | Surface Infrastructure and Enabling | 06 | Communication Infrastructure Upgrade | 010 | A206010 | Preliminaries Communication Infrastructure Upgrade | 5 | Aiden Goggins |  | BR-P4-A2-06-010 | BRIP4A206010 | BRIP420610 | BRIP4A206010 | #VALUE!
A2 | Surface Infrastructure and Enabling | 06 | Communication Infrastructure Upgrade | 020 | A206020 | Communication Infrastructure Upgrade | 5 | Aiden Goggins |  | BR-P4-A2-06-020 | BRIP4A206020 | BRIP420620 | BRIP4A206020 | #VALUE!
A2 | Surface Infrastructure and Enabling | 07 | Power Supply Upgrade | 000 | A207000 | Power Supply Upgrade | 4 |  |  | BR-P4-A2-07-000 | BRIP4A207000 | BRIP420700 | BRIP4A207000 | #VALUE!
A2 | Surface Infrastructure and Enabling | 07 | Power Supply Upgrade | 010 | A207010 | Preliminaries Power Supply Upgrade | 5 | Aiden Goggins |  | BR-P4-A2-07-010 | BRIP4A207010 | BRIP420710 | BRIP4A207010 | #VALUE!
A2 | Surface Infrastructure and Enabling | 07 | Power Supply Upgrade | 020 | A207020 | Power Supply Upgrade | 5 | Aiden Goggins |  | BR-P4-A2-07-020 | BRIP4A207020 | BRIP420720 | BRIP4A207020 | #VALUE!
A2 | Surface Infrastructure and Enabling | 10 | Yabba Creek Road Option 1 | 000 | A210000 | Yabba Creek Road Option 1 | 4 |  |  | BR-P4-A2-10-000 | BRIP4A210000 | BRIP421000 | BRIP4A210000 | #VALUE!
A2 | Surface Infrastructure and Enabling | 10 | Yabba Creek Road Option 1 | 010 | A210010 | Preliminaries Yabba Ck Rd Option 1 | 5 | Aiden Goggins |  | BR-P4-A2-10-010 | BRIP4A210010 | BRIP421010 | BRIP4A210010 | #VALUE!
A2 | Surface Infrastructure and Enabling | 10 | Yabba Creek Road Option 1 | 020 | A210020 | Bridge 1 (on Yabba Ck Rd - Ana Branche No 1) | 5 | Aiden Goggins |  | BR-P4-A2-10-020 | BRIP4A210020 | BRIP421020 | BRIP4A210020 | #VALUE!
A2 | Surface Infrastructure and Enabling | 10 | Yabba Creek Road Option 1 | 030 | A210030 | Bridge 2 (on Yabba Ck Rd - Ana Branche No 2) | 5 | Aiden Goggins |  | BR-P4-A2-10-030 | BRIP4A210030 | BRIP421030 | BRIP4A210030 | #VALUE!
A2 | Surface Infrastructure and Enabling | 10 | Yabba Creek Road Option 1 | 040 | A210040 | Bridge 3 (on Yabba Ck Rd - No 1 Crossing - Neumans Crossing) | 5 | Aiden Goggins |  | BR-P4-A2-10-040 | BRIP4A210040 | BRIP421040 | BRIP4A210040 | #VALUE!
A2 | Surface Infrastructure and Enabling | 10 | Yabba Creek Road Option 1 | 050 | A210050 | Bridge 4 (on Yabba Ck Rd - No 2 Crossing - Elbow Crossing) | 5 | Aiden Goggins |  | BR-P4-A2-10-050 | BRIP4A210050 | BRIP421050 | BRIP4A210050 | #VALUE!
A2 | Surface Infrastructure and Enabling | 10 | Yabba Creek Road Option 1 | 060 | A210060 | Bridge 5 (on Yabba Ck Rd - No 3 Crossing - Andrews Crossing) | 5 | Aiden Goggins |  | BR-P4-A2-10-060 | BRIP4A210060 | BRIP421060 | BRIP4A210060 | #VALUE!
A2 | Surface Infrastructure and Enabling | 10 | Yabba Creek Road Option 1 | 070 | A210070 | Bridge 6 (on Yabba Ck Rd - No ? Crossing - ????) | 5 | Aiden Goggins |  | BR-P4-A2-10-070 | BRIP4A210070 | BRIP421070 | BRIP4A210070 | #VALUE!
A2 | Surface Infrastructure and Enabling | 10 | Yabba Creek Road Option 1 | 080 | A210080 | Bridge 7 (on Yabba Ck Rd - No 4 Crossing - Boardmans Crossing) | 5 | Aiden Goggins |  | BR-P4-A2-10-080 | BRIP4A210080 | BRIP421080 | BRIP4A210080 | #VALUE!
A2 | Surface Infrastructure and Enabling | 10 | Yabba Creek Road Option 1 | 090 | A210090 | Bridge 8 (on Yabba Ck Rd - No 5 Crossing - Friends Crossing) | 5 | Aiden Goggins |  | BR-P4-A2-10-090 | BRIP4A210090 | BRIP421090 | BRIP4A210090 | #VALUE!
A2 | Surface Infrastructure and Enabling | 10 | Yabba Creek Road Option 1 | 100 | A210100 | Bridge 9 (on Yabba Ck Rd - No 6 Crossing - Deep Crossing) | 5 | Aiden Goggins |  | BR-P4-A2-10-100 | BRIP4A210100 | BRIP421100 | BRIP4A210100 | #VALUE!
A2 | Surface Infrastructure and Enabling | 10 | Yabba Creek Road Option 1 | 110 | A210110 | Bridge 10 (on Yabba Ck Rd - No 7 - Crossing - unknown name) | 5 | Aiden Goggins |  | BR-P4-A2-10-110 | BRIP4A210110 | BRIP421110 | BRIP4A210110 | #VALUE!
A2 | Surface Infrastructure and Enabling | 10 | Yabba Creek Road Option 1 | 120 | A210120 | Upgrade Bella Creek Road intersection | 5 | Aiden Goggins |  | BR-P4-A2-10-120 | BRIP4A210120 | BRIP421120 | BRIP4A210120 | #VALUE!
A2 | Surface Infrastructure and Enabling | 12 | Old Forestry Drive Option 2 | 000 | A212000 | Old Forestry Drive Option 2 | 4 |  |  | BR-P4-A2-12-000 | BRIP4A212000 | BRIP421200 | BRIP4A212000 | #VALUE!
A2 | Surface Infrastructure and Enabling | 12 | Old Forestry Drive Option 2 | 010 | A212010 | Preliminaries Old Forestry Drive Option 2 | 5 | Aiden Goggins |  | BR-P4-A2-12-010 | BRIP4A212010 | BRIP421210 | BRIP4A212010 | #VALUE!
A2 | Surface Infrastructure and Enabling | 12 | Old Forestry Drive Option 2 | 020 | A212020 | Old Forestry Drive Option 2 Construction | 5 | Aiden Goggins |  | BR-P4-A2-12-020 | BRIP4A212020 | BRIP421220 | BRIP4A212020 | #VALUE!
A2 | Surface Infrastructure and Enabling | 13 | Yielo Rd | 000 | A213000 | Yielo Rd | 4 |  |  | BR-P4-A2-13-000 | BRIP4A213000 | BRIP421300 | BRIP4A213000 | #VALUE!
A2 | Surface Infrastructure and Enabling | 13 | Yielo Rd | 010 | A213010 | Preliminaries Upgrade of Yielo Rd | 5 | Aiden Goggins |  | BR-P4-A2-13-010 | BRIP4A213010 | BRIP421310 | BRIP4A213010 | #VALUE!
A2 | Surface Infrastructure and Enabling | 13 | Yielo Rd | 020 | A213020 | Upgrade of Yielo Rd Construction | 5 | Aiden Goggins |  | BR-P4-A2-13-020 | BRIP4A213020 | BRIP421320 | BRIP4A213020 | #VALUE!
A2 | Surface Infrastructure and Enabling | 14 | Walkers Top Access Track | 000 | A214000 | Walkers Top Access Track | 4 |  |  | BR-P4-A2-14-000 | BRIP4A214000 | BRIP421400 | BRIP4A214000 | #VALUE!
A2 | Surface Infrastructure and Enabling | 14 | Walkers Top Access Track | 010 | A214010 | Preliminaries Walkers Top Access Track | 5 | Aiden Goggins |  | BR-P4-A2-14-010 | BRIP4A214010 | BRIP421410 | BRIP4A214010 | #VALUE!
A2 | Surface Infrastructure and Enabling | 14 | Walkers Top Access Track | 020 | A214020 | Walkers Top Access Track Construction | 5 | Aiden Goggins |  | BR-P4-A2-14-020 | BRIP4A214020 | BRIP421420 | BRIP4A214020 | #VALUE!
A2 | Surface Infrastructure and Enabling | 15 | Access Roads - The Borgan | 000 | A215000 | Access Roads - The Borgan | 4 |  |  | BR-P4-A2-15-000 | BRIP4A215000 | BRIP421500 | BRIP4A215000 | #VALUE!
A2 | Surface Infrastructure and Enabling | 15 | Access Roads - The Borgan | 010 | A215010 | Preliminaries Access Roads - The Borgan | 5 | Aiden Goggins |  | BR-P4-A2-15-010 | BRIP4A215010 | BRIP421510 | BRIP4A215010 | #VALUE!
A2 | Surface Infrastructure and Enabling | 15 | Access Roads - The Borgan | 020 | A215020 | Access Roads - The Borgan | 5 | Aiden Goggins |  | BR-P4-A2-15-020 | BRIP4A215020 | BRIP421520 | BRIP4A215020 | #VALUE!
A2 | Surface Infrastructure and Enabling | 16 | Lower Res Access Road | 000 | A216000 | Lower Res Access Road | 4 |  |  | BR-P4-A2-16-000 | BRIP4A216000 | BRIP421600 | BRIP4A216000 | #VALUE!
A2 | Surface Infrastructure and Enabling | 16 | Lower Res Access Road | 010 | A216010 | Lower Res Access Road | 5 | Aiden Goggins |  | BR-P4-A2-16-010 | BRIP4A216010 | BRIP421610 | BRIP4A216010 | #VALUE!
A2 | Surface Infrastructure and Enabling | 17 | Lower Res Haul Road - Construct and Maintain | 000 | A217000 | Lower Res Haul Road - Construct and Maintain | 4 |  |  | BR-P4-A2-17-000 | BRIP4A217000 | BRIP421700 | BRIP4A217000 | #VALUE!
A2 | Surface Infrastructure and Enabling | 17 | Lower Res Haul Road - Construct and Maintain | 010 | A217010 | Lower Res Haul Road - Construct and Maintain | 5 | Steve Pickering |  | BR-P4-A2-17-010 | BRIP4A217010 | BRIP421710 | BRIP4A217010 | #VALUE!
A2 | Surface Infrastructure and Enabling | 18 | Bella Creek Road | 000 | A218000 | Bella Creek Road | 4 |  |  | BR-P4-A2-18-000 | BRIP4A218000 | BRIP421800 | BRIP4A218000 | #VALUE!
A2 | Surface Infrastructure and Enabling | 18 | Bella Creek Road | 010 | A218010 | Bella Creek Road | 5 | Aiden Goggins |  | BR-P4-A2-18-010 | BRIP4A218010 | BRIP421810 | BRIP4A218010 | #VALUE!
A2 | Surface Infrastructure and Enabling | 19 | Yabba Creek Bridge | 000 | A219000 | Yabba Creek Bridge | 4 |  |  | BR-P4-A2-19-000 | BRIP4A219000 | BRIP421900 | BRIP4A219000 | #VALUE!
A2 | Surface Infrastructure and Enabling | 19 | Yabba Creek Bridge | 010 | A219010 | Yabba Creek Bridge | 5 | Aiden Goggins |  | BR-P4-A2-19-010 | BRIP4A219010 | BRIP421910 | BRIP4A219010 | #VALUE!
A2 | Surface Infrastructure and Enabling | 20 | Kingaham Creek Bridge | 000 | A220000 | Kingaham Creek Bridge | 4 |  |  | BR-P4-A2-20-000 | BRIP4A220000 | BRIP422000 | BRIP4A220000 | #VALUE!
A2 | Surface Infrastructure and Enabling | 20 | Kingaham Creek Bridge | 010 | A220010 | Kingaham Creek Bridge | 5 | Aiden Goggins |  | BR-P4-A2-20-010 | BRIP4A220010 | BRIP422010 | BRIP4A220010 | #VALUE!
A2 | Surface Infrastructure and Enabling | 21 | Road to Lower Inlet / Outlet Structure | 000 | A221000 | Road to Lower Inlet / Outlet Structure | 4 |  |  | BR-P4-A2-21-000 | BRIP4A221000 | BRIP422100 | BRIP4A221000 | #VALUE!
A2 | Surface Infrastructure and Enabling | 21 | Road to Lower Inlet / Outlet Structure | 010 | A221010 | Road to Lower Inlet / Outlet Structure | 5 | Aiden Goggins |  | BR-P4-A2-21-010 | BRIP4A221010 | BRIP422110 | BRIP4A221010 | #VALUE!
A2 | Surface Infrastructure and Enabling | 22 | Road to Upper Res/Saddle Dam | 000 | A222000 | Road to Upper Res/Saddle Dam | 4 |  |  | BR-P4-A2-22-000 | BRIP4A222000 | BRIP422200 | BRIP4A222000 | #VALUE!
A2 | Surface Infrastructure and Enabling | 22 | Road to Upper Res/Saddle Dam | 010 | A222010 | Road to Upper Res/Saddle Dam | 5 | Aiden Goggins |  | BR-P4-A2-22-010 | BRIP4A222010 | BRIP422210 | BRIP4A222010 | #VALUE!
A2 | Surface Infrastructure and Enabling | 23 | Ring Road at Upper Res incl. Access to upper intake and Bellmouth | 000 | A223000 | Ring Road at Upper Res incl. Access to upper intake and Bellmouth | 4 |  |  | BR-P4-A2-23-000 | BRIP4A223000 | BRIP422200 | BRIP4A223000 | #VALUE!
A2 | Surface Infrastructure and Enabling | 23 | Ring Road at Upper Res incl. Access to upper intake and Bellmouth | 010 | A223010 | Ring Road at Upper Res incl. Access to upper intake and Bellmouth | 5 | Aiden Goggins |  | BR-P4-A2-23-010 | BRIP4A223010 | BRIP422210 | BRIP4A223010 | #VALUE!
A2 | Surface Infrastructure and Enabling | 24 | MAT / ECVT Portal Pad Excavation | 000 | A224000 | MAT / ECVT Portal Pad Excavation | 4 |  |  | BR-P4-A2-24-000 | BRIP4A224000 | BRIP422300 | BRIP4A224000 | #VALUE!
A2 | Surface Infrastructure and Enabling | 24 | MAT / ECVT Portal Pad Excavation | 010 | A224010 | MAT / ECVT Portal Pad Excavation | 5 | Aiden Goggins |  | BR-P4-A2-24-010 | BRIP4A224010 | BRIP423010 | BRIP4A224010 | #VALUE!
A3 | Underground Waterways | 00 | Underground Waterways | 000 | A300000 | Underground Waterways | 3 |  |  | BR-P4-A3-00-000 | BRIP4A300000 | BRIP430100 | BRIP4A300000 | #VALUE!
A3 | Underground Waterways | 01 | Contractor Indirect & overheads stage 1 | 000 | A301000 | Contractor Indirect & overheads stage 1 | 4 |  |  | BR-P4-A3-01-000 | BRIP4A301000 | BRIP430100 | BRIP4A301000 | #VALUE!
A3 | Underground Waterways | 01 | Contractor Indirect & overheads stage 1 | 110 | A301110 | Contractor Indirects & overheads | 5 | Shannon Green |  | BR-P4-A3-01-110 | BRIP4A301110 | BRIP430110 | BRIP4A301110 | #VALUE!
A3 | Underground Waterways | 02 | Design | 000 | A302000 | Design | 4 |  |  | BR-P4-A3-02-000 | BRIP4A302000 | BRIP430200 | BRIP4A302000 | #VALUE!
A3 | Underground Waterways | 02 | Design | 210 | A302210 | Design | 5 | Bradley Norwood |  | BR-P4-A3-02-210 | BRIP4A302210 | BRIP430210 | BRIP4A302210 | #VALUE!
A3 | Underground Waterways | 10 | North Alignment Waterway | 000 | A310000 | North Alignment Waterway | 4 |  |  | BR-P4-A3-10-000 | BRIP4A310000 | BRIP431000 | BRIP4A310000 | #VALUE!
A3 | Underground Waterways | 10 | North Alignment Waterway | 010 | A310010 | Upper Inlet/Outlet Structure Bellmouth - North | 5 | Shannon Green |  | BR-P4-A3-10-010 | BRIP4A310010 | BRIP431010 | BRIP4A310010 | #VALUE!
A3 | Underground Waterways | 10 | North Alignment Waterway | 020 | A310020 | Upper Inlet/Outlet Structure Gate Shaft - North | 5 | Shannon Green |  | BR-P4-A3-10-020 | BRIP4A310020 | BRIP431020 | BRIP4A310020 | #VALUE!
A3 | Underground Waterways | 10 | North Alignment Waterway | 030 | A310030 | Lower Inlet/Outlet Structure Bellmouth - North | 5 | Shannon Green |  | BR-P4-A3-10-030 | BRIP4A310030 | BRIP431030 | BRIP4A310030 | #VALUE!
A3 | Underground Waterways | 10 | North Alignment Waterway | 040 | A310040 | Lower Inlet/Outlet Structure Gate Shaft Middle to Top - North | 5 | Shannon Green |  | BR-P4-A3-10-040 | BRIP4A310040 | BRIP431040 | BRIP4A310040 | #VALUE!
A3 | Underground Waterways | 10 | North Alignment Waterway | 050 | A310050 | Lower Inlet/Outlet Structure Gate Shaft Lower Part/Square Section - North | 5 | Shannon Green |  | BR-P4-A3-10-050 | BRIP4A310050 | BRIP431050 | BRIP4A310050 | #VALUE!
A3 | Underground Waterways | 10 | North Alignment Waterway | 060 | A310060 | Low Pressure Tunnel - North | 5 | Shannon Green |  | BR-P4-A3-10-060 | BRIP4A310060 | BRIP431060 | BRIP4A310060 | #VALUE!
A3 | Underground Waterways | 10 | North Alignment Waterway | 070 | A310070 | Erection Chamber - Upper - North | 5 | Shannon Green |  | BR-P4-A3-10-070 | BRIP4A310070 | BRIP431070 | BRIP4A310070 | #VALUE!
A3 | Underground Waterways | 10 | North Alignment Waterway | 080 | A310080 | Vertical Pressure Shaft - North | 5 | Shannon Green |  | BR-P4-A3-10-080 | BRIP4A310080 | BRIP431080 | BRIP4A310080 | #VALUE!
A3 | Underground Waterways | 10 | North Alignment Waterway | 090 | A310090 | Erection Chamber - Lower - North | 5 | Shannon Green |  | BR-P4-A3-10-090 | BRIP4A310090 | BRIP431090 | BRIP4A310090 | #VALUE!
A3 | Underground Waterways | 10 | North Alignment Waterway | 100 | A310100 | High Pressure Tunnel - North | 5 | Shannon Green |  | BR-P4-A3-10-100 | BRIP4A310100 | BRIP431100 | BRIP4A310100 | #VALUE!
A3 | Underground Waterways | 10 | North Alignment Waterway | 110 | A310110 | Penstock Steel Lined - North | 5 | Shannon Green |  | BR-P4-A3-10-110 | BRIP4A310110 | BRIP431110 | BRIP4A310110 | #VALUE!
A3 | Underground Waterways | 10 | North Alignment Waterway | 120 | A310120 | Tailrace Collector Tunnel - North | 5 | Shannon Green |  | BR-P4-A3-10-120 | BRIP4A310120 | BRIP431120 | BRIP4A310120 | #VALUE!
A3 | Underground Waterways | 10 | North Alignment Waterway | 130 | A310130 | Tailrace Tunnel - North | 5 | Shannon Green |  | BR-P4-A3-10-130 | BRIP4A310130 | BRIP431130 | BRIP4A310130 | #VALUE!
A3 | Underground Waterways | 10 | North Alignment Waterway | 140 | A310140 | Surge Tank - North | 5 | Shannon Green |  | BR-P4-A3-10-140 | BRIP4A310140 | BRIP431140 | BRIP4A310140 | #VALUE!
A3 | Underground Waterways | 20 | South Alignment Waterway | 000 | A320000 | South Alignment Waterway | 4 |  |  | BR-P4-A3-20-000 | BRIP4A320000 | BRIP432000 | BRIP4A320000 | #VALUE!
A3 | Underground Waterways | 20 | South Alignment Waterway | 010 | A320010 | Upper Inlet/Outlet Structure Bellmouth - South | 5 | Shannon Green |  | BR-P4-A3-20-010 | BRIP4A320010 | BRIP432010 | BRIP4A320010 | #VALUE!
A3 | Underground Waterways | 20 | South Alignment Waterway | 020 | A320020 | Upper Inlet/Outlet Structure Gate Shaft - South | 5 | Shannon Green |  | BR-P4-A3-20-020 | BRIP4A320020 | BRIP432020 | BRIP4A320020 | #VALUE!
A3 | Underground Waterways | 20 | South Alignment Waterway | 030 | A320030 | Lower Inlet/Outlet Structure Bellmouth - South | 5 | Shannon Green |  | BR-P4-A3-20-030 | BRIP4A320030 | BRIP432030 | BRIP4A320030 | #VALUE!
A3 | Underground Waterways | 20 | South Alignment Waterway | 040 | A320040 | Lower Inlet/Outlet Structure Gate Shaft Middle to Top - South | 5 | Shannon Green |  | BR-P4-A3-20-040 | BRIP4A320040 | BRIP432040 | BRIP4A320040 | #VALUE!
A3 | Underground Waterways | 20 | South Alignment Waterway | 050 | A320050 | Lower Inlet/Outlet Structure Gate Shaft Lower Part/Square Section - South | 5 | Shannon Green |  | BR-P4-A3-20-050 | BRIP4A320050 | BRIP432050 | BRIP4A320050 | #VALUE!
A3 | Underground Waterways | 20 | South Alignment Waterway | 060 | A320060 | Low Pressure Tunnel - South | 5 | Shannon Green |  | BR-P4-A3-20-060 | BRIP4A320060 | BRIP432060 | BRIP4A320060 | #VALUE!
A3 | Underground Waterways | 20 | South Alignment Waterway | 070 | A320070 | Erection Chamber - Upper - South | 5 | Shannon Green |  | BR-P4-A3-20-070 | BRIP4A320070 | BRIP432070 | BRIP4A320070 | #VALUE!
A3 | Underground Waterways | 20 | South Alignment Waterway | 080 | A320080 | Vertical Pressure Shaft - South | 5 | Shannon Green |  | BR-P4-A3-20-080 | BRIP4A320080 | BRIP432080 | BRIP4A320080 | #VALUE!
A3 | Underground Waterways | 20 | South Alignment Waterway | 090 | A320090 | Erection Chamber - Lower - South | 5 | Shannon Green |  | BR-P4-A3-20-090 | BRIP4A320090 | BRIP432090 | BRIP4A320090 | #VALUE!
A3 | Underground Waterways | 20 | South Alignment Waterway | 100 | A320100 | High Pressure Tunnel - South | 5 | Shannon Green |  | BR-P4-A3-20-100 | BRIP4A320100 | BRIP432100 | BRIP4A320100 | #VALUE!
A3 | Underground Waterways | 20 | South Alignment Waterway | 110 | A320110 | Penstock Steel Lined - South | 5 | Shannon Green |  | BR-P4-A3-20-110 | BRIP4A320110 | BRIP432110 | BRIP4A320110 | #VALUE!
A3 | Underground Waterways | 20 | South Alignment Waterway | 120 | A320120 | Tailrace Collector Tunnel - South | 5 | Shannon Green |  | BR-P4-A3-20-120 | BRIP4A320120 | BRIP432120 | BRIP4A320120 | #VALUE!
A3 | Underground Waterways | 20 | South Alignment Waterway | 130 | A320130 | Tailrace Tunnel - South | 5 | Shannon Green |  | BR-P4-A3-20-130 | BRIP4A320130 | BRIP432130 | BRIP4A320130 | #VALUE!
A3 | Underground Waterways | 20 | South Alignment Waterway | 140 | A320140 | Surge Tank - South | 5 | Shannon Green |  | BR-P4-A3-20-140 | BRIP4A320140 | BRIP432140 | BRIP4A320140 | #VALUE!
A3 | Underground Waterways | 30 | Platform and Control Buildings | 000 | A330000 | Platform and Control Buildings | 4 |  |  | BR-P4-A3-30-000 | BRIP4A330000 | BRIP433000 | BRIP4A330000 | #VALUE!
A3 | Underground Waterways | 30 | Platform and Control Buildings | 010 | A330010 | Upper Inlet/Outlet Platform and Control Building | 5 | Shannon Green |  | BR-P4-A3-30-010 | BRIP4A330010 | BRIP433010 | BRIP4A330010 | #VALUE!
A3 | Underground Waterways | 30 | Platform and Control Buildings | 020 | A330020 | Lower Inlet/Outlet Platform and Control Building | 5 | Shannon Green |  | BR-P4-A3-30-020 | BRIP4A330020 | BRIP433020 | BRIP4A330020 | #VALUE!
A3 | Underground Waterways | 40 | Lower Inlet Structure Approach | 000 | A340000 | Lower Inlet Structure Approach | 4 |  |  | BR-P4-A3-40-000 | BRIP4A340000 | BRIP434000 | BRIP4A340000 | #VALUE!
A3 | Underground Waterways | 40 | Lower Inlet Structure Approach | 010 | A340010 | Lower Inlet/Outlet Structure - Approach | 5 |  |  | BR-P4-A3-40-010 | BRIP4A340010 | BRIP434010 | BRIP4A340010 | #VALUE!
A3 | Underground Waterways | 50 | Surge Tanks Permanent access tunnel | 000 | A350000 | Surge Tanks Permanent access tunnel | 4 |  |  | BR-P4-A3-50-000 | BRIP4A350000 | BRIP435000 | BRIP4A350000 | #VALUE!
A3 | Underground Waterways | 50 | Surge Tanks Permanent access tunnel | 010 | A350010 | Surge Tanks Permanent access tunnel | 5 | Shannon Green |  | BR-P4-A3-50-010 | BRIP4A350010 | BRIP435010 | BRIP4A350010 | #VALUE!
A3 | Underground Waterways | 60 | Assembly Chambers | 000 | A360000 | Assembly Chambers | 4 |  |  | BR-P4-A3-60-000 | BRIP4A360000 | BRIP436000 | BRIP4A360000 | #VALUE!
A3 | Underground Waterways | 60 | Assembly Chambers | 010 | A360010 | Upstream Assembly Chambers, Connection Tunnels and Adit | 5 | Shannon Green | Split Upstream/Downstream | BR-P4-A3-60-010 | BRIP4A360010 | BRIP436010 | BRIP4A360010 | #VALUE!
A3 | Underground Waterways | 60 | Assembly Chambers | 020 | A360020 | Downstream Assembly Chambers, Connection Tunnels and Adit | 5 | Shannon Green | New | BR-P4-A3-60-020 | BRIP4A360020 | BRIP436010 | BRIP4A360020 | #VALUE!
A3 | Underground Waterways | 70 | Site Rehabilitation | 000 | A370000 | Site Rehabilitation | 4 |  |  | BR-P4-A3-70-000 | BRIP4A370000 | BRIP437000 | BRIP4A370000 | #VALUE!
A3 | Underground Waterways | 70 | Site Rehabilitation | 010 | A370010 | Site Rehabilitation | 5 | Shannon Green |  | BR-P4-A3-70-010 | BRIP4A370010 | BRIP437010 | BRIP4A370010 | #VALUE!
A4 | Underground Access & Caverns | 00 | Underground Access & Caverns | 000 | A400000 | Underground Access & Caverns | 3 |  | More than 10 level 4 WBS, so an extra integer has been created | BR-P4-A4-00-000 | BRIP4A400000 |  | BRIP4A400000 | #VALUE!
A4 | Underground Access & Caverns | 01 | Contractor Indirect & overheads | 000 | A401000 | Contractor Indirect & overheads | 4 |  |  | BR-P4-A4-01-000 | BRIP4A401000 | BRIP440100 | BRIP4A401000 | #VALUE!
A4 | Underground Access & Caverns | 01 | Contractor Indirect & overheads | 010 | A401010 | Contractor Indirects & overheads | 5 | Shannon Green |  | BR-P4-A4-01-010 | BRIP4A401010 | BRIP440110 | BRIP4A401010 | #VALUE!
A4 | Underground Access & Caverns | 02 | Design | 000 | A402000 | Design | 4 |  |  | BR-P4-A4-02-000 | BRIP4A402000 | BRIP440200 | BRIP4A402000 | #VALUE!
A4 | Underground Access & Caverns | 02 | Design | 010 | A402010 | Detail Design - Main Facility | 5 | Bradley Norwood | Split for Main Facility/OEM | BR-P4-A4-02-010 | BRIP4A402010 | BRIP440210 | BRIP4A402010 | #VALUE!
A4 | Underground Access & Caverns | 02 | Design | 020 | A402020 | Detail Design - OEM | 5 | Bradley Norwood | Split for Main Facility/OEM | BR-P4-A4-02-020 | BRIP4A402020 | BRIP440210 | BRIP4A402020 | #VALUE!
A4 | Underground Access & Caverns | 03 | Site Clearing | 000 | A403000 | Site Clearing | 4 |  |  | BR-P4-A4-03-000 | BRIP4A403000 | BRIP440300 | BRIP4A403000 | #VALUE!
A4 | Underground Access & Caverns | 03 | Site Clearing | 010 | A403010 | Site Clearing | 5 | Shannon Green |  | BR-P4-A4-03-010 | BRIP4A403010 | BRIP440310 | BRIP4A403010 | #VALUE!
A4 | Underground Access & Caverns | 04 | Construction Surface Facilities | 000 | A404000 | Construction Surface Facilities | 4 |  |  | BR-P4-A4-04-000 | BRIP4A404000 | BRIP440400 | BRIP4A404000 | #VALUE!
A4 | Underground Access & Caverns | 04 | Construction Surface Facilities | 010 | A404010 | Construction Site Facilities - Platform Areas | 5 | Shannon Green |  | BR-P4-A4-04-010 | BRIP4A404010 | BRIP440410 | BRIP4A404010 | #VALUE!
A4 | Underground Access & Caverns | 04 | Construction Surface Facilities | 020 | A404020 | Grout plant - mobilise and demobilise | 5 | Shannon Green |  | BR-P4-A4-04-020 | BRIP4A404020 | BRIP440420 | BRIP4A404020 | #VALUE!
A4 | Underground Access & Caverns | 04 | Construction Surface Facilities | 030 | A404030 | Construction Site Facilities - Platform 2 - Concrete Plant | 5 | Shannon Green |  | BR-P4-A4-04-030 | BRIP4A404030 | BRIP440430 | BRIP4A404030 | #VALUE!
A4 | Underground Access & Caverns | 04 | Construction Surface Facilities | 040 | A404040 | Concrete batching plant - mobilise and demobilise | 5 | Shannon Green |  | BR-P4-A4-04-040 | BRIP4A404040 | BRIP440440 | BRIP4A404040 | #VALUE!
A4 | Underground Access & Caverns | 04 | Construction Surface Facilities | 050 | A404050 | Construction Site Facilities - Upper inlet / outlet - Concrete Plant | 5 | Shannon Green |  | BR-P4-A4-04-050 | BRIP4A404050 | BRIP440450 | BRIP4A404050 | #VALUE!
A4 | Underground Access & Caverns | 05 | ECTV Exploratory Drilling | 000 | A405000 | ECTV Exploratory Drilling | 4 |  |  | BR-P4-A4-05-000 | BRIP4A405000 | BRIP440500 | BRIP4A405000 | #VALUE!
A4 | Underground Access & Caverns | 05 | ECTV Exploratory Drilling | 010 | A405010 | Exploratory Tunnel - Surface Works | 5 |  |  | BR-P4-A4-05-010 | BRIP4A405010 | BRIP440510 | BRIP4A405010 | #VALUE!
A4 | Underground Access & Caverns | 05 | ECTV Exploratory Drilling | 020 | A405020 | Exploratory Tunnel - Underground Works | 5 |  |  | BR-P4-A4-05-020 | BRIP4A405020 | BRIP440520 | BRIP4A405020 | #VALUE!
A4 | Underground Access & Caverns | 05 | ECTV Exploratory Drilling | 030 | A405030 | Exploratory Tunnel - Caverns Investigation | 5 |  |  | BR-P4-A4-05-030 | BRIP4A405030 | BRIP440530 | BRIP4A405030 | #VALUE!
A4 | Underground Access & Caverns | 05 | ECTV Exploratory Drilling | 040 | A405040 | Exploratory Tunnel - Management Services | 5 |  |  | BR-P4-A4-05-040 | BRIP4A405040 | BRIP440540 | BRIP4A405040 | #VALUE!
A4 | Underground Access & Caverns | 06 | MAT and ECVT | 000 | A406000 | MAT and ECVT | 4 |  |  | BR-P4-A4-06-000 | BRIP4A406000 | BRIP440600 | BRIP4A406000 | #VALUE!
A4 | Underground Access & Caverns | 06 | MAT and ECVT | 010 | A406010 | Main Access Tunnel (MAT) | 5 | Shannon Green |  | BR-P4-A4-06-010 | BRIP4A406010 | BRIP440610 | BRIP4A406010 | #VALUE!
A4 | Underground Access & Caverns | 06 | MAT and ECVT | 020 | A406020 | Emergency, Cable and Ventilation Tunnel (ECVT) Completion | 5 | Shannon Green |  | BR-P4-A4-06-020 | BRIP4A406020 | BRIP440620 | BRIP4A406020 | #VALUE!
A4 | Underground Access & Caverns | 07 | Power Cavern | 000 | A407000 | Power Cavern | 4 |  |  | BR-P4-A4-07-000 | BRIP4A407000 | BRIP440700 | BRIP4A407000 | #VALUE!
A4 | Underground Access & Caverns | 07 | Power Cavern | 010 | A407010 | Power Cavern | 5 | Shannon Green |  | BR-P4-A4-07-010 | BRIP4A407010 | BRIP440710 | BRIP4A407010 | #VALUE!
A4 | Underground Access & Caverns | 08 | Transformer Cavern | 000 | A408000 | Transformer Cavern | 4 |  |  | BR-P4-A4-08-000 | BRIP4A408000 | BRIP440800 | BRIP4A408000 | #VALUE!
A4 | Underground Access & Caverns | 08 | Transformer Cavern | 010 | A408010 | Transformer Cavern | 5 | Shannon Green |  | BR-P4-A4-08-010 | BRIP4A408010 | BRIP440810 | BRIP4A408010 | #VALUE!
A4 | Underground Access & Caverns | 09 | IPB Galleries (x 6) | 000 | A409000 | IPB Galleries (x 6) | 4 |  |  | BR-P4-A4-09-000 | BRIP4A409000 | BRIP440900 | BRIP4A409000 | #VALUE!
A4 | Underground Access & Caverns | 09 | IPB Galleries (x 6) | 010 | A409010 | IPB Galleries (x 6) | 5 | Shannon Green |  | BR-P4-A4-09-010 | BRIP4A409010 | BRIP440910 | BRIP4A409010 | #VALUE!
A4 | Underground Access & Caverns | 10 | MAT Tunnels between Power Cavern and Transformer Cavern | 000 | A410000 | MAT Tunnels between Power Cavern and Transformer Cavern | 4 |  |  | BR-P4-A4-10-000 | BRIP4A410000 | BRIP441000 | BRIP4A410000 | #VALUE!
A4 | Underground Access & Caverns | 10 | MAT Tunnels between Power Cavern and Transformer Cavern | 010 | A410010 | MAT Tunnels between Power Cavern and Transformer Cavern | 5 | Shannon Green |  | BR-P4-A4-10-010 | BRIP4A410010 | BRIP441010 | BRIP4A410010 | #VALUE!
A4 | Underground Access & Caverns | 11 | Traffic Control | 000 | A411000 | Traffic Control | 4 |  |  | BR-P4-A4-11-000 | BRIP4A411000 | BRIP441100 | BRIP4A411000 | #VALUE!
A4 | Underground Access & Caverns | 11 | Traffic Control | 010 | A411010 | Traffic Control | 5 | Shannon Green |  | BR-P4-A4-11-010 | BRIP4A411010 | BRIP441110 | BRIP4A411010 | #VALUE!
A4 | Underground Access & Caverns | 12 | Site Rehabilitation | 000 | A412000 | Site Rehabilitation | 4 |  |  | BR-P4-A4-12-000 | BRIP4A412000 | BRIP441100 | BRIP4A412000 | #VALUE!
A4 | Underground Access & Caverns | 12 | Site Rehabilitation | 010 | A412010 | Site Rehabilitation | 5 | Shannon Green |  | BR-P4-A4-12-010 | BRIP4A412010 | BRIP441110 | BRIP4A412010 | #VALUE!
A5 | Powerhouse Mech & Elec | 00 | Powerhouse Mech & Elec | 000 | A500000 | Powerhouse Mech & Elec | 3 |  |  | BR-P4-A5-00-000 | BRIP4A500000 |  | BRIP4A500000 | #VALUE!
A5 | Powerhouse Mech & Elec | 01 | Contractor Indirect & overheads | 000 | A501000 | Contractor Indirect & overheads | 4 |  |  | BR-P4-A5-01-000 | BRIP4A501000 | BRIP450100 | BRIP4A501000 | #VALUE!
A5 | Powerhouse Mech & Elec | 01 | Contractor Indirects & overheads | 010 | A501010 | Contractor Indirects & overheads | 5 | Shannon Green |  | BR-P4-A5-01-010 | BRIP4A501010 | BRIP450110 | BRIP4A501010 | #VALUE!
A5 | Powerhouse Mech & Elec | 02 | Design | 000 | A502000 | Design | 4 |  |  | BR-P4-A5-02-000 | BRIP4A502000 | BRIP450200 | BRIP4A502000 | #VALUE!
A5 | Powerhouse Mech & Elec | 02 | Design | 010 | A502010 | Design | 5 | Bradley Norwood |  | BR-P4-A5-02-010 | BRIP4A502010 | BRIP450210 | BRIP4A502010 | #VALUE!
A5 | Powerhouse Mech & Elec | 03 | Mech & Elec | 000 | A503000 | Mech & Elec | 4 |  |  | BR-P4-A5-03-000 | BRIP4A503000 | BRIP450300 | BRIP4A503000 | #VALUE!
A5 | Powerhouse Mech & Elec | 03 | Mech & Elec | 010 | A503010 | Mech & Elec | 5 | Shannon Green |  | BR-P4-A5-03-010 | BRIP4A503010 | BRIP450310 | BRIP4A503010 | #VALUE!
A5 | Powerhouse Mech & Elec | 04 | Power Turbines | 000 | A504000 | Power Turbines | 4 |  |  | BR-P4-A5-04-000 | BRIP4A504000 | BRIP450400 | BRIP4A504000 | #VALUE!
A5 | Powerhouse Mech & Elec | 04 | Power Turbines | 010 | A504010 | Power Turbines | 5 | Shannon Green |  | BR-P4-A5-04-010 | BRIP4A504010 | BRIP450410 | BRIP4A504010 | #VALUE!
A5 | Powerhouse Mech & Elec | 05 | Transformers | 000 | A505000 | Transformers | 4 |  |  | BR-P4-A5-05-000 | BRIP4A505000 | BRIP450500 | BRIP4A505000 | #VALUE!
A5 | Powerhouse Mech & Elec | 05 | Transformers | 010 | A505010 | Transformers | 5 | Shannon Green |  | BR-P4-A5-05-010 | BRIP4A505010 | BRIP450510 | BRIP4A505010 | #VALUE!
A5 | Powerhouse Mech & Elec | 06 | Hydro-Mechanical Works | 000 | A506000 | Hydro-Mechanical Works | 4 |  |  | BR-P4-A5-06-000 | BRIP4A506000 | BRIP450600 | BRIP4A506000 | #VALUE!
A5 | Powerhouse Mech & Elec | 06 | Hydro-Mechanical Works | 010 | A506010 | Hydro-Mechanical Works | 5 | Shannon Green |  | BR-P4-A5-06-010 | BRIP4A506010 | BRIP450610 | BRIP4A506010 | #VALUE!
A5 | Powerhouse Mech & Elec | 07 | Electrical Install | 000 | A507000 | Electrical Install | 4 |  |  | BR-P4-A5-07-000 | BRIP4A507000 | BRIP450700 | BRIP4A507000 | #VALUE!
A5 | Powerhouse Mech & Elec | 07 | Electrical Install | 010 | A507010 | Electrical Install | 5 | Shannon Green |  | BR-P4-A5-07-010 | BRIP4A507010 | BRIP450710 | BRIP4A507010 | #VALUE!
A5 | Powerhouse Mech & Elec | 08 | Power Evacuation and Grid Connection | 000 | A508000 | Power Evacuation and Grid Connection | 4 |  |  | BR-P4-A5-08-000 | BRIP4A508000 | BRIP450800 | BRIP4A508000 | #VALUE!
A5 | Powerhouse Mech & Elec | 08 | Power Evacuation and Grid Connection | 010 | A508010 | Power Evacuation and Grid Connection | 5 | Shannon Green |  | BR-P4-A5-08-010 | BRIP4A508010 | BRIP450810 | BRIP4A508010 | #VALUE!
A5 | Powerhouse Mech & Elec | 09 | Commissioning OEM | 000 | A509000 | Commissioning OEM | 4 |  |  | BR-P4-A5-09-000 | BRIP4A509000 | BRIP450900 | BRIP4A509000 | #VALUE!
A5 | Powerhouse Mech & Elec | 09 | Commissioning OEM | 010 | A509010 | Commissioning OEM | 5 | Shannon Green |  | BR-P4-A5-09-010 | BRIP4A509010 | BRIP450910 | BRIP4A509010 | #VALUE!
A5 | Powerhouse Mech & Elec | 10 | Site Rehabilitation | 000 | A510000 | Site Rehabilitation | 4 |  |  | BR-P4-A5-10-000 | BRIP4A510000 | BRIP451000 | BRIP4A510000 | #VALUE!
A5 | Powerhouse Mech & Elec | 10 | Site Rehabilitation | 010 | A510010 | Site Rehabilitation | 5 | Shannon Green |  | BR-P4-A5-10-010 | BRIP4A510010 | BRIP451010 | BRIP4A510010 | #VALUE!
A6 | Lower Reservoir | 00 | Lower Reservoir | 000 | A600000 | Lower Reservoir | 3 |  |  | BR-P4-A6-00-000 | BRIP4A600000 |  | BRIP4A600000 | #VALUE!
A6 | Lower Reservoir | 01 | Contractor Indirect & overheads | 000 | A601000 | Contractor Indirect & overheads | 4 |  |  | BR-P4-A6-01-000 | BRIP4A601000 | BRIP460100 | BRIP4A601000 | #VALUE!
A6 | Lower Reservoir | 01 | Contractor Indirect & overheads | 010 | A601010 | Contractor Indirect & overheads | 5 | Steve Pickering |  | BR-P4-A6-01-010 | BRIP4A601010 | BRIP460110 | BRIP4A601010 | #VALUE!
A6 | Lower Reservoir | 02 | Design | 000 | A602000 | Design | 4 |  |  | BR-P4-A6-02-000 | BRIP4A602000 | BRIP460200 | BRIP4A602000 | #VALUE!
A6 | Lower Reservoir | 02 | Design | 010 | A602010 | Design | 5 | Bradley Norwood |  | BR-P4-A6-02-010 | BRIP4A602010 | BRIP460210 | BRIP4A602010 | #VALUE!
A6 | Lower Reservoir | 03 | Site Clearing | 000 | A603000 | Site Clearing | 4 |  |  | BR-P4-A6-03-000 | BRIP4A603000 | BRIP460300 | BRIP4A603000 | #VALUE!
A6 | Lower Reservoir | 03 | Site Clearing | 010 | A603010 | Site Clearing | 5 | Steve Pickering |  | BR-P4-A6-03-010 | BRIP4A603010 | BRIP460310 | BRIP4A603010 | #VALUE!
A6 | Lower Reservoir | 04 | Quarry Development and Material Operations | 000 | A604000 | Quarry Development and Material Operations | 4 |  |  | BR-P4-A6-04-000 | BRIP4A604000 | BRIP460400 | BRIP4A604000 | #VALUE!
A6 | Lower Reservoir | 04 | Quarry Development and Material Operations | 010 | A604010 | Quarry Development and Material Operations | 5 | Steve Pickering |  | BR-P4-A6-04-010 | BRIP4A604010 | BRIP460410 | BRIP4A604010 | #VALUE!
A6 | Lower Reservoir | 05 | Diversion and Watering | 000 | A605000 | Diversion and Watering | 4 |  |  | BR-P4-A6-05-000 | BRIP4A605000 | BRIP460500 | BRIP4A605000 | #VALUE!
A6 | Lower Reservoir | 05 | Diversion and Watering | 010 | A605010 | Diversion and Watering | 5 | Steve Pickering |  | BR-P4-A6-05-010 | BRIP4A605010 | BRIP460510 | BRIP4A605010 | #VALUE!
A6 | Lower Reservoir | 06 | Foundations | 000 | A606000 | Foundations | 4 |  |  | BR-P4-A6-06-000 | BRIP4A606000 | BRIP460600 | BRIP4A606000 | #VALUE!
A6 | Lower Reservoir | 06 | Foundations | 010 | A606010 | Foundations | 5 | Steve Pickering |  | BR-P4-A6-06-010 | BRIP4A606010 | BRIP460610 | BRIP4A606010 | #VALUE!
A6 | Lower Reservoir | 07 | Dam Construction | 000 | A607000 | Dam Construction | 4 |  |  | BR-P4-A6-07-000 | BRIP4A607000 | BRIP460700 | BRIP4A607000 | #VALUE!
A6 | Lower Reservoir | 07 | Dam Construction | 010 | A607010 | Dam Construction | 5 | Steve Pickering |  | BR-P4-A6-07-010 | BRIP4A607010 | BRIP460710 | BRIP4A607010 | #VALUE!
A6 | Lower Reservoir | 08 | Spillway | 000 | A608000 | Spillway | 4 |  |  | BR-P4-A6-08-000 | BRIP4A608000 | BRIP460800 | BRIP4A608000 | #VALUE!
A6 | Lower Reservoir | 08 | Spillway | 010 | A608010 | Spillway | 5 | Steve Pickering |  | BR-P4-A6-08-010 | BRIP4A608010 | BRIP460810 | BRIP4A608010 | #VALUE!
A6 | Lower Reservoir | 09 | Intake Tower | 000 | A609000 | Intake Tower | 4 |  |  | BR-P4-A6-09-000 | BRIP4A609000 | BRIP460900 | BRIP4A609000 | #VALUE!
A6 | Lower Reservoir | 09 | Intake Tower | 010 | A609010 | Intake Tower | 5 | Steve Pickering |  | BR-P4-A6-09-010 | BRIP4A609010 | BRIP460910 | BRIP4A609010 | #VALUE!
A6 | Lower Reservoir | 10 | Outlet Works | 000 | A610000 | Outlet Works | 4 |  |  | BR-P4-A6-10-000 | BRIP4A610000 | BRIP461000 | BRIP4A610000 | #VALUE!
A6 | Lower Reservoir | 10 | Outlet Works | 010 | A610010 | Outlet Works | 5 | Steve Pickering |  | BR-P4-A6-10-010 | BRIP4A610010 | BRIP461010 | BRIP4A610010 | #VALUE!
A6 | Lower Reservoir | 11 | Fishway | 000 | A611000 | Fishway | 4 |  |  | BR-P4-A6-11-000 | BRIP4A611000 | BRIP461100 | BRIP4A611000 | #VALUE!
A6 | Lower Reservoir | 11 | Fishway | 010 | A611010 | Fishway | 5 | Steve Pickering |  | BR-P4-A6-11-010 | BRIP4A611010 | BRIP461110 | BRIP4A611010 | #VALUE!
A6 | Lower Reservoir | 12 | Over topping Event of the Lower Dam | 000 | A612000 | Over topping Event of the Lower Dam | 4 |  |  | BR-P4-A6-12-000 | BRIP4A612000 | BRIP461200 | BRIP4A612000 | #VALUE!
A6 | Lower Reservoir | 12 | Over topping Event of the Lower Dam | 010 | A612010 | Over topping Event of the Lower Dam | 5 | Steve Pickering |  | BR-P4-A6-12-010 | BRIP4A612010 | BRIP461210 | BRIP4A612010 | #VALUE!
A6 | Lower Reservoir | 13 | Traffic Control | 000 | A613000 | Traffic Control | 4 |  |  | BR-P4-A6-13-000 | BRIP4A613000 | BRIP461300 | BRIP4A613000 | #VALUE!
A6 | Lower Reservoir | 13 | Traffic Control | 010 | A613010 | Traffic Control | 5 | Steve Pickering |  | BR-P4-A6-13-010 | BRIP4A613010 | BRIP461310 | BRIP4A613010 | #VALUE!
A6 | Lower Reservoir | 14 | Site Rehabilitation | 000 | A614000 | Site Rehabilitation | 4 |  |  | BR-P4-A6-14-000 | BRIP4A614000 | BRIP461400 | BRIP4A614000 | #VALUE!
A6 | Lower Reservoir | 14 | Site Rehabilitation | 010 | A614010 | Site Rehabilitation | 5 | Steve Pickering |  | BR-P4-A6-14-010 | BRIP4A614010 | BRIP461410 | BRIP4A614010 | #VALUE!
A7 | Upper Reservoir | 00 | Upper Reservoir | 000 | A700000 | Upper Reservoir | 3 |  |  | BR-P4-A7-00-000 | BRIP4A700000 |  | BRIP4A700000 | #VALUE!
A7 | Upper Reservoir | 01 | Contractor Indirect & overheads | 000 | A701000 | Contractor Indirect & overheads | 4 |  |  | BR-P4-A7-01-000 | BRIP4A701000 | BRIP470100 | BRIP4A701000 | #VALUE!
A7 | Upper Reservoir | 01 | Contractor Indirect & overheads | 010 | A701010 | Contractor Indirect & overheads | 5 | Clifford Hookham |  | BR-P4-A7-01-010 | BRIP4A701010 | BRIP470110 | BRIP4A701010 | #VALUE!
A7 | Upper Reservoir | 02 | Design | 000 | A702000 | Design | 4 |  |  | BR-P4-A7-02-000 | BRIP4A702000 | BRIP470200 | BRIP4A702000 | #VALUE!
A7 | Upper Reservoir | 02 | Design | 010 | A702010 | Design | 5 | Bradley Norwood |  | BR-P4-A7-02-010 | BRIP4A702010 | BRIP470210 | BRIP4A702010 | #VALUE!
A7 | Upper Reservoir | 03 | Site Clearing | 000 | A703000 | Site Clearing | 4 |  |  | BR-P4-A7-03-000 | BRIP4A703000 | BRIP470300 | BRIP4A703000 | #VALUE!
A7 | Upper Reservoir | 03 | Site Clearing | 010 | A703010 | Site Clearing | 5 | Clifford Hookham |  | BR-P4-A7-03-010 | BRIP4A703010 | BRIP470310 | BRIP4A703010 | #VALUE!
A7 | Upper Reservoir | 04 | Quarry Development and Material Operations | 000 | A704000 | Quarry Development and Material Operations | 4 |  |  | BR-P4-A7-04-000 | BRIP4A704000 | BRIP470400 | BRIP4A704000 | #VALUE!
A7 | Upper Reservoir | 04 | Quarry Development and Material Operations | 010 | A704010 | Quarry Development and Material Operations | 5 | Clifford Hookham |  | BR-P4-A7-04-010 | BRIP4A704010 | BRIP470410 | BRIP4A704010 | #VALUE!
A7 | Upper Reservoir | 05 | Diversion and Watering | 000 | A705000 | Diversion and Watering | 4 |  |  | BR-P4-A7-05-000 | BRIP4A705000 | BRIP470500 | BRIP4A705000 | #VALUE!
A7 | Upper Reservoir | 05 | Diversion and Watering | 010 | A705010 | Diversion and Watering | 5 | Clifford Hookham |  | BR-P4-A7-05-010 | BRIP4A705010 | BRIP470510 | BRIP4A705010 | #VALUE!
A7 | Upper Reservoir | 06 | Foundations | 000 | A706000 | Foundations | 4 |  |  | BR-P4-A7-06-000 | BRIP4A706000 | BRIP470600 | BRIP4A706000 | #VALUE!
A7 | Upper Reservoir | 06 | Foundations | 010 | A706010 | Foundations | 5 | Clifford Hookham |  | BR-P4-A7-06-010 | BRIP4A706010 | BRIP470610 | BRIP4A706010 | #VALUE!
A7 | Upper Reservoir | 07 | Dam Construction | 000 | A707000 | Dam Construction | 4 |  |  | BR-P4-A7-07-000 | BRIP4A707000 | BRIP470700 | BRIP4A707000 | #VALUE!
A7 | Upper Reservoir | 07 | Main CFRD Dam | 010 | A707010 | Main CFRD Dam | 5 | Clifford Hookham |  | BR-P4-A7-07-010 | BRIP4A707010 | BRIP470710 | BRIP4A707010 | #VALUE!
A7 | Upper Reservoir | 07 | Main Saddle (CFRD) Dam | 020 | A707020 | Main Saddle (CFRD) Dam | 5 | Clifford Hookham |  | BR-P4-A7-07-020 | BRIP4A707020 | BRIP470720 | BRIP4A707020 | #VALUE!
A7 | Upper Reservoir | 07 | Secondary Saddle (CFRD) Dam A | 030 | A707030 | Secondary Saddle (CFRD) Dam A | 5 | Clifford Hookham |  | BR-P4-A7-07-030 | BRIP4A707030 | BRIP470730 | BRIP4A707030 | #VALUE!
A7 | Upper Reservoir | 07 | Secondary Saddle (CFRD) Dam B1 | 040 | A707040 | Secondary Saddle (CFRD) Dam B1 | 5 | Clifford Hookham |  | BR-P4-A7-07-040 | BRIP4A707040 | BRIP470740 | BRIP4A707040 | #VALUE!
A7 | Upper Reservoir | 07 | Secondary Saddle (CFRD) Dam B2 | 050 | A707050 | Secondary Saddle (CFRD) Dam B2 | 5 | Clifford Hookham |  | BR-P4-A7-07-050 | BRIP4A707050 | BRIP470750 | BRIP4A707050 | #VALUE!
A7 | Upper Reservoir | 07 | Secondary Saddle (CFRD) Dam No.B3 | 060 | A707060 | Secondary Saddle (CFRD) Dam No.B3 | 5 | Clifford Hookham |  | BR-P4-A7-07-060 | BRIP4A707060 | BRIP470760 | BRIP4A707060 | #VALUE!
A7 | Upper Reservoir | 08 | Emergency Spillway | 000 | A708000 | Emergency Spillway | 4 |  |  | BR-P4-A7-08-000 | BRIP4A708000 | BRIP470800 | BRIP4A708000 | #VALUE!
A7 | Upper Reservoir | 08 | Emergency Spillway | 010 | A708010 | Emergency Spillway | 5 | Clifford Hookham |  | BR-P4-A7-08-010 | BRIP4A708010 | BRIP470810 | BRIP4A708010 | #VALUE!
A7 | Upper Reservoir | 09 | Traffic Control | 000 | A709000 | Traffic Control | 4 |  |  | BR-P4-A7-09-000 | BRIP4A709000 | BRIP470900 | BRIP4A709000 | #VALUE!
A7 | Upper Reservoir | 09 | Traffic Control | 010 | A709010 | Traffic Control | 5 | Clifford Hookham |  | BR-P4-A7-09-010 | BRIP4A709010 | BRIP470910 | BRIP4A709010 | #VALUE!
A7 | Upper Reservoir | 10 | Site Rehabilitation | 000 | A710000 | Site Rehabilitation | 4 |  |  | BR-P4-A7-10-000 | BRIP4A710000 | BRIP471000 | BRIP4A710000 | #VALUE!
A7 | Upper Reservoir | 10 | Site Rehabilitation | 010 | A710010 | Site Rehabilitation | 5 | Clifford Hookham |  | BR-P4-A7-10-010 | BRIP4A710010 | BRIP471010 | BRIP4A710010 | #VALUE!
A8 | Transmissions | 00 | Transmissions | 000 | A800000 | Transmissions | 3 |  |  | BR-P4-A8-00-000 | BRIP4A800000 |  | BRIP4A800000 | #VALUE!
A8 | Transmissions | 01 | Transmissions - Tarong | 000 | A801000 | Borumba - Tarong 275kV | 4 |  | Renumbered L4 to remove double up | BR-P4-A8-01-000 | BRIP4A801000 | BRIP480000 | BRIP4A801000 | #VALUE!
A8 | Transmissions | 01 | Transmissions - Tarong | 010 | A801010 | Borumba - Tarong 275kV | 5 |  |  | BR-P4-A8-01-010 | BRIP4A801010 | BRIP480010 | BRIP4A801010 | #VALUE!
A8 | Transmissions | 02 | Transmissions - Woolooga | 000 | A802000 | Borumba - Woolooga 275kV | 4 |  | Renumbered L4 to remove double up | BR-P4-A8-02-000 | BRIP4A802000 | BRIP480100 | BRIP4A802000 | #VALUE!
A8 | Transmissions | 02 | Transmissions - Woolooga | 110 | A802110 | Borumba - Woolooga 275kV | 5 |  |  | BR-P4-A8-02-110 | BRIP4A802110 | BRIP480110 | BRIP4A802110 | #VALUE!
A9 | Contingency & Escalation | 00 | Contingency & Escalation | 000 | A900000 | Contingency & Escalation | 3 |  | Need to amend L3 | BR-P4-A9-00-000 | BRIP4A900000 |  | BRIP4A900000 | #VALUE!
A9 | Contingency & Escalation | 91 | Contingency | 000 | A991000 | Contingency | 4 |  | Doesn’t fit | BR-P4-A9-91-000 | BRIP4A991000 | BRIP499100 | BRIP4A991000 | #VALUE!
A9 | Contingency & Escalation | 91 | Contingency | 010 | A991010 | P50 Contingency QH Costs | 5 | Mike Wells |  | BR-P4-A9-91-010 | BRIP4A991010 | BRIP499110 | BRIP4A991010 | #VALUE!
A9 | Contingency & Escalation | 91 | Contingency | 020 | A991020 | P90 Contingency QH Costs | 5 | Mike Wells |  | BR-P4-A9-91-020 | BRIP4A991020 | BRIP499120 | BRIP4A991020 | #VALUE!
A9 | Contingency & Escalation | 91 | Contingency | 030 | A991030 | P50 Contingency Surface Infrastructure and Enabling | 5 | Mike Wells |  | BR-P4-A9-91-030 | BRIP4A991030 | BRIP499130 | BRIP4A991030 | #VALUE!
A9 | Contingency & Escalation | 91 | Contingency | 040 | A991040 | P90 Contingency Surface Infrastructure and Enabling | 5 | Mike Wells |  | BR-P4-A9-91-040 | BRIP4A991040 | BRIP499140 | BRIP4A991040 | #VALUE!
A9 | Contingency & Escalation | 91 | Contingency | 050 | A991050 | P50 Contingency Underground Waterways | 5 | Mike Wells |  | BR-P4-A9-91-050 | BRIP4A991050 | BRIP499150 | BRIP4A991050 | #VALUE!
A9 | Contingency & Escalation | 91 | Contingency | 060 | A991060 | P90 Contingency Underground Waterways | 5 | Mike Wells |  | BR-P4-A9-91-060 | BRIP4A991060 | BRIP499160 | BRIP4A991060 | #VALUE!
A9 | Contingency & Escalation | 91 | Contingency | 070 | A991070 | P50 Contingency Underground Access & Caverns | 5 | Mike Wells |  | BR-P4-A9-91-070 | BRIP4A991070 | BRIP499170 | BRIP4A991070 | #VALUE!
A9 | Contingency & Escalation | 91 | Contingency | 080 | A991080 | P90 Contingency Underground Access & Caverns | 5 | Mike Wells |  | BR-P4-A9-91-080 | BRIP4A991080 | BRIP499180 | BRIP4A991080 | #VALUE!
A9 | Contingency & Escalation | 91 | Contingency | 090 | A991090 | P50 Contingency Powerhouse Mech & Elec | 5 | Mike Wells |  | BR-P4-A9-91-090 | BRIP4A991090 | BRIP499190 | BRIP4A991090 | #VALUE!
A9 | Contingency & Escalation | 91 | Contingency | 100 | A991100 | P90 Contingency Powerhouse Mech & Elec | 5 | Mike Wells |  | BR-P4-A9-91-100 | BRIP4A991100 | BRIP499200 | BRIP4A991100 | #VALUE!
A9 | Contingency & Escalation | 91 | Contingency | 110 | A991110 | P50 Contingency Lower Reservoir | 5 | Mike Wells |  | BR-P4-A9-91-110 | BRIP4A991110 | BRIP499210 | BRIP4A991110 | #VALUE!
A9 | Contingency & Escalation | 91 | Contingency | 120 | A991120 | P90 Contingency Lower Reservoir | 5 | Mike Wells |  | BR-P4-A9-91-120 | BRIP4A991120 | BRIP499220 | BRIP4A991120 | #VALUE!
A9 | Contingency & Escalation | 91 | Contingency | 130 | A991130 | P50 Contingency Upper Reservoir | 5 | Mike Wells |  | BR-P4-A9-91-130 | BRIP4A991130 | BRIP499230 | BRIP4A991130 | #VALUE!
A9 | Contingency & Escalation | 91 | Contingency | 140 | A991140 | P90 Contingency Upper Reservoir | 5 | Mike Wells |  | BR-P4-A9-91-140 | BRIP4A991140 | BRIP499240 | BRIP4A991140 | #VALUE!
A9 | Contingency & Escalation | 95 | Escalation | 000 | A995000 | Escalation | 4 | Mike Wells | Doesn’t fit | BR-P4-A9-95-000 | BRIP4A995000 | BRIP499500 | BRIP4A995000 | #VALUE!
A9 | Contingency & Escalation | 95 | Escalation | 010 | A995010 | Escalation QH Costs | 5 | Mike Wells |  | BR-P4-A9-95-010 | BRIP4A995010 | BRIP499510 | BRIP4A995010 | #VALUE!
A9 | Contingency & Escalation | 95 | Escalation | 020 | A995020 | Escalation Surface Infrastructure and Enabling | 5 | Mike Wells |  | BR-P4-A9-95-020 | BRIP4A995020 | BRIP499520 | BRIP4A995020 | #VALUE!
A9 | Contingency & Escalation | 95 | Escalation | 030 | A995030 | Escalation Underground Waterways | 5 | Mike Wells |  | BR-P4-A9-95-030 | BRIP4A995030 | BRIP499530 | BRIP4A995030 | #VALUE!
A9 | Contingency & Escalation | 95 | Escalation | 040 | A995040 | Escalation Underground Access & Caverns | 5 | Mike Wells |  | BR-P4-A9-95-040 | BRIP4A995040 | BRIP499540 | BRIP4A995040 | #VALUE!
A9 | Contingency & Escalation | 95 | Escalation | 050 | A995050 | Escalation Powerhouse Mech & Elec | 5 | Mike Wells |  | BR-P4-A9-95-050 | BRIP4A995050 | BRIP499550 | BRIP4A995050 | #VALUE!
A9 | Contingency & Escalation | 95 | Escalation | 060 | A995060 | Escalation Lower Reservoir | 5 | Mike Wells |  | BR-P4-A9-95-060 | BRIP4A995060 | BRIP499560 | BRIP4A995060 | #VALUE!
A9 | Contingency & Escalation | 95 | Escalation | 070 | A995070 | Escalation Upper Reservoir | 5 | Mike Wells |  | BR-P4-A9-95-070 | BRIP4A995070 | BRIP499570 | BRIP4A995070 | #VALUE!

## Program WBS
Code Mapping
Program ID | Program | WBS Level 1 - ID | WBS Level 1 | WBS Level 2 - ID | WBS Level 2 | WBS Level 3 - ID | WBS Level 3 | OBS ID | OBS Area | WBS Level 4 - ID | L4 Code | WBS Level 4 | WBS Level 5- ID | L5 Code | NEW WBS ID | WBS Level 5 | Responsible | WBS Level | CONTROL ACCOUNT | Current WBS | Estimate | Prism Code
QH | QLD Hydro PHES | [16 empty] | 0 | [5 empty] | WFP | WFP $
QH | QLD Hydro PHES | QH | Program | [14 empty] | 1
QH | QLD Hydro PHES | QH | Program | P0 | Program | [12 empty] | 2
QH | QLD Hydro PHES | QH | Program | P0 | Program | [12 empty] | 2
QH | QLD Hydro PHES | QH | Program | P1 | Feasibility Studies | [12 empty] | 2
QH | QLD Hydro PHES | QH | Program | P1 | Feasibility Studies | [12 empty] | 2
QH | QLD Hydro PHES | QH | Program | P2 | Options Analysis & DAR | [12 empty] | 2
QH | QLD Hydro PHES | QH | Program | P2 | Options Analysis & DAR | [12 empty] | 2
QH | QLD Hydro PHES | QH | Program | P3 | Design Development & Procurement | [12 empty] | 2
QH | QLD Hydro PHES | QH | Program | P3 | Design Development & Procurement | [12 empty] | 2
QH | QLD Hydro PHES | QH | Program | P4 | Delivery | [12 empty] | 2
QH | QLD Hydro PHES | QH | Program | P0 | Delivery | W01 | Client Costs | A1 | Program | 0 | 00 | Program | 00000 | 000 | A100000 | Program |  | 3 | QHP0-A1-00-000 |  |  | QHP0A100000
QH | QLD Hydro PHES | QH | Program | P0 | Delivery | W01 | Client Costs | A1 | QH Costs | 10000 | 10 | EGM Corporate | 10000 | 000 | A110000 | EGM Corporate |  | 4 | QHP0-A1-10-000 |  |  | QHP0A110000 | Finance/Corporate
QH | QLD Hydro PHES | QH | Program | P0 | Delivery | W01 | Client Costs | A1 | QH Costs | 10000 | 10 | EGM Corporate | 10010 | 010 | A110010 | Finance (Staff) | Amy Treble | 5 | QHP0-A1-10-010 | 0 |  | QHP0A110010 |  | 8 | #VALUE! | Program | 159 | #VALUE!
QH | QLD Hydro PHES | QH | Program | P0 | Delivery | W01 | Client Costs | A1 | QH Costs | 10000 | 10 | EGM Corporate | 10020 | 020 | A110020 | Finance (Contractors) | Amy Treble | 5 | QHP0-A1-10-020 | 0 |  | QHP0A110020 |  | 0 | 0 | Assets and Engineering | 1 | #VALUE!
|  | QH |  | P0 |  |  |  | A1 |  | 10000 | 10 | EGM Corporate | 10030 | 030 | A110030 | Finance (Expenses & Fees) | Amy Treble | 5 | QHP0-A1-10-030 |  |  | QHP0A110030 |  | 0 | 0 | CEO Office | 2 | #VALUE!
QH | QLD Hydro PHES | QH | Program | P0 | Delivery | W01 | Client Costs | A1 | QH Costs | 10000 | 10 | EGM Corporate | 10040 | 040 | A110040 | ICT (Staff) | Ashlen Naicker | 5 | QHP0-A1-10-040 | 0 |  | QHP0A110040 | ICT | 4 | #VALUE! | Commercial | 19 | #VALUE!
QH | QLD Hydro PHES | QH | Program | P0 | Delivery | W01 | Client Costs | A1 | QH Costs | 10000 | 10 | EGM Corporate | 10050 | 050 | A110050 | ICT (Contractors) | Ashlen Naicker | 5 | QHP0-A1-10-050 | 0 |  | QHP0A110050 |  | 0 | 0 | Communications and Stakeholder Engagement | 37 | #VALUE!
QH | QLD Hydro PHES | QH | Program | P0 | Delivery | W01 | Client Costs | A1 | QH Costs | 10000 | 10 | EGM Corporate | 10060 | 060 | A110060 | Legal (Staff) | Erin McCormick | 5 | QHP0-A1-10-060 | 0 |  | QHP0A110060 | Legal, Risk and Governance | 7 | #VALUE! | Corporate | 1 | #VALUE!
QH | QLD Hydro PHES | QH | Program | P0 | Delivery | W01 | Client Costs | A1 | QH Costs | 10000 | 10 | EGM Corporate | 10070 | 070 | A110070 | Legal (Contractors - Capital) | Erin McCormick | 5 | QHP0-A1-10-070 | 0 |  | QHP0A110070 |  | 0 | 0 | Delivery | 1 | #VALUE!
|  | QH |  | P0 |  |  |  | A1 |  | 10000 | 10 | EGM Corporate | 10080 | 080 | A110080 | Legal (Contractors - Operating) | Erin McCormick | 5 | QHP0-A1-10-080 |  |  | QHP0A110080
|  | QH |  | P0 |  |  |  | A1 |  | 10000 | 10 | EGM Corporate | 10090 | 090 | A110090 | Legal (Expenses & Fees) | Erin McCormick | 5 | QHP0-A1-10-090 |  |  | QHP0A110090 |  | 0 | 0 | Development | 2 | #VALUE!
QH | QLD Hydro PHES | QH | Program | P0 | Delivery | W01 | Client Costs | A1 | QH Costs | 10000 | 10 | EGM Corporate | 10100 | 100 | A110100 | People and Capability (Staff) | Marissa Heggie | 5 | QHP0-A1-10-100 | 0 |  | QHP0A110100 | People and Culture | 11 | #VALUE! | Environment and Approvals | 5 | #VALUE!
QH | QLD Hydro PHES | QH | Program | P0 | Delivery | W01 | Client Costs | A1 | QH Costs | 10000 | 10 | EGM Corporate | 10110 | 110 | A110110 | People and Capability (Contractors) | Marissa Heggie | 5 | QHP0-A1-10-110 | 0 |  | QHP0A110110 |  | 0 | 0 | Environment and Approvals - B | 2 | #VALUE!
|  | QH |  | P0 |  |  |  | A1 |  | 10000 | 10 | EGM Corporate | 10120 | 120 | A110120 | People and Capability (Expenses & Fees) | Marissa Heggie | 5 | QHP0-A1-10-120 |  |  | QHP0A110120 |  | 0 | 0 | Environment and Approvals - PB | 5 | #VALUE!
QH | QLD Hydro PHES | QH | Program | P0 | Delivery | W01 | Client Costs | A1 | QH Costs | 10000 | 10 | EGM Corporate | 10130 | 130 | A110130 | Procurement (Contractors) | Jessica Oxford | 5 | QHP0-A1-10-130 | 0 |  | QHP0A110130 |  | 0 | 0 | ESC | 1 | #VALUE!
QH | QLD Hydro PHES | QH | Program | P0 | Delivery | W01 | Client Costs | A1 | QH Costs | 10000 | 10 | EGM Corporate | 10140 | 140 | A110140 | Procurement (Staff) | Jessica Oxford | 5 | QHP0-A1-10-140 | 1001 |  | QHP0A110140 | Procurement | 8 | #VALUE! | Finance | 7 | #VALUE!
QH | QLD Hydro PHES | QH | Program | P0 | Delivery | W01 | Client Costs | A1 | QH Costs | 11000 | 20 | EGM Commercial | 11000 | 000 | A120000 | EGM Commercial |  | 4 | QHP0-A1-20-000 | 0 |  | QHP0A111000 |  | 0 | 0 | Government Relations and Policy | 9 | #VALUE!
QH | QLD Hydro PHES | QH | Program | P0 | Delivery | W01 | Client Costs | A1 | QH Costs | 11000 | 20 | EGM Commercial | 11000 | 010 | A120010 | Commercial - Procurement (Staff) | Jason Long | 5 | QHP0-A1-20-010 | 0 |  | QHP0A111000 | Commercial | 19 | #VALUE! | Health & Safety | 5 | #VALUE!
QH | QLD Hydro PHES | QH | Program | P0 | Delivery | W01 | Client Costs | A1 | QH Costs | 11000 | 20 | EGM Commercial | 11010 | 020 | A120020 | Commercial - Contract Management (Staff) | Jason Long | 5 | QHP0-A1-20-020 | 0 |  | QHP0A111010 |  | 0 | 0 | ICT | 4 | #VALUE!
QH | QLD Hydro PHES | QH | Program | P0 | Delivery | W01 | Client Costs | A1 | QH Costs | 11000 | 20 | EGM Commercial | 11020 | 030 | A120030 | Commercial - Procurement (Contractors) | Jason Long | 5 | QHP0-A1-20-030 | 0 |  | QHP0A111020 |  | 0 | 0 | Indigenous Partnerships | 3 | #VALUE!
QH | QLD Hydro PHES | QH | Program | P0 | Delivery | W01 | Client Costs | A1 | QH Costs | 11000 | 20 | EGM Commercial | 11030 | 040 | A120040 | Commercial - Contract Management (Contractors) | Jason Long | 5 | QHP0-A1-20-040 | 0 |  | QHP0A111030 |  | 0 | 0 | Integration | 3 | #VALUE!
QH | QLD Hydro PHES | QH | Program | P0 | Delivery | W01 | Client Costs | A1 | QH Costs | 11000 | 20 | EGM Commercial | 11040 | 050 | A120050 | PMO (Staff) | Mike Wells | 5 | QHP0-A1-20-050 | 0 |  | QHP0A111040 | PMO | 10 | #VALUE! | Land | 4 | #VALUE!
QH | QLD Hydro PHES | QH | Program | P0 | Delivery | W01 | Client Costs | A1 | QH Costs | 11000 | 20 | EGM Commercial | 11050 | 060 | A120060 | PMO (Contractors) | Mike Wells | 5 | QHP0-A1-20-060 | 0 |  | QHP0A111050 |  | 0 | 0 | Legal, Risk and Governance | 7 | #VALUE!
QH | QLD Hydro PHES | QH | Program | P0 | Delivery | W01 | Client Costs | A1 | QH Costs | 12000 | 30 | EGM Development | 12000 | 000 | A130000 | EGM Development |  | 4 | QHP0-A1-30-000 | 0 |  | QHP0A112000 |  | 0 | 0 | People and Culture | 11 | #VALUE!
QH | QLD Hydro PHES | QH | Program | P0 | Delivery | W01 | Client Costs | A1 | QH Costs | 12000 | 30 | EGM Development | 12010 | 010 | A130010 | Development Pioneer Burdekin Project (Staff) | Trish Auld | 5 | QHP0-A1-30-010 | 0 |  | QHP0A112010 | Development | 2 | #VALUE! | PMO | 10 | #VALUE!
QH | QLD Hydro PHES | QH | Program | P0 | Delivery | W01 | Client Costs | A1 | QH Costs | 12000 | 30 | EGM Development | 12020 | 020 | A130020 | Integration (Staff) | Paul Smith | 5 | QHP0-A1-30-020 | 0 |  | QHP0A112020 | Integration | 3 | #VALUE! | Procurement | 8 | #VALUE!
QH | QLD Hydro PHES | QH | Program | P0 | Delivery | W01 | Client Costs | A1 | QH Costs | 12000 | 30 | EGM Development | 12030 | 030 | A130030 | Quality and Assurance (Staff) | Fintan Moore | 5 | QHP0-A1-30-030 | 0 |  | QHP0A112030 | Quality & Assurance | 3 | #VALUE! | Quality & Assurance | 3 | #VALUE!
QH | QLD Hydro PHES | QH | Program | P0 | Delivery | W01 | Client Costs | A1 | QH Costs | 12000 | 30 | EGM Development | 12040 | 040 | A130040 | Strategy and Planning (Staff) | Chris Gwynne | 5 | QHP0-A1-30-040 | 0 |  | QHP0A112040 | Strategy and Planning | 8 | #VALUE! | Regional Development | 1 | #VALUE!
QH | QLD Hydro PHES | QH | Program | P0 | Delivery | W01 | Client Costs | A1 | QH Costs | 12000 | 30 | EGM Development | 12050 | 050 | A130050 | Regional Development (Staff) | Tracey Lines | 5 | QHP0-A1-30-050 | 0 |  | QHP0A112050 | Regional Development | 1 | #VALUE! | Strategy and Planning | 8 | #VALUE!
QH | QLD Hydro PHES | QH | Program | P0 | Delivery | W01 | Client Costs | A1 | QH Costs | 12000 | 30 | EGM Development | 12060 | 060 | A130060 | Health, Safety and Wellbeing (Staff) | Kelly Palmer | 5 | QHP0-A1-30-060 | 0 |  | QHP0A112060 | Health & Safety | 5 | #VALUE!
QH | QLD Hydro PHES | QH | Program | P0 | Delivery | W01 | Client Costs | A1 | QH Costs | 12000 | 30 | EGM Development | 12070 | 070 | A130070 | Assets and Engineering (Staff) | TBD | 5 | QHP0-A1-30-070 | 0 |  | QHP0A112070 | Assets and Engineering | 1 | #VALUE!
QH | QLD Hydro PHES | QH | Program | P0 | Delivery | W01 | Client Costs | A1 | QH Costs | 13000 | 40 | EGM Delivery | 13000 | 000 | A140000 | EGM Delivery |  | 4 | QHP0-A1-40-000 | 0 |  | QHP0A113000 |  | 0 | 0
QH | QLD Hydro PHES | QH | Program | P0 | Delivery | W01 | Client Costs | A1 | QH Costs | 13000 | 40 | EGM Delivery | 13010 | 010 | A140010 | Delivery (Staff) | Geoff Scott | 5 | QHP0-A1-40-010 | 0 |  | QHP0A113010 | Delivery | 1 | #VALUE!
QH | QLD Hydro PHES | QH | Program | P0 | Delivery | W01 | Client Costs | A1 | QH Costs | 13000 | 40 | EGM Delivery | 13020 | 020 | A140020 | Delivery Contractors | Geoff Scott | 5 | QHP0-A1-40-020 | 0 |  | QHP0A113020 |  | 0 | 0
QH | QLD Hydro PHES | QH | Program | P0 | Delivery | W01 | Client Costs | A1 | QH Costs | 14000 | 50 | EGM Communication, Stakeholder Engagement and Environment | 14000 | 000 | A150000 | EGM Communication, Stakeholder Engagement and Environment |  | 4 | QHP0-A1-50-000 | 0 |  | QHP0A114000 |  | 0 | 0
QH | QLD Hydro PHES | QH | Program | P0 | Delivery | W01 | Client Costs | A1 | QH Costs | 14000 | 50 | EGM Communication, Stakeholder Engagement and Environment | 14010 | 010 | A150010 | Community and Stakeholder (Staff) | Juile Spencer | 5 | QHP0-A1-50-010 | 0 |  | QHP0A114010 | Communications and Stakeholder Engagement | 38 | #VALUE!
QH | QLD Hydro PHES | QH | Program | P0 | Delivery | W01 | Client Costs | A1 | QH Costs | 14000 | 50 | EGM Communication, Stakeholder Engagement and Environment | 14020 | 020 | A150020 | Community and Stakeholder (Contractors) | Juile Spencer | 5 | QHP0-A1-50-020 | 0 |  | QHP0A114020 |  | 0 | 0
QH | QLD Hydro PHES | QH | Program | P0 | Delivery | W01 | Client Costs | A1 | QH Costs | 14000 | 50 | EGM Communication, Stakeholder Engagement and Environment | 14030 | 030 | A150030 | Environment (Staff) | Juile Spencer | 5 | QHP0-A1-50-030 | 0 |  | QHP0A114030 | Environment and Approvals | 12 | #VALUE!
QH | QLD Hydro PHES | QH | Program | P0 | Delivery | W01 | Client Costs | A1 | QH Costs | 14000 | 50 | EGM Communication, Stakeholder Engagement and Environment | 14040 | 040 | A150040 | Environment (Contractors) | Damien Brown | 5 | QHP0-A1-50-040 | 0 |  | QHP0A114040 |  | 0 | 0
QH | QLD Hydro PHES | QH | Program | P0 | Delivery | W01 | Client Costs | A1 | QH Costs | 14000 | 50 | EGM Communication, Stakeholder Engagement and Environment | 14050 | 050 | A150050 | Land (Staff) | Andrew Nolan | 5 | QHP0-A1-50-050 | 0 |  | QHP0A114050 | Land | 4 | #VALUE!
QH | QLD Hydro PHES | QH | Program | P0 | Delivery | W01 | Client Costs | A1 | QH Costs | 14000 | 50 | EGM Communication, Stakeholder Engagement and Environment | 14060 | 060 | A150060 | Indigenous Partnership (Staff) | Natasha Patterson | 5 | QHP0-A1-50-060 | 0 |  | QHP0A114060 | Indigenous Partnerships | 3 | #VALUE!
QH | QLD Hydro PHES | QH | Program | P0 | Delivery | W01 | Client Costs | A1 | QH Costs | 14000 | 50 | EGM Communication, Stakeholder Engagement and Environment | 14070 | 070 | A150070 | Government Relations and Policy (Staff) | Natasha Patterson | 5 | QHP0-A1-50-070 | 0 |  | QHP0A114070 | Government Relations and Policy | 9 | #VALUE!
QH | QLD Hydro PHES | QH | Program | P0 | Delivery | W01 | Client Costs | A1 | QH Costs | 14000 | 50 | EGM Communication, Stakeholder Engagement and Environment | 14080 | 080 | A150080 | Government Relations and Policy (Contractors) | Mike Foster | 5 | QHP0-A1-50-080 | 0 |  | QHP0A114080 |  | 0 | 0
QH | QLD Hydro PHES | QH | Program | P0 | Delivery | W01 | Client Costs | A1 | QH Costs | 15000 | 60 | CEO |  | 000 | A160000 | CEO |  | 4 | QHP0-A1-60-000 | 0 |  | QHP0A1 |  | 0 | 0
QH | QLD Hydro PHES | QH | Program | P0 | Delivery | W01 | Client Costs | A1 | QH Costs | 15000 | 60 | CEO | 15010 | 010 | A160010 | CEO & EGM Staff | Kieran Cusack | 5 | QHP0-A1-60-010 | 0 |  | QHP0A115010 | CEO Office | 2 | #VALUE!
QH | QLD Hydro PHES | QH | Program | P0 | Delivery | W01 | Client Costs | A1 | QH Costs | 15000 | 60 | CEO | 15020 | 020 | A160020 | CEO & EGM (Expenses and Events) | Kieran Cusack | 5 | QHP0-A1-60-020 | 0 |  | QHP0A115020 |  | 0 | 0
QH | QLD Hydro PHES | QH | Program | P0 | Delivery | W01 | Client Costs | A1 | QH Costs | 17000 | 70 | Indirect | 17000 | 000 | A170000 | Indirect |  | 4 | QHP0-A1-70-000 | 0 |  | QHP0A117000 |  | 0 | 0
QH | QLD Hydro PHES | QH | Program | P0 | Delivery | W01 | Client Costs | A1 | QH Costs | 17000 | 70 | Indirect | 17010 | 010 | A170010 | Travel, Accommodation & Disbursements | Amy Treble | 5 | QHP0-A1-70-010 | 1009 |  | QHP0A117010 |  | 0 | 0
QH | QLD Hydro PHES | QH | Program | P0 | Delivery | W01 | Client Costs | A1 | QH Costs | 17000 | 70 | Indirect | 17020 | 020 | A170020 | Training & Development | Amy Treble | 5 | QHP0-A1-70-020 | 0 |  | QHP0A117020 |  | 0 | 0
QH | QLD Hydro PHES | QH | Program | P0 | Delivery | W01 | Client Costs | A1 | QH Costs | 17000 | 70 | Indirect | 17030 | 030 | A170030 | Other Staff Costs (memberships, subscriptions) | Amy Treble | 5 | QHP0-A1-70-030 | 1012 |  | QHP0A117030 |  | 0 | 0
QH | QLD Hydro PHES | QH | Program | P0 | Delivery | W01 | Client Costs | A1 | QH Costs | 17000 | 70 | Indirect | 17040 | 040 | A170040 | IT Software, Licenses & Equipment | Amy Treble | 5 | QHP0-A1-70-040 | 0 |  | QHP0A117040 |  | 0 | 0
QH | QLD Hydro PHES | QH | Program | P0 | Delivery | W01 | Client Costs | A1 | QH Costs | 17000 | 70 | Indirect | 17050 | 050 | A170050 | Offices and Facilities | Amy Treble | 5 | QHP0-A1-70-050 | 1007 |  | QHP0A117050 |  | 0 | 0
QH | QLD Hydro PHES | QH | Program | P0 | Delivery | W01 | Client Costs | A1 | QH Costs | 17000 | 70 | Indirect | 17060 | 060 | A170060 | Vehicles and Transport | Amy Treble | 5 | QHP0-A1-70-060 | 0 |  | QHP0A117060 |  | 0 | 0
QH | QLD Hydro PHES | QH | Program | P0 | Delivery | W01 | Client Costs | A1 | QH Costs | 17000 | 70 | Indirect | 17070 | 070 | A170070 | Portable Long Service Leave Levy | Amy Treble | 5 | QHP0-A1-70-070 | 1060 |  | QHP0A117070 |  | 0 | 0
QH | QLD Hydro PHES | QH | Program | P0 | Delivery | W01 | Client Costs | A1 | QH Costs | 17000 | 70 | Indirect | 17080 | 080 | A170080 | Insurances | Amy Treble | 5 | QHP0-A1-70-080 | 0 |  | QHP0A117080 |  | 0 | 0
QH | QLD Hydro PHES | QH | Program | P0 | Delivery | W01 | Client Costs | A1 | QH Costs | 17000 | 70 | Indirect | 17090 | 090 | A170090 | Finance costs (FBT) | Amy Treble | 5 | QHP0-A1-70-090 | 0 |  | QHP0A117090 |  | 0 | 0
QH | QLD Hydro PHES | QH | Program | P0 | Delivery | W01 | Client Costs | A1 | QH Costs | 17000 | 70 | Indirect | 17100 | 100 | A170100 | Tax expenses | Amy Treble | 5 | QHP0-A1-70-100 | 0 |  | QHP0A117100 |  | 0 | 0
QH | QLD Hydro PHES | QH | Program | P0 | Delivery | W09 | Escalation & Escalation | A9 | Contingency & Escalation |  | 00 |  |  | 000 | A900000 | Contingency & Escalation |  | 3 | QHP0-A9-00-000 | 0 |  | QHP0A9 |  | 0 | 0
QH | QLD Hydro PHES | QH | Program | P0 | Delivery | W09 | Contingency & Escalation | A9 | Contingency & Escalation | 90100 | 91 | Contingency | 90100 | 000 | A991000 |  | Mike Wells | 4 | QHP0-A9-91-000 | 0 |  | QHP0A990100 |  | 0 | 0
QH | QLD Hydro PHES | QH | Program | P0 | Delivery | W09 | Contingency & Escalation | A9 | Contingency & Escalation | 90100 | 91 | Contingency | 90110 | 010 | A991010 | P50 Contingency QH Costs | Mike Wells | 5 | QHP0-A9-91-010 | 0 |  | QHP0A990110 |  | 0 | 0
QH | QLD Hydro PHES | QH | Program | P0 | Delivery | W09 | Contingency & Escalation | A9 | Contingency & Escalation | 90100 | 91 | Contingency | 90120 | 020 | A991020 | P90 Contingency QH Costs | Mike Wells | 5 | QHP0-A9-91-020 | 0 |  | QHP0A990120 |  | 0 | 0
QH | QLD Hydro PHES | QH | Program | P0 | Delivery | W09 | Contingency & Escalation | A9 | Contingency & Escalation | 90200 | 95 | Escalation | 90200 | 000 | A995000 | Escalation | Mike Wells | 4 | QHP0-A9-95-000 | 0 |  | QHP0A990200 |  | 0 | 0
QH | QLD Hydro PHES | QH | Program | P0 | Delivery | W09 | Contingency & Escalation | A9 | Contingency & Escalation | 90200 | 95 | Escalation | 90210 | 010 | A995010 | Escalation QH Costs | Mike Wells | 5 | QHP0-A9-95-010 | 0 |  | QHP0A990210 |  | 0 | 0
QH | QLD Hydro PHES | QH | Borumba PHES | P6 | Close out