## L0 - Program
Group ID | Group Description
QH | QLD Hydro PHES

## L1 - Projects
Group ID | Group Description
BR | Borumba PHES
PB | Pioneer-Burdekin PHES
QH | Program / Corporate

## L2 - Phases
Group ID | Group Description
P0 | Program
P1 | Feasibility Studies
P2 | Options Analysis & DAR
P3 | Design Development & Procurement
P4 | Delivery
P5 | Transition to Operations
P6 | Close-out

## L3 - Area
Group ID | Group Description
A1 | QH Costs
A2 | Surface Infrastructure and Enabling
A3 | Underground Waterways
A4 | Underground Access & Caverns
A5 | Powerhouse Mech & Elec
A6 | Lower Reservoir
A7 | Upper Reservoir
A8 | Transmissions
A9 | Contingency & Escalation

## L3-L4 - Element
Group ID | Group Description
A1-10 | QH Delivery (Staff)
A1-20 | Project Contractors
A1-30 | Engineering
A1-40 | Environment and Approvals
A1-50 | Community Development and Stakeholder
A1-60 | Land Acquisition
A1-70 | Indirect
A1-80 | Ops Readiness & Commissioning
A2-01 | Contractor Indirect & overheads
A2-02 | Design
A2-03 | Camps
A2-04 | Geotechnical
A2-05 | Temporary Water Infrastructure
A2-06 | Communication Infrastructure Upgrade
A2-07 | Power Supply Upgrade
A2-10 | Yabba Creek Road Option 1
A2-12 | Old Forestry Drive Option 2
A2-13 | Yielo Rd
A2-14 | Walkers Top Access Track
A2-15 | Access Roads - The Borgan
A2-16 | Lower Res Access Road
A2-17 | Lower Res Haul Road - Construct and Maintain
A2-18 | Bella Creek Road
A2-19 | Yabba Creek Bridge
A2-20 | Kingaham Creek Bridge
A2-21 | Road to Lower Inlet / Outlet Structure
A2-22 | Road to Upper Res/Saddle Dam
A2-23 | Ring Road at Upper Res incl. Access to upper intake and Bellmouth
A3-01 | Contractor Indirect & overheads stage 1
A3-02 | Design
A3-10 | North Alignment Waterway
A3-20 | South Alignment Waterway
A3-30 | Platform and Control Buildings
A3-40 | Lower Inlet Structure Approach
A3-50 | Surge Tanks Permanent access tunnel
A3-60 | Assembly Chambers
A3-70 | Site Rehabilitation
A4-01 | Contractor Indirect & overheads
A4-02 | Design
A4-03 | Site Clearing
A4-04 | Construction Surface Facilities
A4-05 | ECTV Exploratory Drilling
A4-06 | MAT and ECVT
A4-07 | Power Cavern
A4-08 | Transformer Cavern
A4-09 | IPB Galleries (x 6)
A4-10 | MAT Tunnels between Power Cavern and Transformer Cavern
A4-12 | Site Rehabilitation
A5-01 | Contractor Indirect & overheads
A5-02 | Design
A5-03 | Mech & Elec
A5-04 | Power Turbines
A5-05 | Transformers
A5-06 | Hydro-Mechanical Works
A5-07 | Electrical Install
A5-08 | Power Evacuation and Grid Connection
A5-09 | Commissioning OEM
A5-10 | Site Rehabilitation
A6-01 | Contractor Indirect & overheads
A6-02 | Design
A6-03 | Site Clearing
A6-04 | Quarry Development and Material Operations
A6-05 | Diversion and Watering
A6-06 | Foundations
A6-07 | Dam Construction
A6-08 | Spillway
A6-09 | Intake Tower
A6-10 | Outlet Works
A6-11 | Fishway
A6-12 | Over topping Event of the Lower Dam
A6-13 | Traffic Control
A6-14 | Site Rehabilitation
A7-01 | Contractor Indirect & overheads
A7-02 | Design
A7-03 | Site Clearing
A7-04 | Quarry Development and Material Operations
A7-05 | Diversion and Watering
A7-06 | Foundations
A7-07 | Dam Construction
A7-08 | Emergency Spillway
A7-09 | Traffic Control
A7-10 | Site Rehabilitation
A8-01 | Borumba - Tarong 275kV
A8-02 | Borumba - Woolooga 275kV
A9-91 | Contingency
A9-95 | Escalation

## L3-L5 - Sub Element
Group ID | Group Description
A1-10-010 | Project (Staff)
A1-10-020 | Commercial (Staff)
A1-10-030 | Engineering Assurance (Staff)
A1-10-040 | Health & Safety (Staff)
A1-10-050 | Project Controls (Staff)
A1-10-060 | Environment (Staff)
A1-10-070 | Community and Stakeholder (Staff)
A1-10-080 | Land (Staff)
A1-10-090 | Regional Development (Staff)
A1-10-100 | Quality (Staff)
A1-20-010 | Project Support
A1-20-020 | Commercial Pre-Contracts
A1-20-030 | Commercial - Contracts Admin
A1-20-040 | Project Controls
A1-20-050 | Legal
A1-20-060 | Health and Safety Consultants
A1-20-070 | Engineering Assurance
A1-20-080 | Operation and Maintenance Strategy
A1-30-010 | Specialist Engineering - External Advisory Services
A1-30-020 | Specialist Engineering - Owners Engineer
A1-30-030 | Specialist Engineering - Design for Procurement
A1-30-040 | Specialist Engineering - FEED
A1-30-050 | Specialist Engineering - Exploratory Works
A1-30-060 | Specialist Advisors - Technical Assurance
A1-30-070 | Connection Application Process/Services
A1-30-080 | Independent certifier
A1-40-010 | Technical Advisors - EIS Approvals and Studies
A1-40-020 | EIS - Engineering Input
A1-40-030 | EIS - Technical Studies
A1-40-040 | Exploratory Works Approvals
A1-40-050 | Main Works - Approvals
A1-40-060 | Offset Implementation
A1-40-070 | Sustainability
A1-40-080 | Office of the Coordinator-General (OCG Costs)
A1-40-090 | EIS - Delivery
A1-40-100 | GIS Support
A1-40-110 | Cultural Heritage - Investigations and Monitoring
A1-40-120 | Indigenous Land Use Agreement
A1-40-130 | Compliance Monitoring
A1-40-140 | Indigenous Partnerships
A1-50-010 | Community and Stakeholder Consultants
A1-50-020 | Community Benefits Program
A1-50-030 | Sponsorships
A1-50-040 | Community Engagement Program
A1-50-050 | Regional Development
A1-50-060 | Regional Development Accommodation Partners
A1-50-070 | Regional Development Community Infrastructure
A1-50-080 | Regional Development - Community Development Initiatives (GRC)
A1-50-090 | Regional Development - Community Development Initiatives (SRC)
A1-60-010 | Land Access & Conveyancing
A1-60-020 | Land Acquisition
A1-60-030 | Land Access - Specialist Advisors
A1-70-010 | Project Expenses – General
A1-70-020 | PPE
A1-70-030 | Emergency Response Plan
A1-70-040 | Travel, Accommodation & Disbursements
A1-70-050 | IT Software, Licenses & Equipment
A1-70-060 | Training & Development (Delivery)
A1-70-070 | Mandatory Safety Training
A1-70-080 | Site Vehicles and Transport
A1-70-090 | Project Offices and Facilities
A1-70-100 | Portable Long Service Leave Levy
A1-70-110 | Insurances
A1-70-120 | Bid cost reimbursement
A1-70-130 | Site Equipment & Tooling
A1-70-140 | Corporate Overheads
A1-70-150 | Legal Costs
A1-70-160 | Site Communications
A1-70-170 | Finance costs (FBT)
A1-70-180 | Other Staff Costs (memberships, subscriptions)
A1-80-010 | Op Readiness
A1-80-020 | Commissioning
A1-80-030 | Full Load Compliance Testing
A2-01-010 | Temporary Camps - Indirects and Overheads
A2-01-020 | Main Camps - Indirects and Overheads
A2-01-030 | Exploratory Works - Contractor Indirect & overheads
A2-01-040 | Enabling Works - Contractor Indirect & overheads
A2-02-010 | Design - Exploratory Works
A2-02-020 | Design - Enabling Works
A2-02-030 | Temp Camps Design
A2-03-010 | Temp Camps
A2-03-020 | Upper Res Camps Hardstand
A2-03-030 | Lower Res Camps Hardstand
A2-03-040 | Main Camps Hardstand
A2-03-050 | Upper Res Camps Install and Operate
A2-03-060 | Lower Res Camps Install and Operate
A2-03-070 | Main Camps Install and Operate
A2-03-080 | Camp Set up
A2-04-010 | Contractor Indirect & overheads
A2-04-020 | Geotechnical Studies
A2-04-030 | Geotechnical Drilling
A2-04-040 | Geotechnical Service Management
A2-05-010 | Preliminaries Temporary Water Infrastructure
A2-05-020 | Temporary Water Infrastructure
A2-05-030 | Temporary Water Supply
A2-06-010 | Preliminaries Communication Infrastructure Upgrade
A2-06-020 | Communication Infrastructure Upgrade
A2-07-010 | Preliminaries Power Supply Upgrade
A2-07-020 | Power Supply Upgrade
A2-10-010 | Preliminaries Yabba Ck Rd Option 1
A2-10-020 | Bridge 1 (on Yabba Ck Rd - Ana Branche No 1)
A2-10-030 | Bridge 2 (on Yabba Ck Rd - Ana Branche No 2)
A2-10-040 | Bridge 3 (on Yabba Ck Rd - No 1 Crossing - Neumans Crossing)
A2-10-050 | Bridge 4 (on Yabba Ck Rd - No 2 Crossing - Elbow Crossing)
A2-10-060 | Bridge 5 (on Yabba Ck Rd - No 3 Crossing - Andrews Crossing)
A2-10-070 | Bridge 6 (on Yabba Ck Rd - No ? Crossing - ????)
A2-10-080 | Bridge 7 (on Yabba Ck Rd - No 4 Crossing - Boardmans Crossing)
A2-10-090 | Bridge 8 (on Yabba Ck Rd - No 5 Crossing - Friends Crossing)
A2-10-100 | Bridge 9 (on Yabba Ck Rd - No 6 Crossing - Deep Crossing)
A2-10-110 | Bridge 10 (on Yabba Ck Rd - No 7 - Crossing - unknown name)
A2-10-120 | Upgrade Bella Creek Road intersection
A2-12-010 | Preliminaries Old Forestry Drive Option 2
A2-12-020 | Old Forestry Drive Option 2 Construction
A2-13-010 | Preliminaries Upgrade of Yielo Rd
A2-13-020 | Upgrade of Yielo Rd Construction
A2-14-010 | Preliminaries Walkers Top Access Track
A2-14-020 | Walkers Top Access Track Construction
A2-15-010 | Preliminaries Access Roads - The Borgan
A2-15-020 | Access Roads - The Borgan
A2-16-010 | Lower Res Access Road
A2-17-010 | Lower Res Haul Road - Construct and Maintain
A2-18-010 | Bella Creek Road
A2-19-010 | Yabba Creek Bridge
A2-20-010 | Kingaham Creek Bridge
A2-21-010 | Road to Lower Inlet / Outlet Structure
A2-22-010 | Road to Upper Res/Saddle Dam
A2-23-010 | Ring Road at Upper Res incl. Access to upper intake and Bellmouth
A2-24-010 | MAT / ECVT Portal Pad Excavation
A3-01-110 | Contractor Indirects & overheads
A3-02-210 | Design
A3-10-010 | Upper Inlet/Outlet Structure Bellmouth - North
A3-10-020 | Upper Inlet/Outlet Structure Gate Shaft - North
A3-10-030 | Lower Inlet/Outlet Structure Bellmouth - North
A3-10-040 | Lower Inlet/Outlet Structure Gate Shaft Middle to Top - North
A3-10-050 | Lower Inlet/Outlet Structure Gate Shaft Lower Part/Square Section - North
A3-10-060 | Low Pressure Tunnel - North
A3-10-070 | Erection Chamber - Upper - North
A3-10-080 | Vertical Pressure Shaft - North
A3-10-090 | Erection Chamber - Lower - North
A3-10-100 | High Pressure Tunnel - North
A3-10-110 | Penstock Steel Lined - North
A3-10-120 | Tailrace Collector Tunnel - North
A3-10-130 | Tailrace Tunnel - North
A3-10-140 | Surge Tank - North
A3-20-010 | Upper Inlet/Outlet Structure Bellmouth - South
A3-20-020 | Upper Inlet/Outlet Structure Gate Shaft - South
A3-20-030 | Lower Inlet/Outlet Structure Bellmouth - South
A3-20-040 | Lower Inlet/Outlet Structure Gate Shaft Middle to Top - South
A3-20-050 | Lower Inlet/Outlet Structure Gate Shaft Lower Part/Square Section - South
A3-20-060 | Low Pressure Tunnel - South
A3-20-070 | Erection Chamber - Upper - South
A3-20-080 | Vertical Pressure Shaft - South
A3-20-090 | Erection Chamber - Lower - South
A3-20-100 | High Pressure Tunnel - South
A3-20-110 | Penstock Steel Lined - South
A3-20-120 | Tailrace Collector Tunnel - South
A3-20-130 | Tailrace Tunnel - South
A3-20-140 | Surge Tank - South
A3-30-010 | Upper Inlet/Outlet Platform and Control Building
A3-30-020 | Lower Inlet/Outlet Platform and Control Building
A3-40-010 | Lower Inlet/Outlet Structure - Approach
A3-50-010 | Surge Tanks Permanent access tunnel
A3-60-010 | Upstream Assembly Chambers, Connection Tunnels and Adit
A3-60-020 | Downstream Assembly Chambers, Connection Tunnels and Adit
A3-70-010 | Site Rehabilitation
A4-01-010 | Contractor Indirects & overheads
A4-02-010 | Detail Design - Main Facility
A4-02-020 | Detail Design - OEM
A4-03-010 | Site Clearing
A4-04-010 | Construction Site Facilities - Platform Areas
A4-04-020 | Grout plant - mobilise and demobilise
A4-04-030 | Construction Site Facilities - Platform 2 - Concrete Plant
A4-04-040 | Concrete batching plant - mobilise and demobilise
A4-04-050 | Construction Site Facilities - Upper inlet / outlet - Concrete Plant
A4-05-010 | Exploratory Tunnel - Surface Works
A4-05-020 | Exploratory Tunnel - Underground Works
A4-05-030 | Exploratory Tunnel - Caverns Investigation
A4-05-040 | Exploratory Tunnel - Management Services
A4-06-010 | Main Access Tunnel (MAT)
A4-06-020 | Emergency, Cable and Ventilation Tunnel (ECVT) Completion
A4-07-010 | Power Cavern
A4-08-010 | Transformer Cavern
A4-09-010 | IPB Galleries (x 6)
A4-10-010 | MAT Tunnels between Power Cavern and Transformer Cavern
A4-12-010 | Site Rehabilitation
A5-01-010 | Contractor Indirects & overheads
A5-02-010 | Design
A5-03-010 | Mech & Elec
A5-04-010 | Power Turbines
A5-05-010 | Transformers
A5-06-010 | Hydro-Mechanical Works
A5-07-010 | Electrical Install
A5-08-010 | Power Evacuation and Grid Connection
A5-09-010 | Commissioning OEM
A5-10-010 | Site Rehabilitation
A6-01-010 | Contractor Indirect & overheads
A6-02-010 | Design
A6-03-010 | Site Clearing
A6-04-010 | Quarry Development and Material Operations
A6-05-010 | Diversion and Watering
A6-06-010 | Foundations
A6-07-010 | Dam Construction
A6-08-010 | Spillway
A6-09-010 | Intake Tower
A6-10-010 | Outlet Works
A6-11-010 | Fishway
A6-12-010 | Over topping Event of the Lower Dam
A6-13-010 | Traffic Control
A6-14-010 | Site Rehabilitation
A7-01-010 | Contractor Indirect & overheads
A7-02-010 | Design
A7-03-010 | Site Clearing
A7-04-010 | Quarry Development and Material Operations
A7-05-010 | Diversion and Watering
A7-06-010 | Foundations
A7-07-010 | Main CFRD Dam
A7-07-020 | Main Saddle (CFRD) Dam
A7-07-030 | Secondary Saddle (CFRD) Dam A
A7-07-040 | Secondary Saddle (CFRD) Dam B1
A7-07-050 | Secondary Saddle (CFRD) Dam B2
A7-07-060 | Secondary Saddle (CFRD) Dam No.B3
A7-08-010 | Emergency Spillway
A7-09-010 | Traffic Control
A7-10-010 | Site Rehabilitation
A8-01-010 | Borumba - Tarong 275kV
A8-02-110 | Borumba - Woolooga 275kV
A9-91-010 | P50 Contingency QH Costs
A9-91-020 | P90 Contingency QH Costs
A9-91-030 | P50 Contingency Surface Infrastructure and Enabling
A9-91-040 | P90 Contingency Surface Infrastructure and Enabling
A9-91-050 | P50 Contingency Underground Waterways
A9-91-060 | P90 Contingency Underground Waterways
A9-91-070 | P50 Contingency Underground Access & Caverns
A9-91-080 | P90 Contingency Underground Access & Caverns
A9-91-090 | P50 Contingency Powerhouse Mech & Elec
A9-91-100 | P90 Contingency Powerhouse Mech & Elec
A9-91-110 | P50 Contingency Lower Reservoir
A9-91-120 | P90 Contingency Lower Reservoir
A9-91-130 | P50 Contingency Upper Reservoir
A9-91-140 | P90 Contingency Upper Reservoir
A9-95-010 | Escalation QH Costs
A9-95-020 | Escalation Surface Infrastructure and Enabling
A9-95-030 | Escalation Underground Waterways
A9-95-040 | Escalation Underground Access & Caverns
A9-95-050 | Escalation Powerhouse Mech & Elec
A9-95-060 | Escalation Lower Reservoir
A9-95-070 | Escalation Upper Reservoir